### শুদ্ধাচার কর্মপরিকল্পনা

National Integrity Strategy work plan

Ministry of Science & Technology

- The Ministry

| Mission | Support attainment of overall socio -economic development of the country through research, development, extension and successful utilization of science and technology |
| --- | --- |
| Major Functions | - Formulate national policies on science and technology and coordinate science and technology based initiatives and activities of different Ministries; - Implementation of recommendations of the National Council for Science and Technology (NCST) ; - Provide grants and overall assistance to agencies /institutions in the science and technology sector, including non-government scientific organisations /societies, undertake surveys, research and development in the science and technology sector and provide access to funding for such activities; - Liaise with different countries and international organisations in the science and technology sector and also implement agreements and assistance programmes in relevant sectors; - Activities relating atomic security and radiation control and establishment of atomic power plants; - Coordinate potential and new technology-based research activities including marine resources, chemical metrology, biology, electronics and industry and assist in the development of the related infrastructure and human resources; - Promote, extend and popularise new science related initiatives and organise an annual National Science and Technology Week with support from research and educational institutions |
| Strategic Objectives | - Capacity building in the research process on science and technology. - Development of infrastructure for expansion of science and technology. - Promoting and applying environment-friendly and sustainable technology for socio-economic development. - Enhanced application of nuclear technology for medical diagnosis and treatment. - Peaceful use of nuclear energy. |
| Departments/Units | - Bangladesh Atomic Energy Commission - Bangladesh Atomic Energy Regulatory Authority - National Museum of Science & Technology - National Institute of Biotechnology - Bangabandhu Sheikh Mujibur Rahman Novotheatre - Bangladesh Council of Scientific and Industrial Research ( BCSIR) - Bangladesh National Scientific & Technical Documentation Centre (BANSDOC) |

NIS Action Plan

2) Institutional Arrangements

a)

| Activities (Ministry Level) | Time frame | Baseline (December 2014) | Target | Official In charge |
| --- | --- | --- | --- | --- |
| Formation of Ethics committee | Done (May 2013) | N/A | N/A | Secretary Most |
| Holding Ethics committee Meeting | Continuous | 4 | 6 / Year | Admin Wing NIS Focal Point |
| Formations of Ethics committee at Department Level | Done (Dec 2014) | 07 | 07 | Concern Department Heads |
| Formation of Innovation Team | DEC 2014 | Done | N/A | Secretary MOST |
| Identify Stakeholders concern to NIS Implementation | March 2015 | Done | N/A | Admin Wing NIS Focal Point |

b)

| Activities (Department Level) | Time Frame | Baseline No | Target No | Official In Charge |
| --- | --- | --- | --- | --- |
| Formation of Ethics Committee at seven Departments/Units | Dec 2014 Done | 07 | 07 | Respective Department Heads |

3) Awareness & Capacity Building

| Activities | Time Frame | Baseline (March 2015) | Target No | Official In charge |
| --- | --- | --- | --- | --- |
| NIS orientation Workshop for Ministry Officials | March 2015 | 30 Officials | 30 Officials | Admin Wing NIS Focal Point |
| NIS orientation workshop for Department officials | Dec 2014 | 40 Officials | 40 Officials | Respective Department Heads |

4) E- Governance (Ministry Level)

| Activities | Time Frame | Baseline No | Target No 24/Year | Official In charge |
| --- | --- | --- | --- | --- |
| Website Update | Fortnightly | N/A | 24/Year | Chief Innovation Officer Programmer MOST |
| Maintenance of E mail Accounts | March 2015 Done | N/A | All officers of MOST | All officers of MOST |

5) Grievances  Redress System

| Activities | Time Frame March 2015 | Baseline No | Target No | Official In charge |
| --- | --- | --- | --- | --- |
| Appointment of Focal Point | Done | 1 | 1 | Admin Wing NIS Focal Point |

6) Audit Objection Disposal

| Activities | Time Frame | Baseline No | Target No | Official In charge |
| --- | --- | --- | --- | --- |
| Holding Tri-Party Meeting | June 2016 | ----------------- | One Meeting/Month | Admin Wing MOST |

7) Right to Information

| Activities | Time Frame | Baseline No | Target No | Official In charge |
| --- | --- | --- | --- | --- |
| Proactive Disclosure | On Going | ----------------------- | As Much | Chief Innovation Officer MOST |

8) Monitoring & Evaluation

| Activities | Time Frame | Baseline No | Target No | Official In charge |
| --- | --- | --- | --- | --- |
| Interim Evaluation | Dec 2015 | --------------------------- | ---------------------------- | Ethics Committee MOST |