Investing for impact against HIV, tuberculosis or malaria

A concept note outlines the reasons for Global Fund investment. Each concept note should describe a strategy, supported by technical data that shows why this approach will be effective. Guided by a national health strategy and a national disease strategic plan, it prioritizes a country’s needs within a broader context. Further, it describes how implementation of the resulting grants can maximize the impact of the investment, by reaching the greatest number of people and by achieving the greatest possible effect on their health.

A concept note is divided into the following sections:

Section 1:	A description of the country’s epidemiological situation, including health systems and barriers to access, as well as the national response.

Section 2:	Information on the national funding landscape and sustainability.

Section 3:	A funding request to the Global Fund, including a programmatic gap analysis, rationale and description, and modular template.

Section 4:	Implementation arrangements and risk assessment.

STANDARD

CONCEPT NOTE

| SUMMARY INFORMATION |  |  |  |
| --- | --- | --- | --- |
| Applicant Information |  |  |  |
| Country | Bangladesh | Component | Malaria |
| Funding Request Start Date | 2015 (July) | Funding Request End Date | 2018 (June) |
| Principal Recipient(s) | The Economic Relations Division, Ministry of Finance, The Government of the People's Republic of Bangladesh; Bangladesh Rural Advancement Committee (BRAC) |  |  |

IMPORTANT NOTE: This template and core tables are subject to minor changes pending further decisions to be taken in early 2014.

Applicants should refer to the Standard Concept Note Instructions to complete this template.

THIS IS DRAFT IN PROGRESS…

Funding Request Summary Table *

A funding request summary table will be automatically generated in the online grant management platform based on the information presented in the programmatic gap table and modular templates.  Detailed information will be provided in early 2014.

SECTION 1: COUNTRY CONTEXT

This section requests information on the country context, including the disease epidemiology, the health systems and community systems setting, and the human rights situation. This description is critical for justifying the choice of appropriate interventions.

1.1 Country Disease, Health and Community Systems Context

With reference to the latest available epidemiological information, in addition to the Portfolio Analysis provided by the Global Fund, highlight: - The current and evolving epidemiology of the disease(s) and any significant geographic variations in disease risk or prevalence. - Key affected populations that may have disproportionately low access to prevention and treatment services (and for HIV and TB, the availability of care and support services), and the contributing factors to this inequality. - Key human rights barriers and gender inequalities that may impede access to health services. - The health systems and community systems context in the country, including any constraints.

Malaria is an entirely preventable and treatable disease, provided the currently recommended interventions are properly implemented. These interventions include (i) vector control through the use of insecticide treated nets (ITNs), indoor residual spraying (IRS) and, in some specific settings, larval control; (ii) chemoprevention for the most vulnerable populations, particularly pregnant women and infants; (iii) confirmation of malaria diagnosis through microscopy or rapid diagnostic tests (RDTs) for every suspected case; and (iv) timely treatment with appropriate antimalarial medicines (according to the parasite species). In 2013, there are 97 countries and territories with ongoing malaria transmission, and 7 countries in the prevention of reintroduction phase, making a total of 104 countries and territories in which malaria is presently considered endemic. Globally, an estimated 3.4 billion people are at risk of malaria in 2012. Of this total, the 1.2 billion at high risk (>1 case per 1000 population) were living mostly in the African Region (47%) and the South-East Asia Region (37%). The WHO estimates that 207 million cases of malaria occurred globally in 2012 (uncertainty range 135–287 million) and 627 000 deaths (uncertainty range 473 000–789 000) [Chapter 8; Section 8.3]. Most cases (80%) and deaths (90%) occurred in Africa (Figure 1.1), and most deaths (77%) were in children under 5 years of age. In Bangladesh, malaria is endemic in 13 eastern and north-eastern border belt districts of the country with variable transmission potentials (high, moderate and low). A total of 13.25 million people are at risk of malaria inhabited in those districts. In 2013 the prevalence rate of malaria was found to be 0.7% in these districts. About 80% of the total cases are reported from the three Chittagong Hill Tract (CHT) districts (Rangamati, Khagrachari and Banderban) including Chittagong and the coastal district Cox’s Bazar. The CHT districts have perennial transmission throughout the year due to the geo-physical location in the hilly, forested and the foot-hills, climate, and other favourable conditions for the vector species An. baimi (dirus), An. minimus and An. philippinensis. The map of Bangladesh blow shows the malaria endemic areas (high, moderate, low, pre-elimination districts, and malaria free) based on available epidemiological data. Key Information: Area- Population.- Divisions-7 Districts-64 Upazila-483 Total endemic districts-13 High endemic districts-3 Moderate/Low endemic-10 Cases in 2013: Total- P. falciparum- P.vivax- Mixed- Principal vectors: An. baimaii, An philippinensis, An. minimus, An. sundicus LLINs/ITNs Coverage: 100% in high endemic areas 80% in Low endemic areas. Total population of the three CHT districts is 1.6 million. The indigenous population constitutes about 50% of the total population in these districts. The tribal hamlets are in clusters in the remote hills and foothills and some are hard-to-reach due to lack of communication. Most of the houses are thatched built with indigenous material e.g. bamboo, wood etc. and these houses seldom have any protection against the vector mosquitoes and thus peoples are vulnerable to malaria infection. The aggregation of laborers for development work sometimes further aggravates the malaria situation in these areas. Settlers coming from the plain areas of the country in the CHT districts are non-immune and more prone to get malaria infection. Traditional ‘Jhum cultivators’, forest goers, refugees, travelers from non-endemic areas, and mobile population are the most-at-risk groups due to lack of adequate protection for mosquito bites and adoption of personal protection measures. There are also higher risk of malaria transmission in the border areas, due to cross-border movement/migration across international boundaries with eastern districts of Bangladesh and part of Myanmar. Four districts (Mymensingh, Netrakona, Sherpur and Kurigram) with eight endemic upazilas have low transmission of malaria and have shown <5% malaria positivity rates (RDT and Microscopy) over last three years. These districts currently may be considered for adopting pre-elimination strategies. The NMCP should have phased targets of elimination for these districts and gradually expanding to the other moderate endemic areas in near future. There is significant progress in malaria control in Bangladesh during the period from 2008 to 2013 showing a progressive decline in total cases and deaths. The graph below shows the epidemiological trend of case incidence and deaths 2007-2013. Figure: Malaria cases and deaths from 2007 to 2013 The NMCP had the GFATM support since 2007 and there was an increase in number of cases due to scaling up of interventions; introduction of RDR for diagnosis, and ACT for treatment of P. falciparum cases. Thereafter, a steady decline is noted from 59,857 cases in 2007 to 26,891 cases in 2013, having nearly …. reduction. The total deaths came down to 15 as against 228 showing a reduction of …%. The table below shows District-wise epidemiological data of the 13 endemic districts for three consecutive years for a comparision based on total cases, API, and the proportional contribution to the burden of malaria in the country. District-wise Epidemiological data (13 Districts) : 2011-2013 District; Population; 2013 (up to Sep); 2012; 2011. Total Cases; API; National Burden (%); Total Cases; API; National Burden (%); Total Cases; API; National Burden (%). Sherpur; 442,098; 32; 0.07; 0.16; 73; 0.17; 0.25; 68; 0.15; 0.13. Mymensingh; 461,000; 63; 0.14; 0.31; 168; 0.36; 0.57; 244; 0.53; 0.47. Netrokona; 436,260; 107; 0.25; 0.53; 285; 0.65; 0.97; 270; 0.62; 0.52. Kurigram; 225,000; 53; 0.24; 0.26; 101; 0.45; 0.34; 168; 0.75; 0.32. Sylhet; 657,480; 326; 0.50; 1.62; 436; 0.66; 1.48; 444; 0.68; 0.86. Hobigonj; 405,000; 31; 0.08; 0.15; 72; 0.18; 0.24; 65; 0.16; 0.13. Sunamgonj; 1,436,808; 422; 0.29; 2.09; 540; 0.38; 1.83; 461; 0.32; 0.89. Moulvibazar; 1,048,191; 161; 0.15; 0.80; 421; 0.40; 1.43; 448; 0.43; 0.87. Chittagong; 2,946,901; 456; 0.15; 2.26; 1,095; 0.37; 3.71; 1,415; 0.48; 2.73. Khagrachari; 540,192; 3,122; 5.78; 15.49; 5,997; 11.10; 20.32; 12,952; 23.98; 25.02. Rangamati; 548,762; 5,833; 10.63; 28.93; 7,981; 14.54; 27.04; 13,669; 24.91; 26.40. Bandarban; 314,291; 7,041; 22.40; 34.93; 8,461; 26.92; 28.66; 16,097; 51.22; 31.09. Cox's bazar; 1,500,047; 2,513; 1.68; 12.47; 3,888; 2.59; 13.17; 5,472; 3.65; 10.57. Total; 10,962,030; 20,160; 1.84; 29,518; 2.69; 51,773; 4.72. TO BE UPDATED……….. AN ANALYSIS TO BE ADDED HERE IN THE CHANGING PATTERN OF ……. A shift in paradigm is noted that about 95% cases detected are P. falciparum infections. However, the P.vivax diagnosis needs to be strengthened and institute more efforts for treatment in order to address this problem. There is a wide variation in malaria incidence between the sexes and across age groups. During the 2008-2013, males consistently had more positive diagnoses than females; adult age group suffered more than the other age groups but the incidence of cases in three age groups (0-4yr, 5-15yr and 15+ yrs) were almost same. Bangladesh is also on track to achieving the malaria MDGs Goals, and Targets. The Table below shows the status of MDG goals and targets related to malaria in 2012-13 as compared to baseline 2008. Malaria MDG Goals and Targets MDG Goals, Targets and Indicators; Baseline 2008; Current Status (2012-2013); Target 2015. 6.6a: Prevalence of Malaria per 100,000 population; 776; 271; 310. 6.6b: Deaths of Malaria per 100,000 population; 1.4; 0.1; 0.6. 6.7: Proportion of children U-5 sleeping under insecticide treated bed nets; 81%; 94.4%; 90%. 6.8: Proportion of children U-5 who are treated with appropriate anti malarial drugs; 60%; 89.5%; 90%. The Global Fund has been supporting the National Malaria Program in Bangladesh since the approval of Round 6 malaria proposal in 2006. The goal of the program is to reduce overall burden of malaria morbidity and mortality) by 60% from baseline year 2008 in 10.9 million people in 13 high endemic districts of Bangladesh by 2015. The Round 6 and Round 9 grant have been consolidated and has helped streamline the areas of national interventions through economies of scale and scope in both programmatic and financial areas of the national program. The PR of this consolidated grant is Bangladesh Rural Advancement Committee (BRAC), in close collaboration with the other PR, Economic Relations Division, Ministry of Finance of the Government of Bangladesh with the Malaria and Parasitic Diseases Control (M&PDC) of the Ministry of Health and Family Welfare as implementing agency, and Sub-recipients from private and non-governmental organizations. The budgetary efficiencies gained from the consolidation were partially ploughed back to strengthening Procurement Management Systems (PMS), introducing gender-based approach to programming and increasing enhanced multisectoral M&E of the National Malaria Program in Bangladesh. The aim of the Round 6 program was primarily focused on early diagnosis of uncomplicated P. falciparum malaria through the introduction of Rapid Diagnostic Tests (RDT) with improved microscopy and case management and promotion of Long Lasting Insecticide Nets (LLINs)/Insecticide Treated Nets (ITNs) with the goal of reducing malaria in the 13 high endemic districts by 50%. The Round 9 program complements and supplements the critical gaps that were not addressed in the Round 6 program by scaling up the use of LLINs, two per household, to achieve 100% coverage in three highly endemic districts, expand and improve quality of diagnosis and treatment to 90% of malaria cases and further strengthen and enhance the program management capacity, coordination and partnership of the malaria control program of Bangladesh. Population at Risk; key population The total population at risk of malaria in the 13 endemic districts is approximately 13.25 million. (Ref:UZ/union-wise population- attached). About 80% of the cases of malaria in Bangladesh are reported from the three CHT districts with a total population of about 1.6 million. The indigenous population constitutes about 50% of the total population in CHT districts. The tribal hamlets are in clusters in the remote hills and foothills. Most of the houses are thatched built with indigenous material e.g. bamboo, wood etc. and these houses seldom have any protection against the vector mosquitoes. The peoples are vulnerable to malaria infection. The aggregation of laborers for development work sometimes further aggravates the malaria situation in these areas. Settlers coming from the plain areas of the country in the hill district are non-immune and more prone to get malaria infection. Seasonal workers such as Jhum cultivators, forest goers etc. are at high risk group due to staying overnight in open spaces in the forest and hill. There are higher than average levels of malaria in border areas which may be due to migration to and from endemic areas of neighboring Bangladesh and Myanmar. Key populations are groups that face an increased burden and/or vulnerability due to a combination of biological, socioeconomic, and structural factors combined with lower access to services. Malaria affects all age groups and both males and females; however, adult males are commonly affected mainly due to occupations and behavior that put them at risk of being bitten by malaria vectors. Pregnant women and children <5 yrs are biologically at higher risk and they tend to develop more severe malaria due to low level of immunity. Thus, in high transmission areas, these groups should be given priority for interventions. High risk populations (key population) includes: - Young children, particularly under <5 yr children - Pregnant women - Travelers from non-endemic areas - People from non-endemic areas residing for a long time and returning home - Jhum cultivators and forest goers - Refugees and mobile population - People with HIV/AIDS Most malaria cases and deaths probably occur among these key populations, as malaria transmission is intense in areas inhabited/frequented by them. Hence, they remain central in the fight against malaria. In cases where women do not enjoy the same rights, opportunities, and access to services as men, placing them at a greater risk and at a disadvantage with respect to treatment and care as well as in cases where gender norms for men often puts pressure and discourages health-seeking or other positive health behaviors create health vulnerabilities for both women and men, varied responses from health systems and consequently health outcomes are affected. Women and girls are at particular risk for malaria during pregnancy with an associated increased risk of death or adverse birth outcomes. Gender inequalities that sometimes hinder effective responses to malaria and health vulnerabilities for both women and men (‘jhum’ cultivators, wood cutters, other travelers) are addressed by the National Malaria Control Programme by strengthening/orienting the program implementation to ensure right to health of women and girls as well as men and boys. As mentioned above, they remain key populations. While recognizing that strategic, high-impact, gender-responsive investments will prevent new cases of malaria and save lives, the gender dynamics within the epidemic are assessed and any identified issue is appropriately responded to with mix of approaches that is most appropriate to the specific epidemiological and social context. Capacity is also build to design and implement gender-responsive programming at all level. Progressively, it is being ensured that gender norms/traditional power dynamics impeding women’s ability to protect them are taken of and women are able to utilize insecticide treated nets (ITNs), to receive antenatal care, or to take their malaria-stricken children to health services without any inhibition. In addition, men who are at higher risk if they work in mines, fields or forests at peak biting times, are also having access to health care services and effective tools. The NMCP and BRAC have integrated gender indicators and gender-responsive monitoring and evaluation into NSP 2014-20. The outcome indicator is ‘Proportion of pregnant women who slept under an ITN the previous night’; in addition to collation of age- and sex-disaggregated routine data, amongst others. LLIN/ITN usage among high-risk pregnant women and children under 5 has reached to desired level. Beneficiaries report high levels of satisfaction with the services offered through the programme [Client Satisfaction Survey-NMCP, 2010 (Annex)]. The grant cycle has been aligned with the country fiscal cycle. The CCM proposal highlighted the process of discussion and coordination among all the major stakeholders of the Malaria program. Through such coordination the value of the investments for the Program is maximized by avoiding the duplication of components under different grants. The CCM proposal also highlights the coordination and alignment between different donor funded programs, e.g. alignment between the Health Population and Nutrition Sector Development Program (HPNSDP), supported by the donors’ pool fund through World Bank, WHO aid and the Global Fund supported program. The grants from other donors and the Government’s own fund (HNPSP, World Bank and WHO) are also aligned with that of the Global Fund grants to avoid any duplication of activities. As an example, the Armed Forces, Border Guards and Police Force members working in the hill tracts were not covered by LLIN under the Global Fund grant. The government has therefore planned to provide LLINs to these people from HNPSP fund. The drugs used for vivax malaria treatment (Chloroquine and Primaquine) are also procured from HNPSP fund. The partnership mechanism includes broad representation from GOB, NGOs, WHO and the private sector. Activities implemented by NMCP, BRAC and its SRs, along with WHO are closely interlinked. Coordination among partners in a harmonized way helps to improve equitable access and provision of malaria services to the people affected with malaria in the country. Health systems and community systems: The government of Bangladesh is now implementing the sector wide program (HNPSP). The Malaria Control Program activities are integrated with HNPSP and the primary health care services delivery. The main weaknesses of and/or gaps in the health system that affect malaria outcomes are: Issues that are common to malaria, tuberculosis and HIV programming and service delivery: - Inadequate access to treatment especially in hard-to-reach, border areas and tribal population areas. - Inadequate diagnostic provisions in the community and health facilities. - No effective referral services and poor severe malaria management in hospitals. - Vacancies /under staffing especially at the hard to reach areas; inadequate trained personnel and frequent turnover. - Lack of timeliness and incomplete health and disease surveillance - Inadequate monitoring and evaluation of health system and health programs regarding output, outcome and impact. - Inadequate linkages with private health providers - Inadequate linkage between different health departments and programs and other development sectors Issues that are relevant to the health system and malaria outcomes: - Additional LLINs were not included to achieve 100% coverage of HHs in high endemic districts (only 40% were planned in R-6); no cost for storage and distribution; replacement of ITNs by LLINs and withdrawal and replacement of LLINs after expiry; - Diagnostic facility for P. vivax malaria at community level is not available. Availability of Pan-RDT at community level will increase access to diagnosis and treatment of both P. vivax and P. falciparum malaria. - Low access to diagnosis and treatment of vulnerable groups. - Absence of pre-referral treatment for severe malaria at the community level; inadequate referral linkages; and case management of severe malaria in hospital is not optimal. - Inadequate program and health system management capacity - Lack of linkage between malaria control with reproductive health care and IMCI services - Lack of effective linkage between malaria control and other sectors such as education and agriculture The ongoing malaria control program is addressing some of the weaknesses/gaps. Efforts were also taken to cover some of the issues in the R-6 proposal. Access to treatment with effective antimalarials has been expanded; 203 microscopy centres operating; and RDT for P. falciparum malaria has been provided in the community. Treatment with ACT has been extended to the community level by both GoB and NGOs. Health workers and volunteers have been recruited and trained to carry out the activities by NGOs. To improve the partnership a consortium has been formed with 21 NGOs with BRAC as a lead NGO. PSM plan has been developed to ensure un-interrupted supply of LLINs, drugs, diagnostics and logistics. M&E plan has been developed to strengthen the tracking of outputs, outcome and impact. Baseline survey for malaria prevalence has been completed by GoB, ICDDR,B and PR-NGO. Program management capacity has been improved by recruiting human resources. Capacity building with refresher training of health workers and managers at different levels were carried out by both GoB and NGOs. The HNPSP endorses priority on control of vector borne diseases and to reduce malaria specific morbidity and mortality through improved access to EDPT and promotion of LLINs in collaboration with NGOs (Annex-15). HNPSP supports for training and improving coordination under Line Director, Disease Control to mitigate some of these gaps in the malaria program. WHO provides technical support for the areas related to Monitoring and Evaluation, Drug Resistance Monitoring; and capacity development at the national level. Institutions/group like Malaria Research group (MRG); Bangladesh Institute of Tropical and Infectious Diseases (BITID); Institute of Epidemiology, Disease Control and Research (IEDCR); National Institute of Preventive and Social Medicine (NIPSOM); and International Center for Diarrhoeal Disease Research, Bangladesh (ICDDR,B) are collaborating in the areas of research and training and supporting to address identified gaps in implementation of the malaria program. The Government of Bangladesh is implementing the sector wide program (HNPSP). The Malaria Control Program activities are integrated with HNPSP and the primary health care services delivery. The main weaknesses of and/or gaps in the health system that affect malaria outcomes are: Issues that are common to malaria, tuberculosis and HIV programming and service delivery: - Inadequate access to treatment especially in hard-to-reach, border areas and tribal population areas. - Inadequate diagnostic provisions in the community and health facilities. - No effective referral services and poor severe malaria management in hospitals. - Vacancies /under staffing especially at the hard to reach areas; inadequate trained personnel and frequent turnover. - Lack of timeliness and incomplete health and disease surveillance - Inadequate monitoring and evaluation of health system and health programs regarding output, outcome and impact. - Inadequate linkages with private health providers - Inadequate linkage between different health departments and programs and other development sectors Issues that are relevant to the health system and malaria outcomes: - Additional LLINs were not included to achieve 100% coverage of HHs in high endemic districts (only 40% were planned in R-6); no cost for storage and distribution; replacement of ITNs by LLINs and withdrawal and replacement of LLINs after expiry; - Low access to diagnosis and treatment of vulnerable groups. - Absence of pre-referral treatment for severe malaria at the community level; inadequate referral linkages; and case management of severe malaria in hospital is not optimal. - Inadequate program and health system management capacity - Lack of linkage between malaria control with reproductive health care and IMCI services - Lack of effective linkage between malaria control and other sectors such as education and agriculture The ongoing malaria control program is addressing some of the weaknesses/gaps. Efforts were also taken to cover some of the issues in the R-6 proposal. Access to treatment with effective antimalarials has been expanded; 203 microscopy centres operating; and RDT for P. falciparum malaria has been provided in the community. Treatment with ACT has been extended to the community level by both GoB and NGOs. Health workers and volunteers have been recruited and trained to carry out the activities by NGOs. To improve the partnership a consortium has been formed with 21 NGOs with BRAC as a lead NGO. PSM plan has been developed to ensure un-interrupted supply of LLINs, drugs, diagnostics and logistics. M&E plan has been developed to strengthen the tracking of outputs, outcome and impact. Baseline survey for malaria prevalence has been completed by GoB, ICDDR,B and PR-NGO. Program management capacity has been improved by recruiting human resources. Capacity building with refresher training of health workers and managers at different levels were carried out by both GoB and NGOs. The HNPSP endorses priority on control of vector borne diseases and to reduce malaria specific morbidity and mortality through improved access to EDPT and promotion of LLINs in collaboration with NGOs (Annex-15). HNPSP supports for training and improving coordination under Line Director, Disease Control to mitigate some of these gaps in the malaria program. WHO provides technical support for the areas related to Monitoring and Evaluation, Drug Resistance Monitoring; and capacity development at the national level. Institutions/group like Malaria Research group (MRG); Bangladesh Institute of Tropical and Infectious Diseases (BITID); Institute of Epidemiology, Disease Control and Research (IEDCR); National Institute of Preventive and Social Medicine (NIPSOM); and International Center for Diarrhoeal Disease Research, Bangladesh (ICDDR,B) are collaborating in the areas of research and training and supporting to address identified gaps in implementation of the malaria program.

1.2 National Disease Strategic Plans

With clear references to the current national disease strategic plan(s) and supporting documentation (include the name of the document and specific page reference), briefly summarize: - The key goals, objectives and priority program areas. - Implementation to date, including the main outcomes and impact achieved. - Limitations to implementation and any lessons learned that will inform future implementation. In particular, highlight how the inequalities and key constraints described in question 1.1 are being addressed. - The main areas of linkage to the national health strategy, including how implementation of this strategy impacts relevant disease outcomes. - For standard HIV or TB funding requests, describe existing TB/HIV collaborative activities, including linkages between the respective national TB and HIV programs in areas such as: diagnostics, service delivery, information systems and monitoring and evaluation, capacity building, policy development and coordination processes. - Country processes for reviewing and revising the national disease strategic plan(s) and results of these assessments. Explain the process and timeline for the development of a new plan (if current one is valid for 18 months or less from funding request start date), including how key affected populations will be meaningfully engaged.

The National Malaria Strategic 2014-2020 has been developed to provide technical guidance for the work of malaria control and elimination in Bangladesh for the coming years considering the changing landscape of the situation and aligning with the overall development goals of the country. Over the last decade or so, implementation of the previous strategies with the increase in resources available for malaria control in Bangladesh resulted in scaling up of malaria control interventions such as: i) early diagnosis and treatment with effective drugs; ii) high coverage of long-lasting insecticide treated nets; iii) improved surveillance and vector control options; iv) raising mass awareness of the population at risk; and v) effective collaboration and partnerships with NGOs and other multi-sector stakeholders. As a result of these interventions, the case incidence has a progressive decline and deaths due to malaria have been reduced remarkably over last a few years (kindly refer to section 1.1). However, these gains need to be sustained and enhanced by NMCP and the programme warrants a major shift towards embarking on a stratified phased elimination to eventually achieve the goal of a malaria free Bangladesh, in near future. This is the background of the National Strategic Plan (2015-2020) for Malaria Control. Existing Strategic Plan (2008-15) The existing National Strategic Plan (2008-2015) envisaged 60% reduction of malaria morbidity and mortality (compared to baseline 2005) by 2015 with the specific objectives of: i) providing early diagnosis and prompt treatment (EDPT) with effective drugs to 90% of malaria patients; ii) ensuring effective malaria prevention to 100% population at risk in five high endemic districts and 80% in the remaining eight districts; iii) providing pre-referral treatment and timely referral of 90% of severe malaria cases; iv) strengthening surveillance, establishing Rapid Response Team (RRT) for containment of outbreaks; vi) promoting community participation, partnership with NGOs and private sector and vi) strengthening management capacity, M&E and Procurement and Supply Management (PSM) systems in the National Malaria Control Programme. Largely, National Malaria Control Programme.has been successful in achieving the set objectives and targets as revealed in the Malaria Programme Review (MPR) in June 2011 and the Mid-Term Review (MTR) in April 2014. The MPR and MTR highlighted programmatic strengths, weaknesses and gaps to address for creating a sustainable impact in malaria control through stratified micro-planning based on evidences that will support further reducing disease burden in low malaria endemic districts as against a blanket approach to implementation of malaria interventions, countrywide. National Malaria Strategic Plan (2014-2020) The Malaria Strategic Plan provides the framework and technical guidance for the malaria control programme to plan and implement interventions for achieving pre-determined goals, objectives and targets. The Malaria National Strategic Plan 2015–2020 has been developed through a multi-stakeholder, multi-sector participatory approach in line with recommendations from the Malaria Programme Review (MPR) and the Mid-Term Review (MTR) of NMCP conducted by national and international experts, during June 2011 and April 2014, respectively. Moreover, the paradigm shift due to epidemiological changes; the gradual shrinking of the malaria map in low transmission districts; and need for planning to step down to a stratified and phased elimination of malaria in Bangladesh have been considered. Some differences from the previous strategies therefore are the scale up and consolidation of malaria control interventions including disease and vector surveillance; improved programme planning and targeted implementation; and strengthening monitoring and evaluation. The strategy is aligned to overall health sector strategies of the country and using state of the art technologies, in line with regional and global malaria control strategies, in particular. Vision, Goal and Objectives of the Strategic Plan (2014-2020) Vision: Malaria-free Bangladesh Goal: By 2020, to have reduced malaria incidence by 75% (baseline 2013) and achieved ‘zero deaths’ aiming at phased elimination in targeted districts. Strategic Objectives: Objective 1: To have 100% coverage of the people living in malaria risk areas with appropriate malaria preventive interventions by 2020 Implementation strategies: During implementing GF supported proposal of R-6 and R-9, the National Malaria Control Programme has achieved remarkable success in scaling up diagnostic and treatment services and reduced malaria incidence remarkably. However, a 100% coverage by appropriate and effective preventive methods for the population at risk, yet to be achieved. The following interventions need to be considered: - Procurement and distribution of LLINs (@1 net per 1.8 Population) and ensuring use for maximizing personal protection; - Treatment and re-treatment of community owned nets; - Special measures for high risk groups (Jhum Cultivators, forest goers etc); - Additional personal protection measures for tourists, short term travelers, labourers in development projects etc. Objective 2: To have 100% malaria patients received early and quality diagnosis (RDT and Microscopy) and effective treatment by 2020 Implementation strategies: The National Malaria Control Programme needs to emphasize the “Test, Treat and Track” principles and ensure that 100% malaria patients are diagnosed and treated within 48 Hrs of the onset of disease. The following areas to be taken into account: - Provision of Pan-RDT and microscopy centres closer to the community; - Trained Lab. Technologists and QA system for microscopy and RDT; - Uninterrupted supplies of RDT and ACT; - Utilization of Community Clinics (all 800 CCs in malaria endemic areas); - Special efforts for reaching remote/hard to reach areas (Mobile clinics and deployment of additional local community health workers); - Case based reporting and follow up; and investigation of each death Objective 3: To strengthen programme management capacity to plan, implement and achieve phased elimination by 2020 Implementation strategies: As the National Malaria Control Programme needs to embark on phased elimination, the present capacity should have to be strengthened to ensure proper planning and effective implementation. The following areas are critically important: - Geographical Reconnaissance (GR) of villages/households and mapping of malaria endemic areas as per micro-stratification to introduce area specific interventions; - Target based approach to planning prioritizing the most at risk populations and adapting sound strategies to address local needs; - Deployment and development of additional Human Resources at central and district levels (Entomology Team, in particular) - Reinforce partnerships and collaboration; - Investing in Health system and community system strengthening; - Re-orientation of National Malaria Control Programme towards pre-elimination and elimination in phased manner Objective 4: To strengthen disease and vector surveillance, Monitoring and Evaluation in all malaria endemic districts Implementation strategies: The present capacity of National Malaria Control Programme in areas of disease and vector surveillance, Monitoring and Evaluation is weak which needs to be enhanced. The following steps should have to be taken: - Strengthen central team for malaria surveillance, M&E and operational research; - Improve Entomological surveillance to include studies of vector biology; advise on effective vector control interventions; and monitor vector resistance to insecticides; - To develop indicators and targets, performance framework and monitoring & evaluation; - Introduce electronic data base and web-based reporting; - Integrated Communicable Disease Surveillance linked to HMIS; Objective 5: To scale up Advocacy, Communication and Social Mobilization (ACSM) on prevention and treatment of malaria Implementation strategies: Mass awareness of the population at risk should be continued and intensified through intensive IEC using appropriate materials and tools. Community empowerment is the key to successful programme implementation. For a sustainable impact, a well-planned ACSM is instrumental for ensuring community participation in malaria control. The following elements of ACSM should guide to effective mass awareness campaign: - Development and use of appropriate ACSM materials and tool; - Using local cultural and ethnic norms and practices for target population; - Coordination between health and related sectors; - Mult-sectoral approach to remove cultural and ethnic barriers in communications; A log frame is also an integral section of the NSP 2014-2020 (Annex). Achievements so far: Achievements towards the Goal of Malaria Control Programme: Figure 10: Achievement (number of deaths) by the target year 2015 Figure 11: Achievement (number of cases) by the target year 2015 The Programme objectives, indicators with baseline, targets and achievements during the period from July 2012 to June 2013 are given in the table below: Table 10: Programme achievement (objective-wise) (July 2012-June 2013) Indicator; Baseline (Year 2011); July 2012 – June 2013. Target; Achievements. Objective 1: To expand use of LLIN, 2 nets per household, to achieve 100% coverage in 3 high malaria endemic districts and maintain 80% coverage with ITN/LLIN in the remaining districts. Number of people reached through BCC orientation meetings on malaria prevention; 12,803; 14,200; 15,148. Objective 2: To expand and improve quality diagnosis and treatment to 90% of malaria cases. Number of laboratory technicians trained in malaria microscopy; 10; 20; 20. Total number of fever cases examined by microscopy and RDT (in the 3 highest Malaria transmission districts); 246,950; 253,443; 229,930. Total number of fever cases examined by microscopy and RDT (in the other 10 high Malaria transmission districts); 143,152; 148,848; 158,668. Number of clinical malaria cases examined by RDT and/or microscopy with positive diagnosis; 51,795; 44,698; 26,524. Number of P. vivax cases received CQ+PQ; 2,580; 1,265; 1,132. Number of P. falciparum cases received ACT; 46,123; 23,881; 23,401. Number of people received malaria treatment through community service providers (in the 3 highest Malaria transmission districts); 24,680; 15,176; 10,292. Number of people received malaria treatment through community service providers (in the other 10 high Malaria transmission districts); 7,792; 6,504; 5,118. Number of health facilities with no reported stock outs lasting > 1 week of nationally recommended anti-malarial drugs at any time during past three months; 120; 121; 121. Number of village doctors oriented with malaria management (in the 3 highest Malaria transmission districts); 505; 2,875; 2,889. Number of village doctors oriented with malaria management (in the other 10 high Malaria transmission districts); 731; 3,975; 3,825. Objective 3: To further strengthen programme management capacity, and coordination and partnership in malaria control. Number of health facilities reporting timely, completely and accurately; 120; 121; 121. Number of people attended advocacy meeting/workshops; 4,385; 5,550; 5,678. Objective 1: To expand use of LLIN by 2 nets per household to achieve 100% coverage in three high malaria endemic districts (Khagrachhari, Bandarban and Rangamati) and maintain 80% coverage with ITN/LLIN in the remaining district. ITN/LLINs are well-known and useful tools for reducing transmission of malaria and are well accepted in the community. The households having no mosquito nets were targeted to supply LLINs. The nets were treated with Deltamethrine (KO tab and KO tab 123) for the households that already had nets. BCC activities were continued to ensure that people use those nets. The need of ITN/LLINs was assessed after conducting household census, and then distribution of LLIN and the treatment of nets (ITN) were done accordingly. Figure 12: House-hold coverage by LLIN/ITN (2011 & 2012) Since 2008, 3,123,905 LLINs were distributed (including 1,199,978 replacements) under GFATM support. Since May 2007 a total number of 1,581,402 ordinary bed-nets were treated with regular KO tab and 1,563,984 ITNs were treated with KO tab 123 during 2011-2012. Figure 13: LLIN/ITN utilization rate (pregnant women & under 5 year) Objective 2: To expand and improve quality diagnosis and treatment to 90% of malaria cases. Since May 2007, a total of 2,623,417 cases of fever were examined nationally by RDT and/or microscopy, where BRAC and partner NGOs performed 1,509,254 RDT/ microscopy tests. The number of confirmed malaria cases was 345,522 of which BRAC and partner NGOs diagnosed 218,507 cases by RDT and microscopy. A total of 289,519 falciparum malaria cases were treated; of which, BRAC and partner NGOs treated 188,022 cases. Around 2,500 Shasthyo Kormis and Shasthyo Shebikas (community based service providers of BRAC) provided malaria diagnose and treatment services. A total of 181,640 confirmed patients received treatment at the community level. Figure 14: Percentage of malaria cases diagnosed by RDT and microscopy (2007–2013 June) Objective 3: To further strengthen programme management capacity, and coordination and partnership in malaria control. The third objective of the programme was to strengthen programme management capacity, coordination and partnership in malaria control. Recruiting additional human resources and ensuring availability of vehicles and equipments strengthened the procurement, supply management and M&E system. Different types of coordination and review meetings are held at central to upazila level to analyse the performance and make an effective operation plan. Executive directors of partner organizations, representatives of NMCP and WHO, are the major participants of central level meetings. Supervision refers to the activity carried out to oversee the progress of the programme. It is a management activity to convey information and directives to improve the work done as well as maintaining its quality. While monitoring is the systematic collection and analysis of information of a project, it is aimed to improve the efficiency and effectiveness of a project or organization. It is based on targets set and activities planned during the planning phases of work. It helps to keep the work on track and can let management know when things are going wrong. Supportive supervision jointly by both PRs: NMCP and BRAC jointly visit the health facilities of both government and NGO in every quarter with specific checklist. Both PRs monitor HR status, data quality, laboratory condition, stock status and quality implementation of malaria activities in the field. It enhances the programme quality at the same time coordination and commitment among both PRs. BRAC adopts three tiers of monitoring and supervision from central to field level. Central level personnel from BRAC monitor each NGO twice a year using a specific checklist. The regional level personnel conduct supervisory visit of each NGO once in a quarter with a distinct checklist. During supervisory visit, programmatic activities such as efficiency of human resources, performance of BCC activities, correctness of MIS report, laboratory performance are observed and analyzed. Programme Organizers of the district conduct in depth monitoring at all strata of field from community level to upazila level, including health facilities using the specific checklist. Methodologies of monitoring are observation and cross checking. Findings of the visit are shared at the field office of respective partner SR and a report is sent to the central office of BRAC malaria control programme. In addition to routine monitoring and supervision, in depth/ vigorous field visits are made according to programme necessity. BRAC Research and Evaluation Division (RED) and Monitoring Department also evaluate the effectiveness of the programme independently once a year. Project Managers of SRs are involved in programmatic supervision of planned activities. They make a monthly visit schedule to cover all the designated upazilas as per the plan. They follow a specific method and checklist during monitoring. Monitoring officers submit the report of each quarter to the respective executive directors with a copy to BRAC. Apart from programmatic monitoring, financial audit is done yearly by BRAC Internal Audit Department to control the financial activities, which ensures transparency at all levels. A reputed audit firm also does external audit annually. Quality control and quality assurance is another important issue in malaria control programme. To ensure the quality of microscopic services, six quality assurance (QA) labs have been established. The labs are located at Rangamati, Bandarban, Khagrachhari, Chittagong, Cox’s Bazar and Sylhet. Every month, 10% of the slides are randomly selected from each NGO laboratory and sent to the QA lab of the respective district for cross checking. In addition, 100% of the positive slides and 10% of negative slides from each NGO laboratory are sent to government laboratories for the same purpose. Feedback and support is provided to the respective laboratories based on those reports. # The lab technicians are provided with basic training followed by refresher training to improve their efficiency. Programme organizers (Quality & EQA) are continuously ensuring the quality of laboratory services, standard of RDT, assuring quality of data (DQA), follow-up of health workers and beneficiaries by verifying programme activities through relevant checklists. Management Information System (MIS) has been upgraded with new reporting formats. Two types of reporting systems are maintained, a monthly reporting system and quarterly reporting system. Disease specific and programme data are collected through monthly performance and quarterly progress reports that are compiled and analyzed by the MIS unit. In the reporting system, data of diagnosis, treatment services and preventive activities (mosquito net distribution and net treatment) are submitted to the government’s Upazila Health Complex (UHC) using specific reporting format. GO and NGO achievements are compiled at UHC office and signed by the UH&FPO. Then it is sent to the Civil Surgeon’s Office. Reports from upazilas are compiled at the office of the Civil Surgeon, signed by the Civil Surgeon and then sent to NMCP. Achievements of 13 malaria endemic districts are compiled at NMCP. This report is the monthly national report and a copy is collected by BRAC from NMCP. The quarterly report is collected by BRAC using a specific reporting format both from BRAC and sub-recipients’ working areas. Both diagnosis and treatment of cases, preventive and BCC activities performed by NGOs, are collected quarterly. All NGO achievements are compiled and submitted to the Global Fund at the end of each quarter. The MIS data quality management is an essential component of the programme. It supports the implementation, accurate reflection of the improvement and assessment of outcome of the programme. It is done through routine monitoring and supervision, and routine data quality assessment (RDQA). Annual MIS validation is done by BRAC Monitoring Department independently. RDQA validate the data and assess the consistence and accuracy from bottom to top level. Training and Orientation on Malaria: All Shasthya Kormis and Shasthya Shebikas in malaria endemic areas receive an 18-day basic training including training in malaria to improve their skills and knowledge by BRAC-HNPP Training Unit. They also receive regular refresher training. Staffs at different levels of both BRAC and the partner NGOs working in malaria areas, get different types of training for effective programme implementation. The trainings include: malaria microscopy training for laboratory technicians, training on malaria diagnosis and treatment for health volunteers and workers, basic training on prevention and control of malaria for BRAC (Regional Managers, Medical Officers and POs) and partner NGO staffs (Project Manager and Upazila Manager), programme management training for Project Managers and Upazila Managers, QA training for Upazila Managers and Programme Organizers, and M&E training for partner NGOs’ Monitoring Officers. In addition, health management training and M&E training courses conducted by BRAC University are provided to most promising staffs of malaria programme to enhance their knowledge and self improvement. Health personnel from the government, WHO, MRG, BRAC and other organizations are invited in different training sessions as resource persons to deliver their speech in particular topics. Capacity building is one of the key responsibilities of BRAC. As the Principal Recipient (PR), it capacitates the programme staffs to perform their job effectively and efficiently. It is vital that the PR has adequate capacity, resource and system in place to manage the SRs and ensure that they can access capacity building as needed. Being the principal recipient, BRAC has prioritized for capacity building of SR to: - Enhance sub-recipients’ understanding of Global Fund programmatic and operational procedure in line with proposal goals and ensure effective management of sub-grants. - Establish a system to enable regular reporting by the sub-recipients on programmatic and financial aspects of the grant. - Make best use of partnerships with government, civil society and other stakeholders through strengthening their capacity to carry out the responsibilities of GFATM sub-recipient. BRAC performs participatory monitoring of both financial and programmatic activities of SR NGOs. During regular monitoring visit to health facilities and laboratories, community service provisions are observed, records and reports are reviewed, and MIS reports are verified on sampling basis. In addition, performance review and annual internal and external audits are done. Feedback and necessary assistance is provided to the respective SR NGOs, based on the findings of monitoring visits, performance review and audit report. SRs are different from each other in terms of organizational and management capacity. Different trainings are provided to different levels of SR-NGO staffs by BRAC Training Division and Finance Department to develop a uniform and acceptable standard for both programmatic and financial management capacity to deliver quality services. BRAC will conduct these trainings as per yearly training plan duly approved by the Global Fund. Annual Review and Planning Meeting: Two annual review and planning meetings were held in two different places targeting high and low endemic districts separately. Government personnel from NMCP and DGHS, Civil Surgeons of different malaria districts, representatives from WHO, and BRAC and partner NGOs attended those meetings. The objective of these meetings was to formulate appropriate implementation strategies to further reduce the burden of malaria and strengthen the collaboration among different government and private stakeholders. Partnership with Civil Society: The civil society has been a vital partner contributing to the design and structure of the Global Fund and subsequently encouraging governments to commit more resources to support its work. In Bangladesh, the involvement of civil society organizations in both CCM and implementing agencies has helped to achieve rapid scale up of interventions and has shown good example of partnership with government programmes. Research activities on Malaria: Research is very much important to monitor programme progress, document achievement and impact assessment. From the inception of the programme, several researches have been conducted in collaboration with BRAC, ICDDR,B and NMCP21, 22, which formed the planning of scaling up and modification of the programme. A malaria baseline socioeconomic and prevalence survey was conducted in 20078 and follow up prevalence survey will be conducted in the later part of 2013 to know the changing situation of malaria in endemic areas. Survey on different performance indicators, such as, distribution and utilization of LLIN/ITN23, and Knowledge, Attitude and Practice (KAP)23 toward services, etc., have been conducted by BRAC Research and Evaluation Division (RED). Advocacy, Communication and Social Mobilization Advocacy, Communication and Social Mobilization (ACSM) is an integral component of a comprehensive malaria prevention, care and support programme. It has a number of different but interrelated roles. ACSM activities are carried out involving the community and civil society to support generation and demand creation. BRAC Advocacy unit conducts round table meetings on malaria with both print and electronic media, and different stakeholders at the central and district levels. Advocacy workshops are organized at district and upazila levels with different stakeholders like teachers, doctors, opinion leaders, civil society representatives, etc. At the union level, orientation sessions on malaria are organized with health workers, local opinion leaders, headmen, karbaris, village doctors, religious leaders and local government representatives to disseminate malaria information and generate their support to the programme. Health Workers/ Volunteers disseminate information to the community regarding symptoms of malaria, diagnosis, available treatment services and prevention of malaria by using LLIN/ITNs, during their regular household visits. Health Workers/ Volunteers also disseminate information through health forums using flip charts Folk media like popular theatre and folk songs with malaria messages are also used to aware people. These highly popular folk media events play a great role in creating sustainable impact on people’s mind. Theatre shows and folk song events are organized at the village level. Local cultural groups and artists perform the events so that they become more acceptable to the people. Malaria short films are shown in high endemic areas. IEC materials such as, billboard, poster, leaflet are also used to educate people regarding malaria diagnosis and treatment services. World Malaria Day was observed in Bangladesh as elsewhere across the globe on April 25th, 2013, at national, district and upazila levels. At the central level, talk show, press conference, rally, discussion meeting, community clinic inauguration, health camp, folk songs, popular theatre, court yard meeting, etc., were organized on that day involving people from all walks with the vow to win the fight against malaria. The theme of the day, “Invest in the Future: Defeat Malaria” pointed to the international community's renewed efforts making progress towards zero malaria deaths by 2015. On that day, the malaria community shared progress and impact made to date, in order to encourage further actions, investments and awareness against the deadly disease. The World Malaria events created greater awareness on malaria prevention and control among the people of the endemic districts of Bangladesh. Lessons Learnt and Challenges BRAC’s decades of development, experience and community empowerment positioned the organization as a strong force to fight malaria. The performance-based funding provides the programme with resources to promote continuity of the intervention. Now the focus is being shifted towards prevention of malaria by effective vector control and reduction of transmission through minimising human and vector contact. The number of households in the hill tract districts has increased from the time when the programme started along with increased LLIN requirement. Simultaneously, existing arrangement is not enough to cover all household members where more than two bed nets are required. It has also been noted that different communal settings which are not households, such as hotels, student dormitories and army camps should be included under LLIN/ITN coverage. The forest and hill workers such as “Jhoom” cultivators, woodcutters, etc., and migrant workers remain exposed to vector for a certain period during their seasonal occupation. Different approaches are required for them to prevent contact with vector, such as hammock net, repellent, etc. Current MIS data shows a decreasing trend of malaria cases and death in malaria endemic areas both of vivax and falciparum malaria. Micro-stratification data shows sporadic distribution of malaria cases in certain geographical pockets particularly in the border areas. Collaboration with the neighbouring endemic countries is required to interrupt the transmission in these areas. Sub-centres have been done in hot spot areas and symptomatic relatives or neighbours of malaria patients are tested for malaria. Many of the areas where malaria is high endemic are characterized by remoteness, hilly geography and limited infrastructure for communication. These hard-to-reach areas are at three districts of CHT and Cox’s Bazar, where incidence is the highest and yet they are not under full coverage in terms of diagnosis, treatment and prevention. Transmission is relatively high in these areas. Population residing in the remote and hard-to-reach areas and the poorest of the poor still has limited access to utilization of the available services. In the recent years, climate change issues and its potential impact on increasing malaria incidence further emphasizes the need for collaborative efforts across the borders. Malaria cases and deaths are now being reported from the medical colleges. Private practitioners are being oriented to follow the malaria national treatment regimen and report the malaria cases in national MIS. Hotel owners/managers are also being sensitized on malaria targeting tourists coming from non-endemic areas to prevent morbidity and mortality from malaria. Mobile health camps are being conducted in hot-spot areas reporting increased number of cases. Rationale for concept note: The malaria situation remains a major problem in certain geographical pockets contributing to majority of the cases of the country. Micro-stratification and micro-level analysis and planning is needed to ensure equitable approach for effective malaria control. Identification of malaria transmission hot spot areas and pocket areas (hard-to-reach areas yet to be under regular coverage of the programme) will be mapped and targeted interventions ill be given as per need. Mobile health team will be formed to provide special campaigns to those areas. Special volunteers will be recruited in areas where regular health workers are not available. According to a survey conducted in 2012, around 53% people living in endemic regions were conscious about malaria programme activities24, which can be increased through intensifying BCC activities. In subsequent years, the current single specimen RDT will be replaced by Combo RDT to trace any missing case in the community particularly vivax malaria. Use of bed-nets and other lifestyle changes will be promoted in order to attain sustainability of the programme. Health system will be strengthened through reinforcing community level making the diagnostic and treatment services available. To avoid delay in referring severe malaria cases, transport cost will be provided to the poor and hard to reach areas patient. Integrated vector management activities will be undertaken for sustainable vector control. Community participation will be encouraged and ownership will be developed among them to create sustainable impact on the community. Community clinics will be made more effective through availability of diagnostic and treatment services. More service delivery points will be established particularly in the place where people gathering is more (such as at market, in pharmacy) and RDT kits will be kept available in remote areas. Every pregnant woman and symptomatic patient will be tested for malaria. National malaria strategy will be updated along with revision of national treatment regimen with inclusion of Primaquine in falciparum malaria and mixed cases. With continued reduction of malaria morbidity and mortality the country is now looking forward to start activities focusing malaria elimination in low endemic districts. Priorities should be given to identification and treatment of all malaria symptomatic patients and all people carrying parasites, and sustainable reduction man-vector contact and the vectorial capacity of the local Anopheles mosquito populations. Regular monitoring of drug and insecticide resistance, drug compliance, efficacy of LLIN/ITN, KAP survey, entomological and epidemiological survey will be continued. Service delivery points will be established in Dhaka to address patients of non-endemic areas. More involvement of different sectors of local government and private sectors will be catalyzed through meetings and orientation sessions. Co-ordination at all levels is essential for smooth implementation of the programme. Strong political commitment and involvement of more civil society will be ensured. Continued strong commitment at all levels and sustained funding and augmented technical capacity will help to continue the current momentum to sustain and achieve the Millennium Development Goals set for 2015. [This concept note remains aligned with the National Strategic Plan 2014-20. The vision and mission, goals, objectives and strategies are cornerstones in preparation/prioritization of the details and modules]. KEY RECOMMENDATIONS OF THE MID-TERM REVIEW (APRIL 2014): …

SECTION 2: FUNDING LANDSCAPE, ADDITIONALITY AND SUSTAINABILITY

To achieve lasting impact against the three diseases, financial commitments from domestic sources must play a key role in a national strategy. Global Fund allocates resources which are far from sufficient to address the full cost of a technically sound program. It is therefore critical to assess how the funding requested fits within the overall funding landscape and how the national government plans to commit increased resources to the national disease program and health sector each year.

2.1 Overall Funding Landscape for Upcoming Implementation Period

In order to understand the overall funding landscape of the national program and how this funding request fits within this, briefly describe: - The program areas currently receiving financial support and the source of such funding (government and/or donor). Highlight any program areas that are adequately resourced (and are therefore not included in the request to the Global Fund). - For program areas financed by the government, additional funding commitments expected (willingness to pay) during the implementation period and indicate how these commitments will be tracked and reported. - How the proposed Global Fund investment has leveraged other donor resources. - For program areas that have significant funding gaps, planned actions to address these gaps.

Currently, the funding landscape for malaria control in Bangladesh entail the following: - GoB funding - GFATM funding (current Phase2 up till June 2015) - Expected funding under NFM (from July 2015 to December 2017, upon approval) - Possible co-funding from other donor (BMGF, JICA), partner organizations (WHO, World Bank) and corporate sector is being explored. For building capacities under the GoB, funding is being solicited, and hence, certain capacity building initiatives are not included as funding request in this concept note. In order to achieve lasting impact, financial commitment from domestic sources is playing a key role in a national strategy. While the Global Fund allocates funding to the country, these resources remain additionality. As the final concept note will be submitted through the Bangladesh-CCM, the requested funding (indicative and incentive) will be fit within the overall funding landscape, including other donor funding, and it will be clearly highlighted how national government plans to commit increased resources to the national disease program and health sector each year. Information on the counterpart financing requirements and its willingness-to-pay commitment: Bangladesh is in compliance with counterpart financing requirements of: 1. Reliable spending data: Bangladesh government budgets have specific line items, which captures government allocation to diseases and the health sector. The country has systems to track and routinely report spending by source of funding. In addition, the country has institutionalized National Health Accounts (NHA), including disease sub-accounts that support tracking of expenditure by source of funds and key services. The funds allocated to the National Malaria Control Programme have been verified; 2. Minimum threshold counterpart contribution of 5% for low income countries: Based on amounts of government spending, the counterpart financing share is around …%; and 3. Stable or increasing trend in government contribution to the disease program and health sector: Past spending, as well as projections of government contribution in the next implementation period to both Malaria and health shows an overall increasing trend. Government budget for health is projected to increase from US$ … to over US$ … by 2018. Total government contribution to the National Malaria Control Programme is non-incremental over time on account of capital expenditure budgeted for in earlier year. Going forward, the funding request to the Global Fund under the NFM is expected to be leveraged for mobilization of additional donor resources. The activities being undertaken currently with the domestic and especially GF grant and tangible outcomes and impacts will be highlighted as possible opportunities for the TRP/GAC for incentive funding and other donors to contribute in malaria control in Bangladesh and be a responsible player in journeying towards pre-elimination and elimination.

2.2 Counterpart Financing Requirements

Complete the Financial Gap Analysis and Counterpart Financing Table (Table 1). The counterpart financing requirements are set forth in the Global Fund Eligibility and Counterpart Financing Policy. Indicate whether the counterpart financing requirements listed below have been met. If not, provide a justification that includes actions planned during implementation to reach compliance. - Availability of reliable data to assess compliance. - Minimum threshold government contribution to disease program (low income-5%, lower lower-middle income-20%, upper lower-middle-income-40%, upper-middle-income-60%). - Increasing government contribution to disease program. - Increasing government contribution to health sector.

The Financial Gap Analysis and Counterpart Financing Table with financial information will be aligned with the NSP 2012-17 and overall HPNDSP. The CCM-Bangladesh is proposing a funding request of USD … for MoF and USD … for BRAC. Drawing from in-country discussions, the CCM-Bangladesh puts forth that the level of government spending will be, at the minimum, … in subsequent years. The government spending data from the Ministry of Health & Family Welfare have been used to calculate the counterpart financing share. Based on current levels of government spending, the counterpart financing share is …% and meets the minimum threshold of 5% for lower income countries. Available data on NMCP expenditures indicate that government health expenditures and malaria expenditures have significantly increased over time. With the prevailing political commitment, it is expected that the Government contribution to malaria control programme will continue to be stable or even increase as the country moves to stratified phased elimination. Overall, the government health budget for … has …. from Tk./USD … to …. Total health expenditure has been …% of GDP. FROM WORLD MALARIA REPORT, OTHER DOCUMENTS, HEALTH BULLETIN…

SECTION 3: FUNDING REQUEST TO THE GLOBAL FUND

This section details the request for funding and how the investment is strategically targeted to achieve greater impact on the disease and health systems. This section requests an analysis of the key programmatic gaps which, in turn, forms the basis upon which the request is prioritized. The modular template (Table 3) organizes the request to clearly link the selected modules of interventions to the goals and objectives of the program, and associates these with indicators, targets, and costs.

3.1 Programmatic Gap Analysis

A programmatic gap analysis needs to be conducted for the three to six priority modules within the applicant’s funding request. Complete a programmatic gap table (Table 2) detailing the quantifiable priority modules within the applicant’s funding request. Ensure that the coverage levels for the priority modules selected are consistent with the coverage targets in section D of the modular template (Table 3). For any selected priority modules that are difficult to quantify (i.e. not service delivery modules), explain the gaps, the types of activities in place, the populations or groups involved, and the current funding sources and gaps.

Subsequent to in-country stakeholder consultations focusing prioritizing modules, interventions, activities, target and cost assumptions drawing from existing implementation experience and guidance by the GF, technical partners, etc., an analysis has been attempted for the period of 2015-16 (from July 2015) to 2017-18 (until June 2018). The priority modules, 05 in number (per GF framework) in the concept note include: - Vector control - Case management - Health Information System/M&E - Health Workforce - Programme Management The program gaps have been estimated for: i) 03 high endemic CHT districts and 01 moderate endemic Cox’s Bazar district; and ii) 09 low endemic districts (being proposed for indicative funding from July 2015 to December 2017 for 30 months as Phase2 will continue till June 2015 & targets will remain same as in Phase2 Performance Framework). Table 2 details the quantifiable components in the above-mentioned priority modules within the applicant’s funding request. It is ensured that the coverage levels for the priority modules selected are consistent with the coverage targets in section D of the modular template (Table 3). Kindly refer to the Table2 and Table3.

3.2 Applicant Funding Request

Provide a strategic overview of the applicant’s funding request to the Global Fund (indicative and above indicative). Describe how it addresses the gaps and constraints described in questions 1, 2 and 3.1. If the Global Fund is supporting existing programs, explain how they will be adapted to maximize impact.

Malaria remains a local and focal disease especially affecting 03 CHT high endemic districts and 10 other moderate/low endemic districts in spite of the fact that the disease is quite preventable and curable as mentioned in the above sections. The most vulnerable are those living in the hard to reach areas inhabited mostly by the tribal and other marginalized groups, migrants and mobile populations (jhum cultivators, forest-goers, etc.). In response to the invitation to submit a concept note for seeking funding under the NFM of the Global Fund and subsequently, the Bangladesh CCM decided to submit this concept note for kind consideration and approval. The priority modules are mentioned in the previous section. It may be noted that even though the total number of cases has decreased, the decline is more evident in low endemic non-hill zone in comparison with high endemic hilly and coastal regions. These areas, especially the three districts of Chittagong Hill Tracts (CHT) and Cox’s Bazar, where incidence is the highest are hard-to-reach and yet not under full coverage in terms of diagnosis, treatment and prevention; and transmission persists at a relatively high rate. The proportion of vivax malaria to the total number of cases has been reduced. Around 54% of people living in endemic regions are aware of malaria diagnosis and treatment services which need to be increased through intensifying ACSM activities [Annex-2: Bed net and KAP survey, June 2011]. Private sector service providers are not yet properly sensitized and brought under routine reporting and surveillance system. Targeted programming is needed to reach newly identified populations at risk especially in high endemic areas. This concept note remains critical for continuation of the need to strengthen the ongoing efforts of the GoB towards further scaling up for universal coverage with effective preventive and curative interventions, as the Phase2 will conclude in September 2015. Continued efforts and investments are much needed to sustain the gains and save lives, drawing from the specific local needs, gaps, and bottlenecks experienced during the implementation of the Phase2. Buoyed by the promise of declining trend of malaria in high and moderate endemic districts and absence of cases and deaths of … Upzilla in 09 low endemic districts, the MOHFW is confident on embarking upon phased elimination by 2020 by interruption of local transmission of malaria in four malaria hypo-endemic districts and selected towns that will progressively expand to other districts. Such ambitious vision will be made possible by the intensified mission that entails intensified and multi-pronged application of locale-specific interventions in the next six years for reducing number of locally acquired cases to zero and number of active foci to zero in the four hypo-endemic districts of the country. The GoB is already proposing to commit additional resources from own sources and various donor, partner organizations apart from the seeking additional funding under the NFM. In fact, the GoB is proposing to seek funding for a unique initiative of “Malaria Free Towns” using the multi-pronged approach drawn from the IVM concept. This concept note includes the related interventions for seeking funding under ‘Above’ section. Towards achievement of this vision and mission as set in the NSP 2014-20, the modules and key interventions and related activities in this concept note stand aligned. The GoB recognizes that there are still significant unmet needs for malaria control in hard-to-reach areas, both in terms of community awareness of the issue and in availability of service delivery. Hence, the number of community-based service providers will be sustained to ensure maximum coverage. Laboratories will be further strengthened and additional laboratories may be established in remote pockets deprived of health services (with funding support from non-GF sources). ACSM activities will be strengthened. Private service providers will be brought under referral and reporting system through orientation and sensitization. Mobile case reporting by health workers will be done for early and prompt referral for severe cases. Activities to improve quality assurance of malaria microscopy, quality of data and storage condition of health products will be implemented. Surveillance and M&E systems will be strengthened. Additional ITMNs are required in high-endemic districts to achieve desired targets. The GoB mission will be on guard with regard to the following disabling factors: - Achievements in malaria mortality and morbidity are very fragile. Reduction in malaria mortality and morbidity is achievable with regular interventions; yet, for pre-elimination and later elimination, sustained and more intensive efforts and resources are necessary. - Emergence of possible resistance to Artemisinin in view of its relatively indiscriminate use as monotherapy (mostly by private providers) and long international porous borders with frequent migration of population presents possibility of importation of resistant parasite and chances of outbreaks. Already, several areas of concern for artemisinin resistance have been identified within the neighbouring Myanmar. - Continued insufficiencies of resources vis-à-vis delaying Artemisinin resistance in Bangladesh as well as the need to realize the goal of pre-elimination and then elimination. - Efficient vector; physical environment (warm/humid conditions); shifting cultivation; possible insecticide resistance; etc. may influence the disease burden adversely, despite the best control efforts. - Hard-to-reach areas where intensity of transmission is the highest and the health care delivery system constraints are yet to be optimal coupled with continuing socio-political challenges and diverse institutions, health seeking behaviour of tribal/ethnic groups. - Surveillance data are largely from public sector. Hence, the real scenario may be different. Micro-stratification and micro-level planning will be key to the planning and to ensure equitable approach for effective malaria control. Many of the endemic districts are hard-to-reach and pose substantial challenges to effective disease control, will require higher levels of M&E support. To support the quality of service delivery, more frequent supervisory visits are required. Supervisory staff will provide technical supervision and assess data collection practices. Programme management and M&E capacity will be strengthened further to ensure data quality. These activities will require additional supervisory staff. Efforts will be increased in all programme areas, with special focus given to hard-to-reach areas. The NGOs will be brought under the web-based reporting of disease specific and inventory data. Further, the partnership between the PRs (GoB and BRAC) have become stronger over Phase2 and catalyzed complementary facet of government and non-government sector efforts by sharing responsibilities. A major focus is on strengthening of community outreach programmes including diagnosis and treatment, ACSM, and supervision and monitoring. Community participation to ensure participation of different stakeholders in the pre-elimination of malaria; and inter-sectoral coordination & collaboration, are and will be major thrust areas which are expected to reduce transmission from existing cases. As examples, collaborative efforts with the Armed and paramilitary forces are planned to reach out to the civilian population in border areas. Child-to Child programmes in the education sector will create change agents in terms of ‘little dictors’ who are being and will be empowered with appropriate information. The funding request is for 13 high, moderate and low endemic districts for funding from July 2015 to December 2017 for 30 months as Phase2 will continue till June 2015 & targets will remain same as in Phase2 Performance Framework. The core elements of Phase2 that will continue till June 2015 as under: - Diagnosis, prompt, effective treatment - BCC: community outreach - HSS: Health Workforce/Service Delivery/Information systems – M&E - Prevention: LLIN The summary funding request under the NFM is as under: The total indicative funding request is: USD … and the ‘above’/incentive funding request is: USD …. The details are as under: For MoF, GoB: CostCategory; indicative/Above; Year1; Year 2; Year 3 (1st 6Month); 30Months Total. Vector Control (Health Products and Health Equipment); Indicative; 5,684,307; 4,967,735; 3,689,931; 14,341,973. Above Indicative; -; -; -. Health Workforce (Human Resources, Training); Indicative; 389,696; 433,710; 241,743; 1,065,149. Above Indicative; 25,972; 30,488; 20,226; 76,686. Program Management (Infrastructure and Other Equipment, Planning and Administration, Other, Overhead); Indicative; 270,203; 245,151; 251,044; 766,398. Above Indicative; -; -; -. Health Information System & M&E; Indicative; 134492; 159544; 153651; 447,687. Above Indicative; -; -; -. Case Management (Pharmaceutical Products (Medicines), Procurement and Supply Management Costs (PSM)); Indicative; 26,350; 20,034; 11,916; 58,300. Above Indicative; -; -; -. Total; Indicative; 6,505,048; 5,826,174; 4,348,285; 16,679,507. Above Indicative; 25,972; 30,488; 20,226; 76,686. Grand Total; 6,531,020; 5,856,662; 4,368,511; 16,756,193. For BRAC: INSERT REVISED TABLE FROM BRAC (PR2). Kindly refer to the Table3: Modular Template for details of concept note. Goal By 2018, to have reduced malaria incidence by 80% (baseline 2013) and achieved ‘zero deaths’ aiming at phased elimination in targeted districts. Impact indicator Impact indicator; 2013 (Baseline); 2015-16; 2016-17; 2017-18. Confirmed malaria cases (microscopy or RDT) per 1000 persons per year; 2.03 (26,891); 1.22 (16,135); 0.81 (10,756); 0.41 (5,378). Malaria deaths per 100,000 population; 0.11 (15); 0.06 (8); 0.02 (3); 0 (0). Objectives - To achieve 100% coverage of the people living in endemic areas of 13 districts with effective preventive intervention (LLIN) by 2018. - To have 100% malaria patients received early and quality diagnosis (RDT or Microscopy) and effective treatment in 13 endemic districts by 2018. - To continue strengthening of programme management, disease and vector surveillance, M&E, coordination & partnerships. Outcome indicators Outcome Indicators; 2013 (Baseline); 2015-16; 2016-17; 2017-18. Proportion of population that slept under an insecticide-treated net* the previous night (disaggregated by sex); 80.30%; 85%; 90%; 90%. Proportion of children under five years old who slept under an insecticide-treated net* the previous night; 90.10%; 90%; 90%; 90%. Proportion of pregnant women who slept under an insecticide-treated net* the previous night; 85.40%; 90%; 90%; 90%. Programmatic Gaps, Modules and interventions, related activities Objective 1: Gaps - Saturation and replacement in eligible area @ 1.8 persons per LLIN. - Protecting special/vulnerable sections, viz. shifting cultivators, pregnant women and children. - Behavior change for utilization of vector control methods. - Mapping of vector breeding sources and management; inter-sectoral coordination. - Insecticide resistance monitoring. - Recording & reporting; supervision & monitoring. Module: Vector Control. Intervention; Description of Intervention; Additional information regarding activities and request for Indicative and Above. LLIN mass campaign (Responsibility: PR1 & PR2); > Target population in endemic areas of 13 districts (with 100% coverage by 2018). [Please refer to 'Target assumptions' in this file and 'Table 2: Programmatic Gap' (separate attachment)]. LLINs to be procured & distributed during 2014-15 have been considered in estimating quantity of LLINs. > Universal coverage (1 LLIN per 1.8 persons) in 03 CHT districts and Cox's Bazar. In addition, universal coverage of identified high endemic villages and Upzila areas in rest of the 09 low endemic districts. > The LLIN distribution will ensure coverage for key populations including pregnant women and under-5 children, Jhum Cultivators, forest goers, etc. > Ensuring LLIN use for maximizing personal protection will continue to be prioritized. > Moreover, treatment and re-treatment of community owned nets by GoB is envisaged. Focus will also be on additional personal protection measures for tourists, short term travelers, labourers in development projects etc., although the requirement will be met from GoB/other sources. > Implementation includes coordination, planning and budgeting, procurement, logistics, communication, implementation, training, M&E, etc. > LLINs will be procured by GoB through Voluntary Pooled Procurement (VPP) and distributed by jointly by BRAC led consortium and GoB as done previously. The quantities may be re-visited and re-set in mid-term, in the event there is any change in procurement & supply side scenario/mode and/or strategy regarding LLIN coverage, etc. > Funding for the entire quantity of LLINs is being proposed from the GF 'Indicative'. However, this concept note is proposed for July 2015 to December 2017 period in view of budget provision under NFM for 30 months and hence, such quantity is not indicated here (?).; > Activities: --GoB: Procurement of LLIN and supply to BRAC(funding source: 'Indicative') > Activities and cost assumptions for related components like training, recording/reporting, supervision & monitoring, HR, are indicated separately since those remain overarching. > Cost assumptions are based on LLIN cost under VPP & handling charges. > Activities: --BRAC: Distribution of LLINs from CMSD (GoB) to village level (includes warehouse rent and utilities at District/Upazilla); transportation expenses for speed boat/engine boat/vehicle; distribution of LLIN (funding source: 'Indicative') > Activities and cost assumptions for related components like training, recording/reporting, supervision & monitoring, HR, are indicated separately since those remain overarching. > The LLIN distribution cost is based on implementation experience, prevailing market rates, policy & gudelines and escalation factor (as applicable).. Output/coverage indicator: - Number of LLINs procured by PR1 for CHT and Cox's Bazar (I) - Number of LLINs procured by PR1 for 09 low endemic districts (I) - VC-1: Number of LLINs distributed to at-risk populations in CHT and Cox's Bazar (I) - VC-1: Number of LLINs distributed to at-risk populations 09 low endemic districts (I) Objective 2: Gaps - Access to services for early and complete treatment (provider availability; private sector; treatment seeking; knowledge of availability of services, etc.). - Microscopy (LTs, equipment, etc.). - Referral. - Management of severe and complicated malaria cases. - QA: RDT/microscopy. - Quality of drugs. - Recording & reporting; supervision & monitoring. - Monitoring therapeutic efficacy of antimalarials. - Evidence-based Behaviour Change Communication; Knowledge, awareness about EDCT, prevention; advocacy at all levels; recording/reporting; M&E (intervention: IEC/BCC covered under case management, although the messages will also cover prevention, etc.) Case Management. Intervention; Description of Intervention; Additional information regarding activities and request for Indicative and Above. Other (Responsibility: PR1 & PR2); > Activities: --GoB: > Activities: --BRAC:. IEC/BCC; > Activities: --GoB: > Activities: --BRAC:. Therapeutic efficacy surveillance; > This will include activities to conduct therapeutic efficacy surveillance by identified research institution.; > Activities: --GoB: For TES, Artemisinine resistance monitoring, the interventions are proposed under indicative budget. > Sites/samples may be drawn from various districts, as appropriate. > The costs are derived from the existing projects, prevailing market rates, etc. Related training, recording/reporting, supervision and monitoring, etc. are included in the package.. Output/coverage indicator: - CM-1a: Proportion of suspected malaria cases that receive a parasitological test at public sector health facilities (I) - CM-1a: Proportion of suspected malaria cases that receive a parasitological test at public sector health facilities (A) - CM-1b: Proportion of suspected malaria cases that receive a parasitological test in the community by health worker (I) - CM-2a: Proportion of confirmed malaria Pv cases receiving CQ+PQ (first-line antimalarial treatment) according to national policy at public sector health facilities (I) - CM-2a: Proportion of confirmed malaria Pv cases receiving CQ+PQ (first-line antimalarial treatment) according to national policy at public sector health facilities (A) - CM-2b: Proportion of confirmed malaria Pv cases receiving CQ+PQ (first-line antimalarial treatment) according to national policy in the community by health worker (I) - CM-2a (i): Proportion of confirmed malaria Pf cases receiving ACT+PQ (first-line antimalarial treatment) according to national policy at public sector health facilities (I) - CM-2a (i): Proportion of confirmed malaria Pf cases receiving ACT+PQ (first-line antimalarial treatment) according to national policy at public sector health facilities (A) - CM-2b (i): Proportion of confirmed malaria Pf cases receiving ACT+PQ (first-line antimalarial treatment) according to national policy in the community by health worker (I) - Proportion of Severe Malaria cases treated by PR1 (I) - CM-4a: Proportion of health facilities of PR1 without stock-outs lasting >1 week of nationally recommended anti-malarial drugs at any time during the past three months (I) - CM-4b: Proportion of health providers of PR2 (facilities, health workers) without stock-outs lasting >1 week of nationally recommended anti-malarial drugs at any time during the past three months (I) Objective 3: Gaps - Suitably qualified staff; Retention of trained staff/volunteer; remuneration commensurate with market; recognition of services - Supportive supervision & feedback; mobility of supervisory levels - Management Information System (including use of IT-mobile technology); case based surveillance in low endemic areas - Correct, complete & timely reporting - Impact evaluation (BCC, NGO, public sector treatments, etc.) - Multi-sectoral collaboration (Armed and paramilitary forces, Tea estates and other corporate entities) - Cross-border (inter-district, inter-state, inter-country-provinces/districts) planning and harmonization of interventions - Documentation and dissemination of information products. - Development of training plan; scheduling of trainings per plan; training facility; updated training module (facilitator, learner) in local language; training evaluation Health information systems and M&E. Intervention; Description of Intervention; Additional information regarding activities and request for Indicative and Above. Routine reporting; > M&E will be part and parcel of the program. The BRAC will M&E Plan will be in line with the NMCP plan/frameworks, according to the principle of “The Three Ones”. > A logical framework (Input-Process-Output-Outcome-Impact) will be applied for M&E. > M&E will follow established standards, ensuring quality, reliability, transparency, and usefulness. > M&E indicators are SMART (specific, measurable, achievable, realistic, and time bound) for measuring performance over the project life toward achieving desired objectives and goals. > MIS (paper & electronic based) will be intrinsic to M&E and standard data sources and approaches will be used for programmatic, logistics data collection, collation and analysis, etc. Existing MIS data collection tools (forms/ checklists) will continue. > Data quality audit including on site verification will be in-built element within the overall M&E. > Feedback, results dissemination and use will be key constituents. > Programmatic data will be accessible to all for use/decision-making. > Capacity building activities will address the challenges related to M&E and both PRs will be involved.; > Activities: --GoB: > Activities: --BRAC:. Analysis, review and transparency; > Overall approaches will remain aligned as mentioned above under routine reporting. > Regular review & planning meetings, supervisory visits/onsite data verification that focuses on quality of services; data quality audits, etc. will be carried out as being presently done. Feedback and orientation are also integral components during these reviews. The review meetings will be conducted jointly with the stakeholders. Already there is an established system of joint review meeting at various levels for program review and discussing solutions to issues/challenges, etc. > Impact evaluation is also being proposed that will look into innovation, best practices, etc. > Information products with program data, news of review and planning will be developed & disseminated in form of newsletters, reports, etc.; > Activities: --GoB: > Activities: --BRAC:. Program management. Intervention; Description of Intervention; Additional information regarding activities and request for Indicative and Above. Program/Grant management; > In order to sustain the progress made and smooth scale up of interventions further towards pre-elimination and elimination, it is proposed to continue with the existing structures. > In addition, infrastructure…NEED TO EXPAND; > Activities: --GoB: > Activities: --BRAC: > Activities include: Staff/consultants for PMU; Procurement of laptop, desktop, related hardware, software; Ongoing office expenses: Documentation, printing, stationery, data card, other office supplies; Planning & admin. costs (overheads/audit expenses), etc. > The costs are aligned with the Phase2 implementation, market rates, escalation factor, etc.. Health workforce. Health and community workers capacity building; > All training activities have training objectives; follow standardized approaches and methods including active learning/field exercises, and pre-and post- assessments as per guidelines. Standardized forms are used to establish a database for training activities. M&E of training is also ensured and is included in the overall one M&E framework.; > Activities: --GoB: > Activities: --BRAC: > Training/re-trainings of staff, health workers, volunteers; and revisiting existing training modules, customization, translation, replication, and dissemination > The costs are aligned with the Phase2 implementation, market rates, escalation factor, etc.. Other; > Community keep accessing the private health care service providers (PSPs) even though overall health systems continue. Mapping, training of private health care service providers commenced in the Phase2 as an initiative to improve rational treatment as per national protocol as well as broaden message dissemination platform through IPC by PSPs. > All training activities have training objectives; follow standardized approaches and methods including active learning/field exercises, and pre-and post- assessments as per guidelines. Standardized forms are used to establish a database for training activities. M&E of training is also ensured and is included in the overall one M&E framework.; > Activities: --GoB: > Activities: --BRAC:. Output/coverage indicator: - Number of nurses and doctors trained on mangement of severe malaria at District and Upzila level by PR1 (I) - Number of village doctors oriented on malaria management by PR2 (I) - Number of rapid response team members at District and Upzila level trained by PR1 (I) - Number of rapid response team members at District and Upzila level trained by PR1 (A) - Number of laboratory technicians of PR2 trained in malaria microscopy by PR2 (I) - M&E-1 (i): Percentage of HMIS or other routine reporting units of PR1 submitting timely, complete and accurate reports (I) - M&E-1 (ii): Percentage of HMIS or other routine reporting units of PR2 submitting timely, complete and accurate reports (I)

3.3 Modular Template

Complete the modular template (Table 3). To accompany the modular template for both the indicative and the above-indicative funding request, briefly: - Explain the rationale for the selection and prioritization of modules and interventions. - Describe the expected impact and outcomes, referring to evidence of effectiveness of the interventions being proposed. Highlight the additional gains expected from the above-indicative investment.

The Table 3 - modular template (with details) is attached with this concept note for kind perusal. The PRs are proposing the following priority modules, 05 in number (per GF framework) in the concept note for additional funding (‘Indicative’/’Above’) under NFM. The modules are selected per priority by the GoB and are in line with the NSP 2014-20, Regional and Global guidelines and imperative for moving forward to universal coverage towards malaria elimination. The priority modules, 05 in number (per GF framework) in the concept note include: - Vector control - Case management - Health Information System/M&E - Health Workforce - Programme Management Expected impact and outcomes are as under as mentioned in the previous section: Impact: - Confirmed malaria cases (microscopy or RDT) per 1000 persons per year - Malaria deaths per 100,000 population Outcome: - Proportion of population that slept under an insecticide-treated net the previous night (disaggregated by sex) - Proportion of children under five years old who slept under an insecticide-treated net the previous night - Proportion of pregnant women who slept under an insecticide-treated net the previous night DESCRIBE… The ‘Above’ allocation is requested for “Malaria Free Town”, a unique initiative of the NMCP-MOHFW together with local bodies and other stakeholders showing the feasibility (drawing from experience) and high impact in terms of no transmission. Already, towards phased pre-elimination and elimination in Bangladesh by 2020, malaria surveys are being undertaken in selected towns in coordination with the local authorities. This includes but not limited to, mapping of breeding sources and subsequent actions for source reduction. In addition, in these towns, identified health facilities are being equipped with logistics for focal IRS (with deltamethrin), chemical larvicides, case search and notification?, establishing Rapid Response Teams, etc. In other words, intensifying multi-pronged interventions are being planned to ensure that by 2020, no case/death is reported. These will contribute to overall impact and catalyze hastened return on investments, made possible by strong political & administrative commitments, an enabled environment. The best practice model is proposed to be replicated in villages in other districts. MORE FROM PROTOCOL…

3.4 Focus on Key Affected Populations and/or Highest-impact Interventions

This question is not applicable for low-income countries.

Describe whether the focus of the indicative and above-indicative funding request meets the Global Fund’s Eligibility and Counterpart Financing Policy requirements as listed below: - If the applicant is a lower-middle-income country, describe how the funding request focuses at least 50 percent of the budget on underserved and key affected populations and/or highest-impact interventions. - If the applicant is an upper-middle-income country, describe how the funding request focuses 100 percent of the budget on underserved and key affected populations and/or highest-impact interventions.

Clearly, more than 50% of the proposed budget is earmarked for underserved and key populations and high-impact interventions including but not limited to, reaching out to hard-to-reach areas especially with new tools and technologies, and others as well as monitoring, besides addressing possible emergence of threats to the broader disease response (like Artemisinin resistance).

SECTION 4: IMPLEMENTATION ARRANGEMENTS AND RISK ASSESSMENT

4.1 Overview of Implementation Arrangements

Provide an overview of the proposed implementation arrangements for the funding request. In the response, describe: - If applicable, the reason why the proposed implementation arrangement does not reflect a dual-track financing arrangement (i.e. both government and non-government sector Principal Recipient(s). - If more than one Principal Recipient is nominated, how coordination will occur between Principal Recipients. - The type of sub-recipient management arrangements likely to be put into place and whether sub-recipients have been identified. - How coordination will occur between each nominated Principal Recipient and its respective sub-recipients. - How representatives of women’s organizations, people living with the three diseases, and other key affected populations will actively participate in the implementation of this funding request.

As in the ongoing Phase2, the PR1 is the MoF, GoB that provides resource support to the NMCP through MOHFW. The PR2 is BRAC that leads a consortium of 20 NGOs. The PR1 will be mainly responsible for the planning, procurement of health products/pharmaceuticals and supply to PR2, implementation, and M&E and review/oversight of PR2 activities. The PR2, which is leading a NGO consortium will complement PR1 activities at community level in endemic districts. The major modules/interventions will include: LLIN distribution; RDT/ACT use; BCC; training of community workers/volunteers and private sector care providers; M&E/MIS. Outline of PR1 and PR2 are presented below: - Principal Recipient 1—PR1—MoF (NMCP), GoB: Policy & strategy, overall programme/grant management, oversight of and technical assistance to implementation of modules/interventions, advocacy and coordination, capacity building of personnel/consultants, M&E including reporting to GFATM, GOI, and joint planning and review, etc. and additional resource mobilization, research & evaluation. - Principal Recipient 2—PR2—BRAC : In alignment with the NMCP, strategic planning, overall programme/grant management, oversight of implementation of modules/interventions, advocacy and coordination, capacity building of personnel/consultants, M&E including reporting to GFATM, GoB, and joint planning and review, etc. and additional resource mobilization. In current Phase2 implementation in NE districts, the following SRs are partners in the journey, who have been and are being strengthened and capacitated over the years. In the event the Bangladesh-CCM deems appropriate, the same SRs will continue under the NFM after a rapid assessment of efficiency and effectiveness, etc. All Sub Recipients are responsible for: implementation of modules/interventions (prevention, diagnosis and treatment), BCC, M&E, etc. There is and will be a provision of coordination structures as in Phase2. These are: … Adequate planning and coordination mechanisms and joint planning has been built into the project management structure for smooth functioning of inter dependent outputs. In addition, the platforms like Joint Review meetings, Monthly meetings will remain important for addressing issues and arriving at locale- and context-specific- solutions. Besides, the PRs regularly are in day-to-day communication, for seeking inputs and validating the policy guidance as well as discussing programmatic achievements and lessons learned. Even the NSP 2014-20 have been prepared and currently being strengthened by the PRs together. The planning will be carried out at the central level and each PR will disseminate the same plan to the district/Upzilla levels for coordination at those levels. In the case of training by the PR2, the NMCP will take the lead and the training will be based on the training curriculum developed and approved by them. The resource persons will be from the GoB as well. Need to expand/firm up in discussion with PRs…

4.2 Ensuring Implementation Efficiencies

Complete this question only if the Country Coordinating Mechanism is overseeing other Global Fund grants.

Describe how the funding requested links to existing Global Fund grants or other funding requests being submitted by the Country Coordinating Mechanism. In particular, from a program management perspective, explain how this request complements (and does not duplicate) any human resources, training, monitoring and evaluation, and supervision activities.

As done through the implementation of ongoing Phase2, the PRs continue to have rationalized structures and systems. The program emphasizes on achieving optimal output utilizing the limited available resources and building human capacity at implementation level. The staff is optimally utilized and multi-task. The existing HR will be continuing under the NFM too. The PR2 has been and will ensure absence of duplication of any HR, training, M&E, and other activities. Community based BCC activities including IPC/mid-media activities and use of local radio are being use as effective intervention instead of relying on mass media which are mostly resource intensive towards enhancement of knowledge and awareness and behaviour change amongst targeted groups. Actual overhead cost is charged.

| 4.3 Minimum Standards for Principal Recipients and Program Delivery |  |  |  |
| --- | --- | --- | --- |
| Complete this table for each nominated Principal Recipient. For more information on minimum standards, please refer to the concept note instructions. |  |  |  |
| PR 1 Name | MoF, GoB | Sector | Govt |
| Does this Principal Recipient currently manage a Global Fund grant(s) for this disease component or a stand-alone cross-cutting health systems strengthening grant(s)? |  | ☐✓Yes ☐No |  |
| Minimum Standards |  | CCM assessment |  |
| - The Principal Recipient demonstrates effective management structures and planning |  | Yes, meets minimum standards. |  |
| - The Principal Recipient has the capacity and systems for effective management and oversight of sub-recipients (and relevant sub-sub-recipients) |  | Yes, meets minimum standards. |  |
| - The internal control system of the Principal Recipient is effective to prevent and detect misuse or fraud |  | Yes, meets minimum standards. |  |
| - The financial management system of the Principal Recipient is effective and accurate |  | Yes, meets minimum standards. |  |
| - Central warehousing and regional warehouse have capacity, and are aligned with good storage practices to ensure adequate condition, integrity and security of health products |  | Yes, meets minimum standards. |  |
| - The distribution systems and transportation arrangements are efficient to ensure continued and secured supply of health products to end users to avoid treatment/program disruptions |  | Yes, meets minimum standards. |  |
| - Data-collection capacity and tools are in place to monitor program performance |  | Yes, meets minimum standards. |  |
| - A functional routine reporting system with reasonable coverage is in place to report program performance timely and accurately |  | Yes, meets minimum standards. |  |
| - Implementers have capacity to comply with quality requirements and to monitor product quality throughout the in-country supply chain |  | Yes, meets minimum standards. |  |

| PR 2 Name | Caritas Bangladesh | Sector | CSO |
| --- | --- | --- | --- |
| Does this Principal Recipient currently manage a Global Fund grant(s) for this disease component or a stand-alone cross-cutting health systems strengthening grant(s)? |  | ☐✓Yes ☐No |  |
| Minimum Standards |  | CCM assessment |  |
| - The Principal Recipient demonstrates effective management structures and planning |  | Yes, the PR2 demonstrates effective management structures and planning. The PR2 is currently the nodal organization for planning, implementation, M&E coordination with GFATM, NVBDCP, state/district VBDCP, besides engaging in advocacy and sharing information at the national and state levels under the ongoing Phase2. Project Management Units are constituted at the central, district, Upzilla levels with multi-disciplinary personnel having relevant expertise and experience. Each structure and position has well defined roles and responsibilities and job description. Add specific details on structures from BRAC… |  |
| - The Principal Recipient has the capacity and systems for effective management and oversight of sub-recipients (and relevant sub-sub-recipients) |  | Yes, the PR2 has the capacity and system for effective management of SRs as demonstrated during the IMCP-II. The PR2 provides management oversight, ongoing capacity assessment and enhancement and support to SRs in the areas of both programme and finance. The PR2 developed an SR Management (SRM) Plan, which was duly approved by the GFATM, see Annex. The plan documents the systems and processes for implementation by the PR2 through SRs. The document provides guidance to the PR2 and the SRs on effective and transparent grant capacity building, implementation, coordination, management and reporting towards optimal grant performance. In addition, the PR2 developed and disseminated Operational Guidelines, M&E Plan, etc. For effective oversight, planning and coordination between PR and SRs, the PR established structures such as … committee that meet monthly/quarterly. On site programme and financial review and monitoring visits of the SRs are planned and conducted by the PR2. Besides this, periodic onsite data verification (OSDVs) and Rapid services Quality Assessments (RSQA) of the SRs are conducted drawing from the exercise conducted by the GF. Major focus is on identification and resolution of bottlenecks and challenges. Planning and review meetings with SRs are held periodically for programmatic and financial oversight and capacity enhancement of SRs. In addition, intensive review of programmatic and financial reports of SRs is done quarterly by the PR for ensuring correct, complete and reliable data is reported for sharing with the GFATM. Similar systems will continue under the NFM funding too. |  |
| - The internal control system of the Principal Recipient is effective to prevent and detect misuse or fraud |  | The PR2 has an established system of Internal Control within the organization to ensure compliance to policies, guidelines and procedures outlined in the GFATM grant agreement, guidelines, and overall organization policy and requirements. This is conducted by qualified independent auditors engaged by the organization as per set timeline and periodicity for all projects/programmes. The Auditor provides opinion on the overall systems and procedures of the organization along with necessary management actions, specific mention of IMCP-II is also made. In addition, as a part of its internal control systems, the PR2 (comprising of finance and programme team) conducts onsite visits of the SRs to ensure adherence to relevant articles of standard terms and conditions of the Grant Agreement, project guidelines and other requirements of GFATM. Similar systems will continue under the NFM funding too. |  |
| - The financial management system of the Principal Recipient is effective and accurate |  | The PR2 finance and accounts management section ensures effective and accurate grant funds management and oversight according to set guidelines & grant agreement; project budget management and periodic financial reporting from the SRs with proper standards of integrity, accountability, transparency, and stewardship for the use of grant funds. This established system manages efficient planning and forecasting, expenditure tracking and reviewing quarterly expenditure reports received from the SRs and most importantly ensures the execution of project audit for the PR2 and SRs. PR2 manages and oversees safeguarding of financial and physical assets. The SRs submits report on quarterly basis to the PR2 through Progress Update Disbursement Request Report which reports about project activities and expenditures incurred as per work plan and budget for said period. The PR2 monitors and reviews the actual expenditures against the approved budget and work plan and identifies variances. The SRs are required to provide adequate justification for variances in programmatic and financial report and prompt action is taken where necessary. Similar systems will continue under the NFM funding too. |  |
| - Central warehousing and regional warehouse have capacity, and are aligned with good storage practices to ensure adequate condition, integrity and security of health products |  | Warehousing facilities for LLIN that are aligned with the good storage practices (to ensure appropriate condition and security of health products) have been reviewed by the GF. These are monitored on a regular basis even by the GoB/LFA. Accordingly, all personnel are also trained and oriented on good storage practices. The premises are secured, spacious and meet essential conditions so as to avoid any form of damage to the LLIN, such as proper ventilation, no seepage in the room, pukka floor, plastered walls, etc. For a targeted area (village), the required number of LLINs is mostly distributed in one single exercise. Similarly, RDT/ACT, etc. received from GoB, are protected to ensure safety and their quality until such time as they are used, according to the NVBDCP guidelines. Necessary storage conditions for RDT/ACT as stated on the label and as per guidelines in terms of temperature, humidity, and protection from light to maintain quality are mostly followed throughout its shelf-life. Similar systems will continue under the NFM funding too. |  |
| - The distribution systems and transportation arrangements are efficient to ensure continued and secured supply of health products to end users to avoid treatment/program disruptions |  | The PR2 has demonstrated efficient distribution systems and transportation arrangements for delivering health products. In consultation and with the support of the GF, GoB, the PR2 ensures that there are security measures for transportation and health supplies without damage till the village level. The PRs maintain stock register and there is a system of reporting logistics supply status on a monthly basis. This facilitates routine assessment of supply status, noting consumption, calculation of actual requirements and tracking of expiry for necessary intervention. The PRs consult each other regarding rational forecasting and timely indenting where stock-out is anticipated. Similar systems will continue under the NFM funding too. |  |
| - Data-collection capacity and tools are in place to monitor program performance |  | Yes, the data collection capacity and tools are in place to monitor programme performance. The GFATM approved M&E plan of the PR2 provides guidance on the M&E and MIS as well as to foster and institutionalize capacity for robust M&E within the PR2 and their SRs towards steering focus on the intended ‘results’. The M&E system and structures capture data by using GoB approved Forms for various output/coverage indicators that are aligned to the goals and objectives of the project. The measurement of impacts/outcomes is the responsibility of the national programme—NMCP, GoB. The PR2 remains and will be involved in the exercise. All project personnel/health worker, volunteer at central, district, Upzilla and village level are trained, re-trained and continue to be capacitated on M&E including use of MIS tools/formats and data integration with the NMCP HMIS. The project personnel within the PR2 and SRs are assigned clear and specific M&E/MIS roles and responsibilities. The PR2’s MIS system and tools (formats) draw from and is harmonized with the NMCP HMIS’s defined systems, processes and forms related to case management and vector control. For ACSM, however, the PR2 uses own recording and reporting tools that have been prepared specifically for the purpose and duly endorsed by the NMCP. Similar systems/tools will continue under the NFM funding too. |  |
| - A functional routine reporting system with reasonable coverage is in place to report program performance timely and accurately |  | Yes, a functional (both computerized and paper based) routine reporting system exists for capturing of programmatic and financial performance monthly. Recording and reporting tools, timelines for submission reports and data flow are well defined for all existing cadres/structures within the consortium. At the Upzilla level, the reporting frequencies and timelines for routine reporting is synchronized with the monthly reporting requirements of NMCP MIS. The data in turns flow to the next reporting unit of PR too from the SRs for consolidation of quarterly report for submission to the GF. The web based BRAC MMIS application software is an efficient and reliable MIS for data entry, aggregation and analysis. The routine reporting system/web based MIS is validated and verified on a periodic basis by the GoB and an independent unit of BRAC and information generated from it helps in decision making and taking of necessary action wherever required. Similar systems will continue under the NFM funding too. |  |
| - Implementers have capacity to comply with quality requirements and to monitor product quality throughout the in-country supply chain |  | The GoB oversees and supervises the quality requirements pharmaceuticals and health products and monitor product quality throughout the supply chain, which includes quality assurance and control activities. These are being done following guidelines/policy and Standard Operating Procedures (SOPs) of the national programme. Similar systems/tools will continue under the NFM funding too. |  |

4.4 Current or Anticipated Risks to Program Delivery and Principal Recipient(s) Performance

- With reference to the Portfolio Analysis, describe any major risks in the country and implementation environment that might negatively affect the performance of the proposed interventions including external risks, Principal Recipient and key implementers’ capacity, and past and current performance issues. - Describe the proposed risk-mitigation measures (including technical assistance) included in the funding request.

No major risk has been identified as per external and internal audit reports, OSDV findings, JRM, MTR and OIG debriefing. Minor issues identified in those reports are partly met and remaining will be mitigated as per recommendations. However, in this concept note, certain possible risks related to the efficient and effective implementation of the program and existing and proposed risk mitigation measures are outlined. Those include: external risks, programmatic, financial, health product quality & service delivery and governance & oversight risks. Drawing from the implementation experience, various interventions/activities are being embedded in the overall program design. Implementation arrangements have been revisited and the concept note focuses on those aspects that will ensure that the program runs well, key populations have access to quality health services, and there are adequate fiduciary controls and programmatic oversight up to the community level; although certain external risks (remoteness/hard to reach areas, conflict situation, natural calamities like cyclones/landslides, macro-economic conditions) may continue to pose challenges. Many risks/issues relating to program implementation, grant management by PRs (and NGO-SRs) have been and will continue to be resolved through strengthened oversight, monitoring, capacity building as well as in extreme circumstances declaring certain expenditures as ineligible and holding the person/organization responsible. Certain risks and mitigation measures include but not limited to the following: The socio-political and eco-geographical constraints in certain districts may pose challenges in optimal program implementation. There could be few instances when service delivery may be temporarily erratic despite continuous strengthening of community ownership of malaria control is being emphasized by way of positioning health workers, volunteers within the overall community systems strengthening portfolio, that involves local networks as well as opinion and religious leaders especially in hard to reach areas. For any delay/postponement of initiatives that may be at times necessary in view of the local situation, efforts are being and will be made to resolve the problems through stakeholder discussions for mitigation locally. Procurement and supply of pharmaceuticals and health products are imperative for uninterrupted diagnosis and treatment service delivery. As in the ongoing Phase2, the procurement and supply will be the responsibility of the PR1-GoB. It is expected that supply-side situation will be conducive and provision of RDTs and ACTs as well as LLINs will be met. Both PRs have and continues to strengthen the district & Upzilla levels (including SRs) drawing from the lessons learned. Capacity building through trainings/re-trainings as well as on-job orientation/motivation remains key although staff turnover remains a challenge at times. Strengthening of M&E, PHPM, management of HR, finance management including but not limited to external and internal audit, etc. are being continuously done. The PRs are focusing on developing a culture of self risk assessment. Delay in GF disbursements and exchange rate fluctuation may impact cash flow. In addition, under-spending/overspending too are risks, which will need to be appropriately tackled. The GoB and BRAC propose to further strengthen the risk identification, assessment and mitigation through the programme/grant management cycle in a much more structured manner drawing from the Global Fund risk management approach and guidance. According to such guidance, the PRs will constantly monitor and assess internal and external events for uncertainty of not achieving targets and negative outcomes and impacts. The PRs will strive to rate the risks in terms of severity, materiality of the adverse outcomes and fix timelines for mitigation using the GF tool as shown below. Overall, key elements of a comprehensive risk management approach to be taken up will continue to include, but not limited to: - Organisational set-up: effective structure, competent staff in key positions, clear roles and responsibilities, hold people accountable. - Governance structure, action from the top, ethics and values, etc. - Effective internal control: policies, procedures, preventive controls (addressing identified risks) and independent monitoring, clear and transparent processes. - Measure progress: regular reporting, and risk based monitoring and supervision. - Ensure effective communication and information (transparency). - Create a risk-aware culture and open dialogue (PR, SRs). Other aspects will include: Guidelines will be used for programme management, M&E; Capacity building; HR and PSM plan; periodic assessments and necessary course correction.

CORE TABLES, COUNTRY COORDINATING MECHANISM ELIGIBILITY AND ENDORSEMENT OF THE CONCEPT NOTE

Before submitting the concept note, ensure that all the core tables, Country Coordinating Mechanism eligibility and endorsement of the concept note shown below have been filled in using the online grant management platform or, in exceptional cases, attached to the application using the offline templates provided. These documents can only be submitted by email if the applicant receives Secretariat permission to do so.

| ☐ | Table 1: Financial Gap Analysis and Counterpart Financing Table (The Financial Gap Table is embedded in the |
| --- | --- |
| ☐✓ | Table 2: Programmatic Gap Table(s) |
| ☐✓ | Table 3: Modular Template |
| ☐✓ | Table 4: List of Abbreviations and Annexes |
| ☐ | Country Coordinating Mechanism Eligibility Requirements |
| ☐ | Country Coordinating Mechanism Endorsement of Concept Note |

List of Abbreviations

ABER		Annual Blood Examination Rate

ACT		Artemisinin-based combination therapy

API		Annual Parasite Incidence

BCC		Behaviour Change Communication

BSE		Blood Slide Examination

CCM		Country Coordinating Mechanism

CSO		Civil Society Organisation

DQA		Data Quality Audit

EDCT		Early Diagnosis and Complete Treatment

GFATM		The Global Fund to fight AIDS, Tuberculosis and Malaria

GoB		Government of Bangladesh

HMIS		Health Management Information System

HSS		Health Systems Strengthening

IRS		Indoor Residual Spraying

ITN			Insecticide Treated (bed) Nets

LFA		Local Fund Agent

LLIN		Long Lasting Insecticidal Nets

LMIS		Logistics Management Information System

LT		Laboratory Technician

MDG		Millennium Development Goals

M&E		Monitoring and Evaluation

MIS		Management Information System

MOHFW		Ministry of Health and Family Welfare

NGO		Non- Governmental Organisation

Pf		Plasmodium falciparum

PHPM		Pharmaceutical and Health Products Management

PR		Principal Recipient

PSM		Procurement and Supply Management

PSCM		Procurement and Supply Chain Management

PUDR		Progress Update Disbursement Request

Pv		Plasmodium vivax

QA		Quality Assurance

RBM		Roll Back Malaria

RDT		Rapid Diagnostic Test

RRT		Rapid Response Team

RSQA		Rapid Service Quality Assessment

SDA		Service Delivery Areas

SfR		Slide falciparum Rate

SOP		Standard Operating Procedures

SPR		Slide Positivity Rate

SR		Sub Recipient

SSF		Single Stream Funding

TA		Technical Assistance

TOR		Terms of Reference

TPR		Test Positivity Rate

VBD		Vector Borne Diseases

WHO				World Health Organisation

List of Annex:

- Strategic Plan for Malaria Control in Bangladesh: 2014-2020

- Sub-recipient Management Plan.

- Epidemiological data.

Countries with high co-infection rates of HIV and TB must submit a single concept note for HIV and TB (the template will be available in January 2014). Countries with high burden of TB/HIV are considered to have a high estimated TB/HIV incidence (in numbers) as well as high HIV positivity rate among people infected with TB.

Drawn from presentations made by the Global Fund team in the CSO Risk Forum, Bangkok, Thailand, November 2013