GRM MANUAL

Bangladesh Environmental Sustainability and Transformation (BEST) Project

Department of Environment (DoE),

Bangladesh Bank (BB),

Bangladesh Road Transport Authority (BRTA),

Bangladesh Hi-Tech Park Authority (BHTPA)

Date: May 2023

Table of Contents

Table of Contents

Introduction	4

GRM Objective and Scope/Boundary	10

GRM Structure (including GRCs at various Levels) and Responsibilities (Adopt to the Project)	10

GRM Process (Uptake, Investigate, Response, Closure)	11

GRM Uptake Channels	14

Sexual Exploitation and Abuse/ Sexual Harassment (SEA/SH) GRM	16

Training and Capacity Building of GRM Staffs	20

GRM Public Communication Channel	23

Budget and Human Resources	24

COMPLAINT FORM  Bangla	27

GRC REVIEW MEETING MINUTES AND DECISION FORM	31

M&E/ QUARTERLY COMPILATION REPORT FORM	33

GRM RESOLUTION SATISFACTION FORM (Needs Bangla Translation)	34

SEA/SH Consent Form	35

POTENTIAL GRIEVANCES FOR THE PROJECT	36

GRIEVANCE REDRESS MECHANISM CHECKLIST	38

SEA/SH SERVICE PROVIDE LIST FOR THE PROJECT	41

Project GRM Manual

# Introduction

The Project Grievance Redress Mechanism (GRM) is an instrument through which dispute resolution is sought and provided. It involves the receipt and processing of complaints from individuals or groups directly and negatively affected by activities of the project. It also provides an avenue to raise issues, concerns and feedback on the project.

The Project’s objective is to: strengthen the capacity of the Government of Bangladesh in environmental management and to pilot new financing mechanisms to promote green investments in targeted sectors.

The Project will be implemented in:

- Khulna, Mymenshing, Rajshahi, Rangpur, Sylhet, Barishal (for Component 1-Divisional Office)

- Rajshahi, Shirajgonj, Nowgaon, Pabna, Tangail, Dhaka, Gazipur, Narsingdi, Munshiganj, Narayanganj, Kishoreganj, Cumilla, Brahmanbaria, Khagrachari, Noakhali, Laxmipur, Chottogram, Feni, Mymenshing, Jamalpur, Sherpur, Netrokona, Habiganj, Moulavibazar, Sylhet, Panchagor, Kurigram, Bhola, Satkhira, Jhinaidah, Khulna and Bagerhat, Cox’s bazar (for Component 1-District Office);

- Mymensing, Faridpur, Cumilla and Noakhali (for Component 3); and

- Gazipur (for Component 4)

The Implementing Agency of the Project is:

- Department of Environment (DoE),

- Bangladesh Bank (BB),

- Bangladesh Road Transport Authority (BRTA),

- Bangladesh Hi-Tech Park Authority (BHTPA)

The stakeholders for the Project are categorized as follows:

| Component | Stakeholder | Influence |  | Interest |  |
| --- | --- | --- | --- | --- | --- |
| Project Affected People |  |  |  |  |  |
| 1 - Environmental governance and Infrastructure | - General Public including women representatives - People impacted by economic and physical displacement including informal settlers | Low |  | Low |  |
| 2 – Green Financing | - Workers in the selected Brickfields including women, adolescent girls, members of the marginalized community working in the brick kiln and their family members. - Shopkeepers, restaurant owners etc. beside the Brick Kilns whose business in primarily dependent on the Brickfield Workers. | Low |  | Low |  |
| 3 – Vehicle Inspection Center VIC | - Private and Commercial Vehicle Owners under the jurisdiction of the VICs planned. - Different Transport Owners and Transport Workers Association plying commercial vehicles under the jurisdiction of the VICs planned. | Low |  | Low |  |
| 4 – E-waste Management Infrastructure | - Individuals including women, members of the minority community/groups who are directly involved with collection, dismantling, sorting, recycling and transportation of E-Waste from source areas to the Pilot E-waste Management Infrastructure at Kaliakair HTP. - Scavenger that collect the E-waste items from landfills and open dustbins for recycling and the buyer Chain of the E-waste recyclable goods. | Low |  | Low |  |
| Other Interested Parties |  |  |  |  |  |
| 1 - Environmental governance and Infrastructure | - Ministry of Finance - Finance Division, - Banking Division, - Planning Commission - Economic Relations Division - Ministry of Environment, Forest and Climate Change (MOEFCC) - Department of Environment (DOE) - Ministry of Road Transport and Bridges (MORTB) - Ministry of Local Government, Rural Development and Cooperatives (MOLGRDC) - Ministry of Posts, Telecommunications and Information Technology (MOPTI) - Prime Minister’s Office (BEZA) - Ministry of Law, Justice and Parliamentary Affairs - Parliamentary Standing Committee on Environment, Forest and Climate Change - Bangladesh Civil Services (BCS) | High |  | High |  |
|  | - CBOs/ Think Tank on Environmental Issues - Media | Low |  | High |  |
|  | - BUET - Bangladesh Council of Scientific and Industrial Research (BCSIR) - International Union for Conservation of Nature and Natural Resources (IUCN) - Research Organizations and other Universities working on Environmental issues | High |  | High |  |
|  | - Local NGOs working on HR, Gender, Labor, Environment and Waste Management including Medical Waste: Waste Concern, PRISM Bangladesh, Geocycle Bangladesh etc. | Low |  | High |  |
|  | - Job seekers for employment in DOE that include the disabled, women, members of the minority and the transgender community. | Low |  | High |  |
|  | - All type of Industries and Factories that emit pollutants in the country and their Associations (BGMEA, BKEMA, REHAB, Tannery Association, Paint production and Dyeing Industries, Insecticide/pesticide Industries, Brick Kilns, Stone Crushing Industries, Cement Factories, Steel Re-rolling Mills, Ship Breaking Industries, Tobacco Companies etc. | High |  | High |  |
|  | - WB-IDA, IFC - Other DPs including ADB, JICA, the Foreign, Commonwealth and Development Office (FCDO) | High |  | High |  |
| 2 – Green Financing | - MOF - Planning Commission - MOEFCC - DOE | High |  | High |  |
|  | - Selected Eligible Brick kilns ready for HHK and Tunnel Kiln Modification - Bangladesh Brick Manufacturing Owners Association (BBMOA) - Bangladesh Auto Brick Manufacturers Association (BABMA) - Brickfield Workers Association in the project locations | Low |  | High |  |
|  | - National/International Vendors and Contractors - Coal Exporters, Suppliers and transport sector people including owners, drivers and laborers involved in transporting Coal and fire wood to the Brick Kilns | Low |  | High |  |
|  | - General public, targeted consumers, Consumer Groups - Industrial Associations - Media Outlets, civil society - NGOs/CBOs working on Labor, Gender and Community health Issues | Low |  | High |  |
|  | - BUET - Bangladesh Housing and Building Research Institute - Bangladesh Council of Scientific and Industrial Research (BCSIR) - International Union for Conservation of Nature and Natural Resources (IUCN) - Local NGOs working on HR, Gender, Labor, Environment and Waste Management. - Research Organizations and other Universities working on Environmental issues | High |  | High |  |
|  | - Bangladesh Bank - Credit Guarantee Unit - Sustainable Finance Department (Technical Oversight) - 5-10 Selected Participating Financial Institutions (PFI) | High |  | High |  |
| 3 – Vehicle Inspection Center | - Ministry of Finance - MOEFCC - DOE - PPP Partners responsible for developing 5 new Vehicle Inspection Centers | High |  | High |  |
|  | - BRTA - Dhaka Transport Coordination Authority (DTCA) - Dhaka Transport Coordination Board (DTCB) - Roads and Highways Department - Dhaka Metropolitan Police (Traffic Division) | High |  | High |  |
|  | - National/International Vendors and Contractors - Local community and businessmen | Low |  | High |  |
|  | - Media - NGOs/CBOs working on Labor, Environment and Community Health Issues - Research Organizations and other Universities working on Environmental issues | Moderate |  | High |  |
|  | - WB-IDA, IFC - Other DPs including ADB, JICA, the Foreign, Commonwealth and Development Office (FCDO) | High |  | High |  |
| 4 – E-waste Management Infrastructure | - MOF - MOLGRD&C - MOEFCC/DOE - MOPT&IT - PM’s Office (BEZA) - BHTPA - PPP partners involved with E-waste management facility at Kaliakair HTP - and other HTPs managed by BHTPA across the country | High |  | High |  |
|  | - National/International Vendors and Contractors and Local Businessmen interested to have a share in the contract of developing E-waste Management Facility | Low |  | High |  |
|  | - Producers, dealers, collection centers, refurbishing companies, dismantlers, recyclers, auctioneers, consumers and bulk consumers involved in the sale, purchase and processing of electrical and electronic equipment or components | Low |  | High |  |
|  | - Bulk users of electronic gadgets namely Military, Para military and Intelligence Organizations, Civil Aviation Authority, mobile phone companies, embassies, Hotels, Commercial Banks, ICT gadget/mobile phone manufacturers, Service sector including Hotels and Tourism, E-Commerce entities, manufacturers, Hospitals and diagnostic Centers, large shopping malls selling computers, mobile phones etc. at Eastern Plaza, Banani DCC Market, Elephant Road, BCS Computer City at Agargaon, Cineplexes, and other users of computers, radio frequency items, radar, mobile phones, jammers and other electronic generating E-waste | Low |  | Low |  |
|  | - BUET - Research Organizations and other Universities working on Environmental issues - Bangladesh Council of Scientific and Industrial Research (BCSIR) - International Union for Conservation of Nature and Natural Resources (IUCN) | High |  | High |  |
|  | - Media - NGOs/CBOs working on HR, Gender, Labor, Environment and Community health Issues - Local NGOs working on Waste Management | Low |  | Low |  |
|  | - WB-IDA, IFC - Other DPs including ADB, JICA, the Foreign, Commonwealth and Development Office (FCDO), Norwegian Embassy, UNIDO, GIZ, UNDP | High |  | High |  |
| 5. Contingency Emergency Response Component (CERC) | - MOF, MOEFCC/DOE, BB, BRTA, BHTPA, PFIs, PPP Partners - WB-IDA, IFC - Other DPs including ADB, JICA, the Foreign, Commonwealth and Development Office (FCDO), Norwegian Embassy, UNIDO, GIZ, UNDPs | High |  | High |  |
| Vulnerable Groups and Individuals |  |  |  |  |  |
| Component 1: Environmental governance and Infrastructure | The VG in this component include: a. Job seekers for employment in DOE that would include the disabled, women, members of the tribal community and members of the transgender community. b. Women, in general, who may fall prey to GBV/SEA/SH, STD related incidents due to presence of migrant workers at various subproject sites where district level DoE offices/Regional Laboratories are planned to be developed. c. People impacted by economic or physical displacement, including informal settlers. |  |  |  |  |
| Component 2: Green Financing | a. Workers of the selected brick kilns, particularly women who may lose job temporarily as transformation would take time and during that period no brick would be produced. b. Women/minor children including adolescent girls working/residing at the selected brick kilns/ in the vicinity may fall prey to GBV/SEA/SH, STD related incidents due to presence of migrant workers involved with transformation work of the kilns. |  |  |  |  |
| Component 3: Vehicle Emission Control | Private and Commercial Vehicle Owners and different Transport Owners and Transport Workers Association who could be victims of corruption/ harassment by BRTA staffs at the Vehicle Inspection Centers |  |  |  |  |
| Component 4: E-waste Management Infrastructure | a. Individuals including women, members of the minority community/groups who would directly be involved with collection, dismantling, sorting, recycling and transportation of E-Waste from source areas to the Pilot E-waste Management Infrastructure at Kaliakair HTP. b. Scavenger that collect the E-waste items from landfills and open dustbins for recycling and the buyer Chain of the E-waste recyclable goods c. Workers including women, members of the minority community and staffs at the Pilot E-waste Management Infrastructure at Kaliakair HTP who would deal with E-waste. |  |  |  |  |
| Component 5: Contingency Emergency Response Component (CERC) | All components would be able to gain rapid access to bank financing to respond to an eligible crisis or emergency that causes major adverse economic and/or social impacts. |  |  |  |  |

The GRM will assist the PMU to ensure that deliberate processes and procedures are put in place to capture, assess and respond to concerns from project beneficiaries, project executors and the general public during the implementation of the Project. This will ensure smooth implementation of the projects and timely and effectively addressing of the problems that would be encountered during implementation.

# GRM Objective and Scope/Boundary

The Project GRM has the following objectives:

- Establish a prompt, easy to understand, consistent and respectful mechanism to support the receiving, investigating and responding to complaints, feedback or grievances from the stakeholders

- Ensure proper documentation of complaints, feedback or grievances and any corrective actions taken; and

- Contribute to continuous improvement in performance of the Project implementation through the analysis of trends and lessons learned.

The scope of this Project GRM will be limited to:

- Any harm or impact caused directly by the project activities.

- Any indirect impact caused by the project activities (for example loss of business due to rerouting of road alignment, where no land acquisition was made to the party) will not be covered by the Project GRM. However, if the grievance screening finds a complaint to be inadmissible due to lack of linkage with the Project, the Complainant may be redirected to other National/ Legal/ Law Enforcement services.

- Complaints already under consideration of a Court of Law will not be under the purview of the GRM. However, any Complainant will not be barred from seeking redress from the national Legal or Law Enforcement Agencies.

# GRM Structure (including GRCs at various Levels) and Responsibilities

The following table illustrates the various GRC structure, their responsibilities and timeline:

| Level | Organogram | Role | Timeline |
| --- | --- | --- | --- |
| Tier 1 – Local GRC | Local GRC Head Member 1 Member 2 Secretary GRC Uptake Staff At least one will be a female member. They may be posted to subproject sites. AD, District DoE Office | Uptake Staffs: - Maintain and implement GRC uptake channels (Phone, SMS etc) - Log in grievances and provide tracking number - Receiving grievances for logging forwarded from other Tiers - Intimating progress to Complainant - Keeping and maintaining Logbook and files - Report quarterly progress to Tier 2 Local GRC: - Ensure GRM is publicized locally - Screening against eligibility criteria (If admissible or not) - Carryout inquiry on eligible grievances - Arrange to solve simple complaints informally - Consult with Contractors and other parties against whom complaints have been launched and mediate, if feasible - Carryout GRC meeting and provide final decision on complaints - Forward complaints to Tier 2 if Complainant is not satisfied with resolution - Refer to Legal and law Enforcement Agencies, NGO if deem fit - Carryout local stakeholder consultation quarterly - Provide GRM related training to staffs - Monitor GRM progress | Uptake to Initial Feedback on eligibility and next course of action = 48 hours Eligibility acceptance to Tier 1 Resolution = 16 days |
| Tier 2 – District Level GRC | District GRC Head Member 1 Member 2 Secretary At least one will be a female member. DD/ DG District/ Divisional Offices | - Monitor GRM status of Tier 1 - Local GRC - Combine the report of all Tier 1 GRC and provide feedback to Tier 3 PMU GRC - Inquire and decide on cases forwarded from Tier 1 GRC - Forward case to Tier 3 GRC if unable to decide or if decision rejected by Complainant - Train own staffs on GRM - Monitor GRM Progress of Tier 1 - Arrange meeting with stakeholders - Provide guidance to Tier 1 Local GRCs | Receive from Tier 1 to Resolution = 15 days |
| Tier 3 – PMU Level GRC | GRC Head/Chairman, SDS - GRC Secretary, Member 1, Member 2, Member 3, GRC Database Officer/Aggregator, Telephone/SMS Receiver Min two females. One will be trained SEA/SH Coordinator ADG, DoE | - Develop GRM policy and implement - Train staffs on GRM Procedure and provide guidance incl SEA/SH GRM - Provide logistics to various GRCs - Develop and maintain various uptake channels - Monitor GRM progress of Tier 1 and 2 - Compile GRM database and share with World Bank and PMU (GRM Aggregator) - Carryout field visits - Provide resolution to complaints forwarded from Tier 2 GRC - Ensure Telephone/SMS receivers receive complaints and forwards to Tier 1 GRC and keep log of complaints - Carryout high-level stakeholder consultation - Maintain database of all GRC members at all Tiers - Be responsible for addressing SEA/SH issues | Receive from Tier 2 to Resolution = 15 days |

# GRM Process (Uptake, Investigate, Response, Closure)

The Project GRM process will be followed as under. This will be tested in the field and may be changed depending on practicality.

| Stage | Activities | Responsibility | Timeframe |
| --- | --- | --- | --- |
| Uptake | Carryout activities listed as per GRM Uptake Channel paragraph. If complaint not eligible as decided by first tier intimate the Complainant and refer him/her to Legal/Law Enforcing Agency/NGOs etc if the complainant desires If eligible, Tier 1 will begin their activities | The Uptake staffs assigned at each field office. If complaint is received via telephone, SMS, Website and email these will be referred to the uptake staffs of that specific field office where the complaint originates who will record, assign tracking number and follow Activities 1 and 2. | The Complainant will be informed if the complaint is legible or not within 48 hours |
| Screening for Eligibility (Just after uptake) | After receiving complaints Tier 1 GRC will test complaint for eligibility. The eligibility will be informed to Uptake Channel staffs | The Tier 1 GRC will be responsible to inform Uptake Channel staffs of eligibility | Eligibility will be intimated to Uptake Channel Staffs in less than 48 hours |
| Complaint Assessment | If the initial assessment establishes the eligibility of the complaint to be pursued, a further assessment is recommended of the seriousness of the complaint—classified in terms of high, medium, or low—and its impact on both the complainant and the project. Criteria for classification include the following: - severity of the problem, - potential impact on the well-being of an individual or group, - potential impact on the project, and - public profile of the issue. Additional data collection through field visits to the sites, discussions and interviews with Complainants and other relevant persons or groups in the community, and cross-checking the information already provided will be required. This phase is an investigation phase | Tier 1 GRC | 3 working days from eligibility intimation to intimation to Complainant of a solution/ option |
| Formulate a Response | Having completed the complaint assessment, a response along with options will be formulated on how to proceed with the complaint for solution. This response should be communicated to the complainant. The response should include the following elements: - acceptance or rejection of the complaint - reasons for acceptance or rejection - provide an initial solution including options - a time frame; and - further documents or evidence required for investigation, if required. In case further evidence is required, the GRC will carryout further investigation with new evidence and repeat the process above | Tier 1 GRC | 3 working days from option intimation to agreement with the Complainant about solution |
| Implementing the Solution (if accepted) | If Complainant agrees with the solution the GRC will settle grievances through: - requesting the relevant agencies responsible for the grievance to take appropriate measures to remove the cause of grievance (e.g., contractors to clear access roads or provide alternative roads, clear canals and other irrigation systems, remove garbage, warn workers or take disciplinary measures against workers etc) - provide timeline for the resolution by the responsible party - signing agreements between Affected Parties (APs) and the GRC for solutions mutually agreed upon - initiating a monitoring process to see if the agreed actions are being implemented or not - After action is completed, intimate the Complainant and get his/her signature in GRM Resolution Satisfaction Form | Tier 1 GRC | 10 working days from agreement |
| Implementing the Solution (if not accepted, or for a complex issue not under Tier 1 jurisdiction) | The complaint will be forwarded to Tier 2 with intimation to the Complainant about timeline. Monitor complain handling process | Tier 1 GRC | 2 working days from solution being unaccepted by Complainant |
|  | Tier 2 GRC will repeat complain resolution process mentioned above for Tier 1. Complaint resolution and options will be intimated to Tier 1 by Tier 2 who will interact with the Complainant. Resolution activities will also be coordinated by Tier 2. For complex issues, Tier 2 will directly contact Complainant | Tier 2 GRC | Presentation of solution in 15 working days from receiving complain from Tier 1 |
| If Tier 2 Solution is not accepted | Tier 2 will forward the Complaint to Tier 3 and same process will follow | Tier 3 GRC | Presentation of solution in 15 working days from receiving complain from Tier 2 |
| Complaint Evaluation | An evaluation system should assess the overall effectiveness and the impact of the GRM. Such evaluations will take place biannually, and their results should contribute to improving the performance of the GRM and provide valuable feedback to PMU. The following questions will be addressed in such evaluations: - How many complaints have been raised? - What types of complaints have been raised? - What is the status of the complaints (rejected or not eligible, under assessment, action agreed upon, action being implemented, or resolved)? - How long did it take to solve the problem? - How many APs have used the grievance redress procedure? - What were the outcomes? - Is the GRM effective in realizing the stated goals, objectives, and principles? - Is the GRM capable of responding to the range of grievances specified in their scope? | All GRC Tiers | Biannually |
| Note 1: for serious Complaints (GBV, fatality, near misses, hazardous spill etc) initial reports must be given to PMU and World Bank within 24-hour time Note 2: Complainant will not be barred from seeking redress from Legal/ Law Enforcement/NGOs. All Tiers of GRC should maintain a good communication network with them, including local Government officials so that Complainant referred to these agencies can be given adequate attention. Note 3. The above processes should not create incentives for Affected Parties (APs) to seek further redress (e.g., by having the Tier 2 routinely yield more benefits or higher compensation than Tier 1 etc.). The process should not encourage unjustified multiple appeals. Note 4. GRCs must upkeep Complaint Forms, GRC Review Meeting Form, M&E/Quarterly Report Compilation Form and GRM Satisfaction Forms – both blank and those filled by the GRM process for future references. Filled form must also be saved digitally |  |  |  |

# GRM Uptake Channels

There will be several uptake channels for complaints to be received:

| Channel | Particular | Timetable | Responsibility |
| --- | --- | --- | --- |
| Face-to-Face | There will be a number of field offices, and each field office will nominate an individual to register complaints. He/ She should have a register to note the complaints and complaint forms to fill up. The form will be signed by both the staff and the Complainant. | Will be operated from 6 AM to 6 PM (12 hours) This information must be disseminated to the public | The complaint desk will be manned during working days only. For non-working days, virtual means (SMS, Telephone, email etc) will be suggested. The field level staff will welcome the Complainant and make him/her comfortable and begin with greetings. The staff will note, fill up the company form (Annex A), get complainant’s signature and sign the form him/herself. The Staff will also provide estimated timeline and a tracking number. The Staff will also intimate the first GRC tier for eligibility checking as well as the Central GRC aggregator for compilation. After eligibility check by the first tier, the Staff will inform the Complainant if the complaint is eligible to be considered or otherwise. If not eligible, the Complainant will be provided other options (NGO, police, legal etc) |
| Telephone | 02-8181767 | Will be operated from 6 AM to 6 PM (12 hours) | Will be manned by two operators working 6 hours shifts. One female and one male. Will be open 7 days a week, even in Government holidays. Following will be noted (Action 1): Name and address (none required if anonymity sought) Complaint, in summary Nature of Complaints If it is project related. Complaint against, if any Operator will (Action 2): Register the complaint in a register Provide a tracking number Provide a timeline Fill up Complaint Form for filing (Complainant’s copy may not be feasible for virtual filing) Intimate the first tier of GRC about the complaint Intimate Central GRC aggregator After eligibility check by first tier, inform the complainant if the complaint is eligible to be considered or otherwise. If not eligible, the complainant will be provided other options (NGO, police, legal etc) |
| SMS | 01712204704 (different from above number) | Will be operated from 6 AM to 6 PM (12 hours) | Will be manned by above two operators. After SMS is received, Operator will call back and execute above steps |
| Email | grs@doe.gov.bd | Will be monitored as per above timing (12 hours) | Will be operated by the Social Development Specialist/Communication Specialist/ Any other nominated staff of the PMU at Project Office. If no details are given will request number (Action 1) above. If phone number is given, the Complainants will be called to get the above information, else email will suffice. Then the Staff will carry out Action 2 above. |
| Website | www.doe.gov.bd/GRS | Will be monitored as per above timing (12 hours). The site will provide a format for complaint registration. This will include info required in Action 1 above. The complaint will be redirected to the email above with a Subject GRM From Web – Date and Time. | As above |
| Letter | Director General Bangladesh Environmental Sustainability and Transformation (BEST) Project Department of Environment, Paribesh Bhaban, Agargaon, Sher-e-Bangla Nagar, Dhaka 1207. Phone: 02-222218500 | Will be received and opened during office hours | After the letter is received, the complaint will be studied and if ineligible, it will be intimated to the Complainant including provision of other options. If eligible Action 1 and 2 above will be implemented |
| Suggestions Box | Suggestion Boxes will be placed in front of every field office | Will remain open round the clock. Will be opened during the beginning of office hours by the staff responsible to register complaints in each field office | As above |

# Sexual Exploitation and Abuse/ Sexual Harassment (SEA/SH) GRM

Some basic definitions:

Sexual exploitation. Any actual or attempted abuse of position of vulnerability, differential power, or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially, or politically from the sexual exploitation of another. In World Bank-financed operations, sexual exploitation occurs when access to or benefit from Bank-financed goods, works, non-consulting services or consulting services is used to extract sexual gain.

Sexual harassment. Any unwelcome sexual advances, request for sexual favors, verbal or physical conduct or gesture of a sexual nature, or any other behavior of a sexual nature that might be reasonably expected or perceived to cause offense or humiliation to another when such conduct interferes with work; is made a condition of employment; or creates an intimidating, hostile, or offensive work environment.

Sexual exploitation and abuse (SEA) versus sexual harassment (SH). SEA occurs against a beneficiary or member of the community. SH occurs between personnel/staff and involves any unwelcome sexual advance or unwanted verbal or physical conduct of a sexual nature. The distinction between the two is important so that PMU policies and staff trainings can include specific instruction on the procedures to report each.

The Importance of Consent in the Handling of SEA/SH Cases

Anyone involved in grievance mechanisms for SEA/SH GRM should remember:

Consent must be informed, which means that the survivor must be aware of and understand what all available options entail. The information provided should be comprehensive, detailed, and communicated in a way which is easy to understand.

Obtaining consent relates not only to the service provision referrals, but also to the utilization of the grievance mechanism itself.

Consent is a process that can change. For example, some survivors may withdraw their consent during the process, possibly to ensure their own safety. Such a choice must be respected.

Consent must always be respected, even when there seems to be little or no risk to the survivor.

The survivor’s consent prevails over any person’s desire to investigate and understand the truth.

Any information about a survivor’s story— even if anonymized—should only be shared if the survivor has given consent.

Consent should be documented: survivors can choose to complete, sign, or fingerprint a consent form specifying their choices regarding sharing information about their cases with other agencies or individuals, including for what purposes. (See Annex E for a sample consent form).

Consent must be mainstreamed throughout the mechanism through pre-established safe and ethical information-sharing protocols and systems for recording and storing information.

Obtaining the consent of children is different than obtaining the consent of adults. Children are considered unable to provide consent because they do not have the ability and/or experience to anticipate the implications of an action, and they may not understand or be empowered to exercise their right to refuse. Special provisions are required for SEA/SH allegations that involve minors, especially given how vulnerable they are, including child-friendly feedback channels and specialized training for staff. Parent or guardian are required to accompany the child.

SEA/SH GRM Process

The following will be the steps to be followed addressing SEA/SH GBV cases:

| STEP | FUNCTION | DETAILS |
| --- | --- | --- |
| Uptake | Receive SEA/SH allegation through multiple reporting channels established for the project | Project GRM channel will be used. Survivor must be informed that her/his wishes to continue with the case will prevail. Upon receiving the allegation, the survivor will be immediately referred to PMU level GRC who will deal with the case in its entirety, given its sensitivity and requirement of training. PMU GRC will have staff trained and assigned for SEA/SH cases |
| Sort and process | Document and register allegation | The SEA/SH coordinator at PMU GRC is responsible to document and register the allegation. It can be done over phone, video conferencing or in person (suggested). The coordinator needs to visit the survivor in person immediately after initial documentation, if the survivor consents to proceed with the case and consent for the Coordinator to disseminate the four information. The SEA/SH allegation will document only (1) the nature of the allegation—what a survivor says in his or her own words without direct questioning; (2) if, to the best of the survivor’s knowledge, the perpetrator is associated with the project; (3) when possible, the age and sex of the survivor; and (4) when possible, information about whether the survivor was referred to services (Health, psychosocial, legal etc). |
|  | Inform survivors about legal and internal data-sharing obligations | If applicable, the survivor will be informed about any legal obligations to report SEA/SH to the Police. Wherever possible, this information should be delivered to the communities and the survivor prior to the disclosure of any information that could trigger mandatory reporting, both through community awareness-raising activities and by providing information as a first step in the uptake phase. Survivor must consent to share the four non-identifiable data with PMU and WB. In the absence of consent, there should be absolutely no data sharing, in line with the principle of survivor-centricity. |
|  | Notify the World Bank in accordance with the required reporting protocols | If a survivor gives consent, the SEA/SH coordinator will inform PMU and WB on the four sets of data. Else, only an intimation to the WB and PMU about the survivor’s non-consent will be made |
| Acknowledge and follow-up | Refer the survivor to relevant GBV service providers | Note: A List of various SEA/SH service providers (Medical, psychosocial, legal, livelihood etc) will be kept at the PMU GRC Coordinator (Annex F). At this stage the survivor will be referred to various service providers. Before referral, the survivor’s consent must be documented. This means that the survivor can choose to fill out, sign, or fingerprint a consent form that outlines the survivor’s choices regarding whether information about the case is shared and whether the survivor wants to take up the proposed referrals or not. |
| Verify, investigate and act | Provide support services to survivors | GBV service providers support survivors until their services are no longer needed. |
|  | Review allegation and determine the likelihood that it is project-related | If a survivor wishes to proceed with accountability measures, the SEA/SH Coordinator, with the help of other GRC members/Contractors as appropriate, will determine the likelihood that it is related to the project. |
|  | Implement sanctions for perpetrators in accordance with employment contracts and local labor laws | If SEA/SH allegations are confirmed, the appropriate party—the employer of the perpetrator, which could be the implementing agency, the supervising engineer, or a contractor—implements disciplinary actions in line with labor law, employment contract and Code of Conduct (CoC). |
|  | Resolve and close cases | If the survivor has been referred to the relevant SEA/SH service providers, received adequate assistance, and no longer requires support; and if appropriate actions have been taken against the perpetrator or if the survivor does not wish to submit an official grievance with the employer, the case can be closed by the Coordinator. The SEA/SH GRM Coordinator records the resolution of the incident, the date it was resolved, and marks it as closed. The PMU and World Bank are notified that the case is closed |
| Monitor and evaluate | Monitor, track, and provide regular reports | The SEA/SH Coordinator is responsible for issuing regular (e .g ., monthly/quarterly) reports to the PMU that can only contain data such as the total number of allegations, the number of alleged perpetrators who have a relationship to the project, the type of incident, the age and sex of survivors and the referral status. |
| Provide feedback | Respond to survivors | The SEA/SH Coordinator needs to provide ongoing feedback to the survivor throughout the process but especially: (1) when the grievance is received; (2) when the case is reported to PMU and WB; (3) when the investigation commences or when a determination is made that there is an insufficient basis to proceed; and (4) when an investigation concludes or when any outcomes are achieved or disciplinary action taken. When an investigation is concluded, the survivor must be informed first to assess his or her safety before the investigation’s conclusions are communicated to the perpetrator, particularly when sanctions will be taken. |

SEA/SH GRM – Points to Keep in mind

Following issues to be kept in mind while dealing in SEA/SH issues:

| ISSUES | DO’S | DON’T’S |
| --- | --- | --- |
| Confidentiality | To record SEA/SH allegations, use an encrypted electronic storage system with proper tracing or a separate logbook that will be kept safe and that guarantees the confidentiality of data Create a sound coding system to anonymize case files by, for example, assigning tracking numbers Establish a formal protocol with clear rules and procedures for interagency information-sharing of case-level data to ensure confidentiality | Register the case in a logbook used for other types of grievances Leave information/logbook easily accessible Underestimate the importance of keeping survivor files confidential, even within an organization or with colleagues Discuss survivor files with anyone unrelated to the case or include identifiable data or information about individual cases in interagency reports Include any elements in shared data that could help identify survivors, including names, characteristics, or specific locations |
| Consent | Document a survivor’s consent to receive referrals and for the sharing of any data Depict the benefits and risks of every referral option and clearly relate to the survivor what cannot be provided as well as any limitations on services Adopt a context-sensitive approach for reporting to the police and making referrals to the legal justice system. Security actors and the rule of law may not be reliable in some context; and some survivors may prefer to turn to traditional, informal justice mechanisms | Force a survivor to file a formal complaint with the grievance mechanism (some survivors may only wish to access services) Act on the allegation in any way without the consent of the survivor Coerce a survivor to make a particular decision or create false expectations of available services and support Assume that reporting to the police, accessing legal support or dealing with the justice system is necessarily desirable. (In many cases, survivors do not want to pursue security- or police-related actions, and their decisions must be respected .) |

Proactive Approach to Address SEA/SH Issues

The Project should bear in mind that SEA/SH issues are extremely sensitive and single case can jeopardize the project, both operationally and reputationally. Therefore, it is of utmost importance that all project staffs, workers, personnel know the implication of SEA/SH and act accordingly. Following measures should be in place to deter any incidence of SEA/SH in the project (list is not exhaustive):

Ensure Contractor’s bidding document and agreement, both reflect issues of SEA/SH, the consequences of SEA/SH by their workers including project fund withdrawal, investigation by law enforcing agencies and risk to their reputation. The agreement must have a SEA/SH non-compliance clause.

Contractor must be responsible for activities of their workers and they should train and monitor their behaviors. All the project workers are bound to sign a Code of Conduct (CoC), illustrating SEA/SH issues, among others.

Workers and labors must be provided with adequate leave and scope of entertainment in the camp.

Training on SEA/SH on a quarterly basis.

Communities must be provided information on lodging SEA/SH complaints through FGD, postering, miking etc.

Signposts and banners in the project site regarding adherence to SEA/SH protocol.

Indication of SEA/SH must be handled with zero tolerance.

Interacting with the communities by project staffs and workers should be discouraged and kept to a certain limit and continuously monitored.

Intent to hide cases of SEA/SH by project staffs and worker to save reputation must be curbed.

# Training and Capacity Building of GRM Staffs

General. Anyone deployed or assigned in the GRM management role should be given prior training. The following paragraphs illustrate the training modalities.

Orientation. 	GRM assignment should be viewed as a customer service issue rather than a complaint issue. There will be a marked difference in the way staffs approach their work between those who see the GRM as a “complaints department” and those who see it as a “customer service” department.

- GRM as “Complaints Department.”  If staffs working in a GRM see their function as addressing complaints, then they will likely assume that every interaction will be unpleasant and be on the defensive in conversation with an affected person (AP). This orientation emphasizes the negative aspects of the process affecting performance, morale, and expectations all around.

- GRM as “Customer Service Department.”  By contrast, if GRM staffs view a GRM as an integral part of effective project management, through which the PMU seeks feedback from “customers” or “beneficiaries,” then they will be far more likely to approach their work positively. Also, if people are asked not only what they do not like about the project, but also what they do like, then their responses are more likely to be moderate about any negative impacts in most cases.

Knowledge. Three types of knowledge are especially important to staffs operating within a GRM:

- Knowing the context—understanding of background issues, politics, sensitivities, precedents, local history, language, and culture of the APs;

- Knowing the facts—having detailed information related to the project and to any cases associated with it; this includes specifics on the risks, impacts and benefits of the project, who is affected, and knowledge of relevant criteria (e.g., laws, costs, valuations); and

- Knowing the system—experience in dealing with people, organizations, procedures, and cases; staffs should be familiar with the process, purpose and objectives of GRMs, the guiding principles governing treatment of APs, relevant legislation, one’s own role in the process, and the limits of GRMs.

Staff Skills.	The following is both a list of the skillsets essential to dealing effectively with APs and recommendations for the development of training tools designed to facilitate those practical training opportunities:

- Negotiation, Influence, and Conflict Management. Every interaction with an AP who has a grievance is a negotiation—a conversation in which parties are attempting to influence each other. Skills in the art and science of negotiation, influence, and conflict management are essential in dealing with grievances effectively, in particular the art of negotiating substantive or technical issues in ways that (a) allow decisions to be based on appropriate, legitimate criteria; (b) preserve manageable relationships even while there might be disagreement over issues; and (c) explore options and alternatives to reach mutual agreements where possible.

- Options Analysis. Understanding how people see (from their own perspective) the choices/options they are being given is essential to understanding why they might behave in certain ways. Staffs need to understand how choices look to others, for the purpose of influencing them more effectively.

- Brainstorming and Joint Problem Solving. While some issues affecting APs are often emotional, there are also technical, non-emotional matters that must be dealt with in GRMs. These include determining responsibility, assessing the validity of claims, determining how policies apply in a case, and valuation. To turn conversations about grievances into productive problem solving, it is useful to have the capacity to engage APs in brainstorming about constructive ideas and to design and manage processes for joint problem solving (engaging both project staff and APs—and possibly other resource people).

- Communication. Several specific communication skillsets that will help most GRM staff deal with grievances are the following:

  - Inquiry and Active Listening. The most basic, and essential, communication skills for anyone dealing with grievances are the skills of inquiry (asking good questions) and active listening (listening to people with the intent of understanding what they mean, as well as hearing what they say). Most APs want to be listened to, in addition to having their substantive complaint addressed.

  - Understanding Perceptions. It is also essential for project staff to be aware that different people, for very logical reasons, will often have very different perceptions of an event, a policy, or other people. It is often vital to turn the type of communication being used into something more constructive, particularly dialogue—a conversation where people are making the effort to understand each other, even if they might strongly disagree.

  - Difficult Conversations.  It will be helpful for any staff working within a GRM to realize that every difficult conversation is actually three conversations. First, there is the “factual” conversation: the technical details of what happened, is happening, or will happen. Second, there is also an “emotional” conversation, which is the conversation about how people feel about what is happening. And third, there is the “identity” conversation, which is the impact that the conversation (or dispute) has on their sense of “who they are” and how they are being treated. It is possible to build the capacity of project staffs and others  in a set of skills that can actually help them to have difficult conversations in ways that are more productive (and less destructive).

  - Feedback. Grievances are fundamentally a form of feedback given about a project by those affected by it, and they should be treated as such. Staffs need to know how to give and receive (and to help others give) feedback effectively and in ways that maximize how helpful that feedback can be.

- Facilitation. Many project-related grievances will be common to many APs and will involve multiple stakeholders. It will be essential for GRM staffs to have facilitation skills so that they can better manage the communication, the collection of information, any option generation, the exploration of alternatives, and/or the making of any commitments consistently and effectively in group settings.

- Risk Management. While staffs are trying to address APs’ concerns, they must also be aware of the risks inherent in doing so. These risks include legal liabilities, reputational damage to the organizations or projects they represent, physical harm to people and/or property, raising expectations, undermining colleagues or previous decisions, and setting precedents that might be used later (i.e., avoiding inconsistency, which will undermine credibility).

- Credibility and Relationship. The staffs dealing with APs will need to have a minimum of credibility with them, meaning that the APs have some confidence that the staffs will treat them with dignity and respect (as customers) and be able to deal professionally with their case (even if the APs do not like the outcome), and that the APs can believe what they are told by that staff, and that it is authoritative.

Tentative Training Plan

| Module | Attendee | Frequency | Responsibility |
| --- | --- | --- | --- |
| Project Details (Objective Scope, risks, impacts, Project Affected People) | Everyone associated with GRM | Before beginning of implementation. Thereafter yearly once | Project Director |
| GRM Process including SEA/SH GRM | Everyone associated with GRM, including SEA/SH issues | Before deployment of GRM and thereafter once half yearly | Social Development Specialist (SDS) |
| Negotiation, Active Listening and Conflict Management | Everyone associated with GRM | Before deployment of GRM and thereafter once half yearly | Communication Specialist/ SDS |
| Problem Solving Skills with exercise/ case study | Field Office GRM Staffs | Before deployment of GRM and thereafter once half yearly | Communication Specialist/ SDS |
| Exercise - Testing GRM Uptake Channels and GRM Solution | Everyone associated with GRM | Before deployment of GRM | Social Development Specialist (SDS) |

# GRM Public Communication Channel

The GRM will be widely publicized among stakeholder groups such as the AP, government agencies, NGOs and civil society organizations. Lack of knowledge about GRMs results in people not approaching and using them, and they eventually lose the relevance and the validity of the purpose for which they were created. People will also be informed about their options, depending on the types of complaints, but should not be encouraged to submit false claims. Criteria for eligibility need to be communicated. An effective awareness campaign launched to give publicity to the roles and functions of the GRMs should include the following components:

Scope of the project, planned phases, etc

Purposes for which the different GRMs can be accessed, e.g., construction-related grievances, land acquisition and compensation-related grievances, SEA/SH etc

Types of grievances not acceptable to the GRM

People who can access the GRM

How complaints can be reported to those GRM and to whom, e.g., phone and SMS, postal and email addresses, and websites of the GRM as well as information that should be included in a complaint

Procedures and time frames for initiating and concluding the grievance redress process

Boundaries and limits of GRM in handling grievances; and

Roles of different agencies such as project implementors and funding agencies.

A variety of methods will be adopted for communicating information to the relevant stakeholders:

Display of posters in public places such as in government offices, project offices, community centers, etc.

Distribution of brochures

Local/village-level government officers/ representatives to hold small-group discussions

NGOs and community-based organizations; and

Village heads, religious heads, Imams etc

Print and electronic media, including radio.

# Budget and Human Resources

The following table depicts staff and other human resource requirement at various levels:

| Location | Staff | Number | Note |
| --- | --- | --- | --- |
| Tier 3 - Central PMU GRC | GRC Head/Chairman | 1 |  |
|  | SDS - GRC Secretary | 1 |  |
|  | Member 1/ SEA/SH Coordinator | 1 |  |
|  | Member 2 | 1 |  |
|  | Member 3 | 1 |  |
|  | GRC Database Officer | 1 |  |
|  | Telephone/SMS Receiver | 2 |  |
| Tier 2 – District GRC | District GRC Head | 5 | For 5 Districts |
|  | Secretary | 5 |  |
|  | Member 1 | 5 |  |
|  | Member 2 | 5 |  |
| Tier 1 – Local | Local GRC Head | 30 | For 30 Unions |
|  | Secretary | 30 |  |
|  | Member 1 | 30 |  |
|  | Member 2/ GRC Uptake Staff | 30 |  |
| TOTAL |  | 148 |  |

Note: Females will make at least 30% of any Committee members. List of all GRC members at all Tiers will be kept with PMU.

The following is a summary of GRC Budget required for GRM implementation per year:

- Required GRM implementation Budget for MoEFCC/DoE

| Sl. | Activities | Quantity | Unit Cost (BDT) | Frequency | Total Cost (BDT)/Yr | Shared with SEP Budget |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Staff/ Consultant Salaries (GRC Database Officer + Telephone/SMS Receiver) Other GRC staffs will be paid from the Project. | 3 | 20000+ 15000+ 15000 | Yearly | 600,000 | No |
| 2 | Training on GRC issues | Twice a year | 100,000 | Yearly | 200,000 | No |
| 3 | Stakeholder/Community/Sensitization meeting on GRM | Lump Sum |  | Yearly | 400,000 | No |
| 4 | Meeting on GRC/ GRC Committee (for all level) | 72 meeting/ yr | 5,000 | Yearly | 360,000 | No |
| 5 | Stationery, Printing, Computer, Phone/SMS Charge etc | Lump Sum |  | Yearly | 300,000 | Yes |
| 6 | Travel Expenses/ Investigation etc | Lump sum |  | Yearly | 400,000 | No |
| 7 | Communication Materials (Poster, Brochure) | Lump Sum |  | One time | 300,000 | Yes |
| 8 | GRM Guidebook/ Manual | Lump Sum |  | One Time | 250,000 | Yes |
| 9 | GRM Box | 100 | 2000 | One time | 200,000 | Yes |
| 10 | GRM/GRC expenses (Uptake, Solution providing etc) | Lump Sum |  | Yearly | 200,000 | No |
| 11 | GRM MIS Database | Lump sum |  | Yearly | 150,000 | Yes |
| 12 | Honorarium for committees | Lump sum |  | Yearly | 200,000 | Yes |
|  | Total (Summation of 1 to 12) |  |  |  | 3,560,000 |  |
| 13 | Contingency (10%) of yearly (Summation of 1 to 12) (Rounded) |  |  |  | 350,000 |  |
| Total (Rounded) (Less those shared with SEP) |  |  |  |  | 2,510,000 |  |

- Required GRM implementation Budget for Bangladesh Bank

| Sl. | Activities | Quantity | Unit Cost (BDT) | Frequency | Total Cost (BDT)/Yr | Shared with SEP Budget |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Staff/ Consultant Salaries (GRC Database Officer + Telephone/SMS Receiver) Other GRC staffs will be paid from the Project. | 2 | 20000+ 15000 | Yearly | 420,000 | No |
| 2 | Training on GRC issues | Twice a year | 75,000 | Yearly | 150,000 | No |
| 3 | Stakeholder/Community/Sensitization meeting on GRM | Lump Sum |  | Yearly | 150,000 | No |
| 4 | Meeting on GRC/ GRC Committee (for all level) | 60 meeting/yr | 4,000 | Yearly | 240,000 | No |
| 5 | Stationery, Printing, Computer, Phone/SMS Charge etc | Lump Sum |  | Yearly | 150,000 | Yes |
| 6 | Travel Expenses/ Investigation etc | Lump sum |  | Yearly | 150,000 | No |
| 7 | Communication Materials (Poster, Brochure) | Lump Sum |  | One time | 120,000 | Yes |
| 8 | GRM Guidebook/ Manual | Lump Sum |  | One Time | 150,000 | Yes |
| 9 | GRM Box | 80 | 2000 | One time | 160,000 | Yes |
| 10 | GRM/GRC expenses (Uptake, Solution providing etc) | Lump Sum |  | Yearly | 180,000 | No |
| 11 | GRM MIS Database | Lump sum |  | Yearly | 100,000 | Yes |
| 12 | Honorarium for committees | Lump sum |  | Yearly | 200,000 | Yes |
|  | Total (Summation of 1 to 12) |  |  |  | 2,170,000 |  |
| 13 | Contingency (10%) of yearly (Summation of 1 to 12) (Rounded) |  |  |  | 220,000 |  |
| Total (Rounded) (Less those shared with SEP) |  |  |  |  | 1,510,000 |  |

- Required GRM implementation Budget for BRTA

| Sl. | Activities | Quantity | Unit Cost (BDT) | Frequency | Total Cost (BDT)/Yr | Shared with SEP Budget |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Staff/ Consultant Salaries (GRC Database Officer + Telephone/SMS Receiver) Other GRC staffs will be paid from the Project. | 2 | 15000+ 15000 | Yearly | 360,000 | No |
| 2 | Training on GRC issues | Twice a year | 75,000 | Yearly | 150,000 | No |
| 3 | Stakeholder/Community/Sensitization meeting on GRM | Lump Sum |  | Yearly | 150,000 | No |
| 4 | Meeting on GRC/ GRC Committee (for all level) | 60 meeting/yr | 4,000 | Yearly | 240,000 | No |
| 5 | Stationery, Printing, Computer, Phone/SMS Charge etc | Lump Sum |  | Yearly | 120,000 | Yes |
| 6 | Travel Expenses/ Investigation etc | Lump sum |  | Yearly | 150,000 | No |
| 7 | Communication Materials (Poster, Brochure) | Lump Sum |  | One time | 100,000 | Yes |
| 8 | GRM Guidebook/ Manual | Lump Sum |  | One Time | 100,000 | Yes |
| 9 | GRM Box | 80 | 2000 | One time | 160,000 | Yes |
| 10 | GRM/GRC expenses (Uptake, Solution providing etc) | Lump Sum |  | Yearly | 120,000 | No |
| 11 | GRM MIS Database | Lump sum |  | Yearly | 100,000 | Yes |
| 12 | Honorarium for committees | Lump sum |  | Yearly | 150,000 | Yes |
|  | Total (Summation of 1 to 12) |  |  |  | 1,900,000 |  |
| 13 | Contingency (10%) of yearly (Summation of 1 to 12) (Rounded) |  |  |  | 200,000 |  |
| Total (Rounded) (Less those shared with SEP) |  |  |  |  | 1,370,000 |  |

- Required GRM implementation Budget for BHTPA

| Sl. | Activities | Quantity | Unit Cost (BDT) | Frequency | Total Cost (BDT)/Yr | Shared with SEP Budget |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Staff/ Consultant Salaries (GRC Database Officer + Telephone/SMS Receiver) Other GRC staffs will be paid from the Project. | 2 | 15000+ 15000 | Yearly | 360,000 | No |
| 2 | Training on GRC issues | Twice a year | 75,000 | Yearly | 150,000 | No |
| 3 | Stakeholder/Community/Sensitization meeting on GRM | Lump Sum |  | Yearly | 100,000 | No |
| 4 | Meeting on GRC/ GRC Committee (for all level) | 60 meeting/yr | 4,000 | Yearly | 240,000 | No |
| 5 | Stationery, Printing, Computer, Phone/SMS Charge etc | Lump Sum |  | Yearly | 120,000 | Yes |
| 6 | Travel Expenses/ Investigation etc | Lump sum |  | Yearly | 100,000 | No |
| 7 | Communication Materials (Poster, Brochure) | Lump Sum |  | One time | 100,000 | Yes |
| 8 | GRM Guidebook/ Manual | Lump Sum |  | One Time | 80,000 | Yes |
| 9 | GRM Box | 80 | 2000 | One time | 160,000 | Yes |
| 10 | GRM/GRC expenses (Uptake, Solution providing etc) | Lump Sum |  | Yearly | 120,000 | No |
| 11 | GRM MIS Database | Lump sum |  | Yearly | 100,000 | Yes |
| 12 | Honorarium for committees | Lump sum |  | Yearly | 100,000 | Yes |
|  | Total (Summation of 1 to 12) |  |  |  | 1,730,000 |  |
| 13 | Contingency (10%) of yearly (Summation of 1 to 12) (Rounded) |  |  |  | 180,000 |  |
| Total (Rounded) (Less those shared with SEP) |  |  |  |  | 1,250,000 |  |

# Annexure

Annex A

## COMPLAINT FORM

Tracking Number:
ট্র্যাকিং নাম্বার:

Complainant Information (Person Reporting)
অভিযোগকারীর তথ্য:

- Name (Not required if anonymity sought):
নাম (প্রকাশে অনিচ্ছুক হলে প্রযোজ্য নয়):

- Address:
ঠিকানা:

- National ID (Not required if anonymity sought):
ন্যাশনাল আইডি নং (প্রকাশে অনিচ্ছুক হলে প্রযোজ্য নয়):

- Gender: 
লিঙ্গ:

- Telephone (Not required if anonymity sought):
টেলিফোন (প্রকাশে অনিচ্ছুক হলে প্রযোজ্য নয়):

- Email (Not required if anonymity sought):
ই-মেইল (প্রকাশে অনিচ্ছুক হলে প্রযোজ্য নয়):

- Type of complainant:
অভিযোগের ধরণ:

□	Affected Person/s (AP)
ক্ষতিগ্রস্ত ব্যাক্তি:

□	Intermediary (on behalf of the AP)
  মধ্যস্থতাকারী (ক্ষতিগ্রস্ত ব্যাক্তির পক্ষে):

□	Civil Society Organization/ NGOs
সুশীল সমাজ / এনজিও:

□	Service Organization (e.g., local government institution)
সেবা প্রদানকারী সংস্থা ( স্থানীয় সরকারি প্রতিষ্ঠান):

□	Others (specify)
অন্যান্য:

Complaint Details অভিযোগের বর্ণনাঃ

- Mode of Receiving Complaint:
অভিযোগ গ্রহনের মাধ্যম:

□		Letter চিঠি:

□		Phone call ফোন:

□		SMS এসএমএস:

□		Email ই-মেইল:

□		Verbal complaint (walk-in) মৌখিক অভিযোগ:

□		Suggestion box পরামর্শ বক্স:

□		Others (specify) অন্যান্য:

- Location of the problem specified in the complaint:

অভিযোগে উল্লেখিত সমস্যার স্থান:

Village/Union/Upazilla:

গ্রাম/ ইউনিয়ন/ উপজেলা:

District and Division:

জেলা ও বিভাগ:

- Type of Complaint অভিযোগের ধরণ:

□	Environmental (Noise, Pollution, Waste etc)
পরিবেশ বিষয়ক (বায়ু দূষণ, শব্দ দূষণ, পানি দূষণ, মাটি দূষণ, আবর্জনার অব্যবস্থাপনা,  ইত্যাদি)

□	Land Acquisition and Compensation
ভূমি অধিগ্রহণ ও ক্ষতিপূরণ বিষয়ক

□	Social (GBV, Security Forces, Community Health, Traffic, Labor Issues, Harassment)
সামাজিক বিষয়ক (লিঙ্গ ভিত্তিক সহিংসতা, নিরাপত্তাকর্মী জনিত সমস্যা, এলাকা ভিত্তিক স্বাস্থ্য সমস্যা, যানবাহনজনিত সমস্যা, শ্রম জড়িত বিষয়াদি, হয়রানি )

□	Construction/ Contractors
নির্মাণ সংক্রান্ত / ঠিকাদার সংক্রান্ত

□	Indigenous People/ Minority issues 
উপজাতি/ সংখ্যালঘু ব্যাক্তি বিষয়ক সমস্যা

□	Others (specify)
অন্যান্য

11.	Short Description of the Complaint
	অভিযোগের সংক্ষিপ্ত বর্ণনা

- Short description of the factors causing the problem 
অভিযোগের মূল কারণের সংক্ষিপ্ত বর্ণনা

- Person/agency likely responsible for causing the problem:  সমস্যা সৃষ্টিকারী ব্যক্তি/ সংস্থা:

□ Project implementing agency   প্রকল্প বাস্তবায়নকারী সংস্থা

□ Other Affected Parties অন্যান্য ক্ষতিগ্রস্ত ব্যক্তি/ সংস্থা

□ Service providing agencies সেবাদানকারী সংস্থা

□ Local political authority স্থানীয় রাজনৈতিক দল

□ Civil organization/NGO সুশীল সমাজ / এনজিও

□ Funding agencies দাতা সংস্থা

□ Contractor ঠিকাদার

□ Labors  শ্রমিক
□ Others (specify)  অন্যান্য

□ Unknown অজ্ঞাত

14.	Details of the staff/ focal point that received the complaint: অভিযোগ গ্রহণকারীর বর্ণনা:

Name: নাম:

Position: পদবী:

Office: অফিস:

Date and Time: তারিখ ও সময়:

Location where complaint received: অভিযোগ গ্রহণের স্থান:

- Action taken by receiving office/staff, including date and time:
অভিযোগ গ্রহণকারী অফিস/ কর্মচারী কর্তৃক গৃহীত পদক্ষেপ (তারিখ ও সময় সহ):

- Subsequent Action Taken:
পরবর্তী পদক্ষেপসমূহ:

| Date and Time তারিখ ও সময় | Action পদক্ষেপ | By Whom অভিযোগ গ্রহণকারীর |
| --- | --- | --- |

- Final Resolution (From the GRC Committee Meeting) সর্বশেষ সমাধান:

- Signature/Acknowledgement: স্বাক্ষর:

| Date and Time তারিখ ও সময় | Individual Appointment সাক্ষাত প্রদানকারী ব্যাক্তি | Name নাম | Mode of Communication অভিযোগের ধরন | Remarks, if any মন্তব্য | Signature স্বাক্ষর |
| --- | --- | --- | --- | --- | --- |
|  | Head of decision-making entity প্রধান সিদ্ধান্ত গ্রহণকারী |  |  |  |  |
|  | Responsible Staff দায়িত্বরত কর্মকর্তা |  |  |  |  |
|  | Complainant অভিযোগ |  |  |  |  |

Annex B

## GRC REVIEW MEETING MINUTES AND DECISION FORM

Date and Time of Meeting:

Tracking Number:

Venue of Meeting:

List of participants:

| Complainant Side | GRC Members | Any Other Party |  |
| --- | --- | --- | --- |

Summary of Grievance:

Key discussions:

Decisions Made/Recommendations by the Grievance Redress Committee:

Status of Grievance (tick where applicable):

| Solved |  | Unsolved |  |
| --- | --- | --- | --- |
| Referred to |  | Others |  |

Signature with Date

Meeting Chairperson:

Complainant:

Others:

Annex C

## M&E/ QUARTERLY COMPILATION REPORT FORM

Date of Submission:

Compiled by:

Period Covering:

| Sl | Tracking Number | Date of Complaint Receipt | Place of receiving complaint | Location of complaint/concern | Name & Address of complainant | Type of Complaint (Environment, Construction, Land, GBV, etc) | Date of 1st Meeting | Date of 2nd Meeting | Progress (on going, solved, referred etc) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Annex D

## GRM RESOLUTION SATISFACTION FORM

Complainant Name. অভিযোগকারীর নাম

NID. এনআইডি

Phone.ফোন

Address. ঠিকানা

Date of Complaint Lodge. অভিযোগ দাখিলের তারিখ

Tracking Number.ট্র্যাকিং নম্বর

I had put up a complain at the XXXX Project GRC Office located at (location) …… . My complain was (summary description of complaint) …………………………………..

আমি, _________________________________ জেলার, _______________________________ প্রোজেক্ট অফিসে একটি অভিযোগ করেছিলাম। আমার অভিযোগটি ছিল নিম্নরূপঃ

…

…

…

…

On …………….. (date of resolution receipt) my complain was given a resolution by GRC. As per the resolution (description of resolution) ……

_________________________ তারিখে আমার অভিযোগটির নিস্পত্তি করা হয়।  নিষ্পত্তিটি নিম্নরূপ:

…………

………..

………..

………..

I am satisfied with the given resolution.
প্রদত্ত নিস্পত্তিতে আমি সন্তুষ্ট।

_______________________________                                                            ______________________________

Signature and date of the Complainant				Signature and date of the GRC Head
অভিযোগকারীর স্বাক্ষর ও তারিখ 					অভিযোগ নিরসন কমিটি প্রধানের স্বাক্ষর ও তারিখ

Annex E

## SEA/SH Consent Form

CONFIDENTIAL

Should be read to the survivor or guardian and explained that she / he can choose any or none of the options listed.

I, ___________________________________________________, give my permission for (Name of Organization) to share information about the incident I have reported to them as explained below:

I understand that in giving my authorization below, I am giving (Name of Organization) permission to share the specific case information from my incident report with the service provider(s), PMU and the World Bank. I have indicated, so that I can receive help with safety, health, psychosocial, and/or legal needs.

I understand that shared information will be treated with confidentiality and respect and shared only as needed to provide the assistance I request. I understand that releasing this information means that a person from the agency or service ticked below may come to talk to me.  At any point, I have the right to change my mind about sharing information with the designated agency / focal point listed below.

I would like information released to the following:

Yes      No

(Tick all that apply, and specify name, facility and agency/organization as applicable)

Security Services (specify):

Psychosocial Services (specify):

Health/Medical Services (specify):

Safe House / Shelter (specify):

Legal Assistance Services (specify):

Livelihoods Services (specify):

Other (specify type of service, name, and agency):

I have been informed and understand that some non-identifiable information may also be shared for reporting. Any information shared will not be specific to me or the incident. There will be no way for someone to identify me based on the information that is shared. I understand that shared information will be treated with confidentiality and respect.

Survivor’s/ Guardians Signature/ Thumb Print 					Date:

Case Code:

Coded Data (The data below must be coded to hide Survivor’s identity)

Survivor’s Name:

Guardian’s Name:

Contact Number:

Address:

Annex F

## POTENTIAL GRIEVANCES FOR THE PROJECT

| Scope | Potential Issues | Suggested Action | Remark/Note |
| --- | --- | --- | --- |
| Land Acquisition | Timely notice or information about acquisition given |  |  |
|  | Land and asset valuation not done properly |  |  |
|  | Land acquired forcibly |  |  |
|  | Compensation not paid |  |  |
|  | Compensation paid less then valuation |  |  |
|  | Delay in compensation payment |  |  |
|  | Land and asset rendered unusable due to project activities |  |  |
|  | Squatters evicted without compensation |  |  |
| Construction | Construction material kept in road/ own plot without permission |  |  |
|  | Sound pollution due to construction |  |  |
|  | Water pollution due to construction activities/ labor camp |  |  |
|  | Air pollution due to construction activities |  |  |
|  | Private land occupied by Contractor |  |  |
|  | Traffic problem due to construction vehicle |  |  |
| Labor | Harassment by Contractor personnel |  |  |
|  | Public nuisance by labors |  |  |
|  | Issue with security personnel employed by Contractors |  |  |
|  | Gender-based Violence by labors |  |  |
|  | Any other social issues by Contractor personnel |  |  |
| Indigenous People | No consultation done with IP. No/limited information shared |  |  |
|  | Consultation not done as per culturally appropriate form |  |  |
|  | Impact on IP Land |  |  |
|  | Impact on IP cultural heritage, belief, social hierarchy |  |  |
| Biodiversity/ Habitat | Impact on biodiversity |  |  |
|  | Impact on habitat |  |  |
|  | Effect on forest, corps and trees |  |  |
| Environmental Impact | Use of pesticides |  |  |
|  | Waste generation (medical and hazardous wastes) |  |  |
|  | GHG emission |  |  |
|  | Resources wastage (Energy, water, raw material) |  |  |
| Social Impact | Not consulting disadvantaged and vulnerable |  |  |
|  | No special arrangement for consulting women and children |  |  |
|  | Lack of GRM/ GRM process ineffective |  |  |
|  | Not closing the feedback loop for consultation |  |  |
| Implementation | Project officials demand money for service/ project benefit |  |  |
|  | Project officials’ rude behavior |  |  |
|  | Elite capture of project benefits |  |  |
|  | Corruption or illegal activities by project personnel |  |  |
|  | Project activities not being implemented as planned/ low quality of service/ product/ activities |  |  |

Annex G

## GRIEVANCE REDRESS MECHANISM CHECKLIST

(Check before deployment of GRM)

- System issues

| 1. Does the project invite feedback/grievances? | Yes | No |
| --- | --- | --- |
| 2. Does the organization have a policy on grievance redress? | Yes | No |
| a. Is the policy available to all staff, beneficiaries, and potential users? | Yes | No |
| b. Is the policy written in the local language(s)? | Yes | No |
| 3. Does the grievance mechanism have the following features? |  |  |
| a. A clearly understood procedure for people to provide feedback and/or submit grievances. | Yes | No |
| b. A statement of who is responsible for dealing with feedback/ grievances. | Yes | No |
| c. Procedures for resolving or mediating and investigating grievances depending on their seriousness and complexity. | Yes | No |
| d. A system for keeping complainants informed of status updates. | Yes | No |
| e. A system for recording feedback/grievances and outcomes. | Yes | No |
| f. Procedures for protecting confidentiality of complainants | Yes | No |

- Staff management

| 1. Is there a grievance manual for staff? | Yes | No |
| --- | --- | --- |
| 2. Do the grievance policy and/or procedures provide guidance on: |  |  |
| a. What is a grievance/feedback? | Yes | No |
| b. What information to collect from complainants? | Yes | No |
| c. What remedies can or should be used to resolve grievances? | Yes | No |
| 3. Are the grievance policy and procedures communicated to all staff? | Yes | No |
| 4. Are adequate resources allocated for the grievance mechanism to function effectively? | Yes | No |
| 5. Does the organization provide training on grievance management to staff? | Yes | No |

- Communication to grievance mechanism users

| 1. Are users told how to submit grievances/feedback? | Yes | No |
| --- | --- | --- |
| a. Is an information brochure on the grievance mechanism available to users? | Yes | No |
| b. Are feedback/grievance forms available to users? | Yes | No |
| c. Are grievance forms or signs displayed prominently and readily accessible? | Yes | No |
| d. Are contact details of staff receiving feedback/grievance published and displayed in public areas? | Yes | No |
| e. Is information on grievance management available in local languages? | Yes | No |
| 2. Are users able to submit grievances/feedback: |  |  |
| a. In writing | Yes | No |
| b. By email | Yes | No |
| c. By SMS | Yes | No |
| d. By telephone | Yes | No |
| e. In person | Yes | No |
| 3. Are users provided with assistance to submit feedback/grievances where needed? | Yes | No |
| 4. Can the grievance mechanism be accessed free of charge? | Yes | No |
| 5. Are users promised confidentiality? | Yes | No |
| 6. Are users informed about the appeals process? | Yes | No |

- Feedback/grievance recording

| 1. Are all feedback/grievances recorded? | Yes | No |
| --- | --- | --- |
| a. Are grievances/feedback logged and documented? | Yes | No |
| b. Are inquiries/suggestions and recommendations recorded? | Yes | No |
| c. Are the outcomes and responses to all grievances/feedback recorded? | Yes | No |

- Business standards

| 1. Are there business standards in place for the process and timing with which grievances/feedback are dealt with? | Yes | No |
| --- | --- | --- |
| a. Is receipt acknowledged within a stipulated time frame? | Yes | No |
| b. Are the grievances supposed to be resolved within a stipulated time frame? | Yes | No |
| 2. Is there a quality control system in place to: |  |  |
| a. Check if all grievances have been dealt with or acted upon. | Yes | No |
| b. Check if all aspects of a grievance have been addressed. | Yes | No |
| c. Check if all necessary follow-up action has been taken. | Yes | No |

- Analysis and feedback

| 1. Are regular internal reports on grievances/feedback produced for senior management? | Yes | No |
| --- | --- | --- |
| 2. Grievances/feedback reports include data on: |  |  |
| Numbers of grievances/feedback received. | Yes | No |
| Compliance with business standards. | Yes | No |
| Issues raised in grievances/feedback. | Yes | No |
| Trends in grievances/feedback over time. | Yes | No |
| The causes of grievances/feedback. | Yes | No |
| Whether remedial action was warranted. | Yes | No |
| What redress was actually provided? | Yes | No |
| Recommendations/strategies to prevent or limit future recurrences. | Yes | No |
| 3. Are reports about grievances/feedback made public, periodically? | Yes | No |

Annex H

## SEA/SH SERVICE PROVIDE LIST FOR THE PROJECT

(Update this list before GRM Deployment. Coordinate with the service providers before listing them here)

| SER | NAME OF ORGANISATION | SERVICE |  |  |  |  |  | CONTACT PERSON AND DESIGNATION | EMAIL, PHONE, ADDRESS | NOTE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Health | Psychosocial | Legal | Shelter | Training/Job | Others |  |  |  |

The Mobile phone number provided for SMS intake might be changed if there is transfer of the official.