Adaptation of 4IR compatible maritime training Scheme in Bangladesh

Roadmap for Piloting

| Sl No. | Action Items | Tentative Timeline | Stakeholder | Status |
| --- | --- | --- | --- | --- |
| 1 | Concept Note, Proposal & Other Required Documentation | Feb, 2022 | MOS, DOS, TSP | Done |
| 2 | Formation of Team | June, 2022 | MOS, DOS | Done |
| 3 | Approval from the Authority |  | MOS |  |
| 4 | Competency Standard and Curricular Development | Nov, 2022 | DOS, TSP |  |
| 5 | Training Materials Development | Dec, 2022 | DOS |  |
| 6 | Software and Hardware Purchase | March, 2023 | DOS |  |
| 7 | Training and Industry Linkage | June, 2023 | Manning Agency, Shipping Company, Shipyards, Dockyards |  |