## Environmental Part
Package_WD_AF_29 Summary (Environmental Part) Camp_10, HHT-100
General Information | [5 empty] | B1 Environmental Features | [6 empty] | B2 Pre Construction Phase |  |  |  |  | B3 Construction Phase | [7 empty] | B4 Operation Phase | [9 empty] | Section_D Impact Summary (Sub-project interventions) |  |  | Section_D Impact Summary (Pre-Construction Phase) |  |  | Section_D Impact Summary (Construction Phase) | [6 empty] | Section_D Impact Summary (Operational Phase) | [5 empty] | Potential Natural Hazards
Sl.No | Package ID | Camp | Block | Lat | Long | Landslide potential | Wildlife Issue | Forest Issue | Existing drainage channel (manmade / natural) Issue | Livelihood Issues | Access Road | Approx. Area Required (sqm) | Stagnant Water Risk | Existing drainage channel (Rivers, cannels) Issue | Aquatic ecosystems Issue | Storage of construction materials issue | Traffic movement Issue | Construction Waste (excavated soil etc.) | Stagnant Water Issue | Storage of Materials | Existing drainage channel (Rivers, cannels) Issue | Aquatic ecosystems Issue | Land Erosion Issue | Traffic movement Issue | Employment (positive impact) | Health Hazards Issue (Fecal Sludge & Liquid waste) | Anticipated impacts on Ground and Surface water | Destruction soils Issue | Odor, water & soil quality impacts Issue | Stagnant Water Risk | Improvement of quality of livelihood | Existing drainage channel (Rivers, cannels) Issue | Aquatic ecosystems Issue | Land Erosion Issue | Traffic movement Issue | Air Quality Impact | Soil Impact | Hydrology (SW & GW) Impact | Impact on Existing drainage | Storage of construction materials Impact | Transportation Impact | Construction Waste (excavated soil etc.) | Stagnant Water Issue | Storage of Materials Impact | Impact on Drain & Aquatic Environment | Erosion of land Impact | Noise Pollution Impact | Air Pollution Impact | Health & Safety Hazard | Destruction of Soil Impact | Odor & waste disposal Impact | Impact on existing drainage & Aquatic Environment | Noise Pollution Impact | Air Pollution Impact | Cyclone | Fire | Flash Flooding | Land sliding
1 | EMCRP-WD_AF_29 | Camp_10 | A | 21.191 | 92.154 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
2 |  |  | A | 21.1912 | 92.1541 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
3 |  |  | A | 21.1913 | 92.1543 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
4 |  |  | E | 21.1868 | 92.154 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
5 |  |  | E | 21.1866 | 92.1535 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
6 |  |  | E | 21.1866 | 92.1532 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
7 |  |  | E | 21.1864 | 92.153 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
8 |  |  | E | 21.1861 | 92.1534 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
9 |  |  | E | 21.1865 | 92.1523 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
10 |  |  | E | 21.1873 | 92.1527 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
11 |  |  | E | 21.1872 | 92.1529 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
12 |  |  | C | 21.1905 | 92.1552 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
13 |  |  | C | 21.1907 | 92.1548 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
14 |  |  | C | 21.1904 | 92.154 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
15 |  |  | C | 21.1904 | 92.1539 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
16 |  |  | C | 21.1904 | 92.1537 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
17 |  |  | B | 21.1943 | 92.1535 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
18 |  |  | B | 21.1946 | 92.1535 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
19 |  |  | B | 21.1942 | 92.1542 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
20 |  |  | B | 21.1944 | 92.1544 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
21 |  |  | B | 21.1937 | 92.154 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
22 |  |  | B | 21.1935 | 92.1542 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
23 |  |  | B | 21.1934 | 92.1535 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
24 |  |  | B | 21.1931 | 92.1545 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
25 |  |  | B | 21.1925 | 92.155 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
26 |  |  | B | 21.1928 | 92.1549 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
27 |  |  | B | 21.1917 | 92.1545 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
28 |  |  | B | 21.1916 | 92.155 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
29 |  |  | B | 21.1922 | 92.155 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
30 |  |  | A | 21.1921 | 92.1516 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
31 |  |  | A | 21.192 | 92.1515 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
32 |  |  | A | 21.1918 | 92.1518 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
33 |  |  | A | 21.1921 | 92.1518 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
34 |  |  | A | 21.1914 | 92.1518 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
35 |  |  | A | 21.1914 | 92.1517 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
36 |  |  | A | 21.1911 | 92.1518 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
37 |  |  | A | 21.1909 | 92.152 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
38 |  |  | A | 21.1914 | 92.1524 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
39 |  |  | A | 21.1917 | 92.1524 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
40 |  |  | A | 21.1939 | 92.1525 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
41 |  |  | A | 21.1932 | 92.153 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
42 |  |  | A | 21.1935 | 92.1522 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
43 |  |  | A | 21.1931 | 92.1525 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
44 |  |  | A | 21.193 | 92.152 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
45 |  |  | A | 21.1928 | 92.1519 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
46 |  |  | A | 21.1923 | 92.1529 | Low | No | No | Yes | Yes | Yes | 10 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
47 |  |  | A | 21.1928 | 92.1527 | Low | No | No | Yes | Yes | Yes | 11 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
48 |  |  | A | 21.1927 | 92.1538 | Low | No | No | Yes | Yes | Yes | 12 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
49 |  |  | A | 21.1922 | 92.1532 | Low | No | No | Yes | Yes | Yes | 13 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
50 |  |  | A | 21.1911 | 92.1528 | Low | No | No | Yes | Yes | Yes | 14 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
51 |  |  | A | 21.191 | 92.1524 | Low | No | No | Yes | Yes | Yes | 15 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
52 |  |  | C | 21.1905 | 92.1524 | Low | No | No | Yes | Yes | Yes | 16 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
53 |  |  | C | 21.1904 | 92.1526 | Low | No | No | Yes | Yes | Yes | 17 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
54 |  |  | C | 21.1902 | 92.1524 | Low | No | No | Yes | Yes | Yes | 18 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
55 |  |  | C | 21.1901 | 92.1525 | Low | No | No | Yes | Yes | Yes | 19 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
56 |  |  | C | 21.1892 | 92.1521 | Low | No | No | Yes | Yes | Yes | 20 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
57 |  |  | C | 21.1889 | 92.152 | Low | No | No | Yes | Yes | Yes | 21 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
58 |  |  | C | 21.1884 | 92.1522 | Low | No | No | Yes | Yes | Yes | 22 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
59 |  |  | C | 21.1883 | 92.1524 | Low | No | No | Yes | Yes | Yes | 23 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
60 |  |  | C | 21.1885 | 92.1524 | Low | No | No | Yes | Yes | Yes | 24 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
61 |  |  | C | 21.188 | 92.1524 | Low | No | No | Yes | Yes | Yes | 25 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
62 |  |  | C | 21.188 | 92.1531 | Low | No | No | Yes | Yes | Yes | 26 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
63 |  |  | C | 21.1879 | 92.1532 | Low | No | No | Yes | Yes | Yes | 27 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
64 |  |  | C | 21.1885 | 92.1532 | Low | No | No | Yes | Yes | Yes | 28 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
65 |  |  | C | 21.1892 | 92.1528 | Low | No | No | Yes | Yes | Yes | 29 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
66 |  |  | C | 21.1878 | 92.1534 | Low | No | No | Yes | Yes | Yes | 30 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
67 |  |  | C | 21.1896 | 92.1537 | Low | No | No | Yes | Yes | Yes | 31 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
68 |  |  | C | 21.1897 | 92.1533 | Low | No | No | Yes | Yes | Yes | 32 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
69 |  |  | C | 21.1892 | 92.154 | Low | No | No | Yes | Yes | Yes | 33 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
70 |  |  | C | 21.189 | 92.1543 | Low | No | No | Yes | Yes | Yes | 34 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
71 |  |  | C | 21.1888 | 92.1543 | Low | No | No | Yes | Yes | Yes | 35 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
72 |  |  | C | 21.1883 | 92.1535 | Low | No | No | Yes | Yes | Yes | 36 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
73 |  |  | C | 21.188 | 92.1538 | Low | No | No | Yes | Yes | Yes | 37 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
74 |  |  | C | 21.1901 | 92.1555 | Low | No | No | Yes | Yes | Yes | 38 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
75 |  |  | C | 21.1899 | 92.1547 | Low | No | No | Yes | Yes | Yes | 39 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
76 |  |  | C | 21.19 | 92.1543 | Low | No | No | Yes | Yes | Yes | 40 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
77 |  |  | D | 21.1892 | 92.1551 | Low | No | No | Yes | Yes | Yes | 41 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
78 |  |  | D | 21.1893 | 92.1557 | Low | No | No | Yes | Yes | Yes | 42 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
79 |  |  | D | 21.1894 | 92.1562 | Low | No | No | Yes | Yes | Yes | 43 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
80 |  |  | D | 21.1895 | 92.1563 | Low | No | No | Yes | Yes | Yes | 44 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
81 |  |  | D | 21.1878 | 92.1551 | Low | No | No | Yes | Yes | Yes | 45 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
82 |  |  | D | 21.1884 | 92.1564 | Low | No | No | Yes | Yes | Yes | 46 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
83 |  |  | E | 21.1868 | 92.1558 | Low | No | No | Yes | Yes | Yes | 47 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
84 |  |  | E | 21.187 | 92.1554 | Low | No | No | Yes | Yes | Yes | 48 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
85 |  |  | E | 21.1872 | 92.1553 | Low | No | No | Yes | Yes | Yes | 49 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
86 |  |  | E | 21.1864 | 92.1549 | Low | No | No | Yes | Yes | Yes | 50 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
87 |  |  | E | 21.1869 | 92.1549 | Low | No | No | Yes | Yes | Yes | 51 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
88 |  |  | E | 21.1874 | 92.1544 | Low | No | No | Yes | Yes | Yes | 52 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
89 |  |  | E | 21.1871 | 92.1541 | Low | No | No | Yes | Yes | Yes | 53 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
90 |  |  | E | 21.1871 | 92.1571 | Low | No | No | Yes | Yes | Yes | 54 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
91 |  |  | E | 21.1871 | 92.1567 | Low | No | No | Yes | Yes | Yes | 55 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
92 |  |  | E | 21.1867 | 92.1567 | Low | No | No | Yes | Yes | Yes | 56 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
93 |  |  | E | 21.1872 | 92.1526 | Low | No | No | Yes | Yes | Yes | 57 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
94 |  |  | E | 21.1861 | 92.1519 | Low | No | No | Yes | Yes | Yes | 58 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
95 |  |  | E | 21.1865 | 92.1519 | Low | No | No | Yes | Yes | Yes | 59 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
96 |  |  | E | 21.1868 | 92.1516 | Low | No | No | Yes | Yes | Yes | 60 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
97 |  |  | E | 21.1872 | 92.1518 | Low | No | No | Yes | Yes | Yes | 61 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
98 |  |  | F | 21.1876 | 92.1575 | Low | No | No | Yes | Yes | Yes | 62 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
99 |  |  | F | 21.1888 | 92.1565 | Low | No | No | Yes | Yes | Yes | 63 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low
100 |  |  | F | 21.1879 | 92.1573 | Low | No | No | Yes | Yes | Yes | 64 | None | Low | Low (negligible) | Yes | yes | yes | Medium | Yes | Low | Low | Low | Yes | Yes | Yes | Low | Low | Medium | None | Yes | Low | Low | None | Yes | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low | Low | Low | Low | Medium | Low | Low | Low | Low to Medium | Low | Low | Low

## Social & Gender Part
Package_WD_AF_29 Summary (Social Part)_Camp 10_ HHT-100 Nos.
General Information | [5 empty] | Will the project potentially involve an influx of workers to the project location, and will the influx be considered significant for the local community? | Is the project located in a rural or remote area? | Section C1, General Labor Influx Screening and Labor and Contractors management during COVID-19 | Section C2, Land acquisition and stakeholder screening and Labor and Contractors management during COVID-19 | Section C3, Social Capital Format | Photo (Consultation meeting events)
Sl.No | Package ID | Camp | Block | Lat | Long
Sl.No | Package ID | Camp | Block | Lat | Long
1 | EMCRP-WD_AF_29 | Camp_10 | A | 21.191 | 92.154 | Under the, subproject household toilet at DRP camp (camp 10) area, as per the E&S Safeguard team labor influx is not a significant issue at DRP subproject areas. Total skilled Labor: 1, unskilled labor 2 need per household toilet construction. All the unskilled labor will be engaged by the DRP community. No foreign labor will be engaged. All the skilled labor will stay at labor shed within the camp. The size of the labor shed will 225 s. ft. for male and 180 sq. ft. (need based) for the female. The frequency and extent of contact, communicate between the local community and outsiders are limited and controlled by the respective SMC and CIC management. Noted that, the incoming workers will be very low in numbers, so there will be no competition to use those resources. And, during screening and site identification process the CiC & local DPHE, the assigned consultants has conducted consultation meeting/ FGD with stakeholders. Among the stakeholders CiC, WASH Sector, SMC representatives, Contractor team and respective DRP Community were attended. Other than the mentioned meetings, the local DPHE has conducted many other consultation with DRP male and females. By the effort of coordination and linkage activities of project authority accomplished some formal view exchange meeting, individual household visit, FGD, Tea Stall discussion, consultation meetings. Local people will not be allowed to visit camp without the permission of CIC. The frequency and extent of contact, communicate between the local community and outsiders are limited and controlled by the respective SMC and CIC. Noted that UNFPA is being hired as a specialized organization to deal with the GBV activities. This project is a part of the Gender Component of the UNFPA 9th Country Programme and will contribute to achieve the CP outcome 3 ‘‘Advanced gender equality, women’s and girls’ empowerment, and reproductive rights, including for the most vulnerable and marginalized women, adolescents and youth’’. | Yes, obviously the sub-project household toilet construction located in a remote hilly, corrugated CiC assigned DRP Camp area. The frequency and extent of contact, communicate between the local community and outsiders are limited and controlled by the respective CIC. The area isn’t sensitive at environmental conditions. TDH is camp focal agency, UNICEF is area focal agency. DPHE is implementing the project with the financial assistance of World Bank and Govt. of Bangladesh. By establishing the household toilet scheme, per toilet about 20 people will be benefitted to sanitation requirements. In the Camp_10 around 29,771 (according to UNHCR data, April 30, 2020) people over there. Within the household toilet area 1 CiC office, 1 meal distribution point, 1 community facilities, 16 SWM, 100+ learning centers, 2 child protection facilities, 2 age friendly space, 80+ fire points, 1 heath facility, 1 SM agency office, 1 community center, 4 distribution points, 3 warehouse, 1 E-Voucher Outlet, 2 LPG centers etc. are identified. However, none is going to be affected due to project intervention. No disturbance is anticipated due to construction activities to those environmental and social components. In this scheme area, no elephant migration routes exists (ref. IUCN & Elephant Response Team). The DRP will be benefited from the sub-project. | Regarding General Labor Influx screening process under the sub-project (DRP household toilet) establishment in the proposed areas, it has been revealed that no scope to arise labor influx situation. Total skilled Labor: 1, unskilled labor 2 need per Latrine construction. All of the unskilled labor will be engaged from the DRP community. No foreign labor will be engaged. To establish the scheme tasks, some outsider labor, and technicians will be engaged over there; so no scope to arise social conflict might be raised. A complete Gender action plan already developed and approved, a full time Gender Specialist of this project has been assigned to oversee the GBV based issues for this subproject. The gender and gender-based violence issues (i.e. human trafficking, eve teasing, etc.) are being addressed through mainstreaming activities. As the mitigation measure the Social Safeguard team and GRC has been following the respective GRM, will aware on GBV and motivate the community through consultation meeting, counseling. Given the sensitivities in the camps areas (social, cultural, religious, gender, disabilities, orphan. No DRP shelters will be affected. However, during construction if any shelters require to shift, mitigation measures will be taken according to RPF. Consultations will be conducted with stakeholders, camp and block focal persons, and site management. During construction, if any shelters are affected, contractors are responsible to mitigate the impacts following the RPF as well. Labor and Contractors management during COVID-19: For projects involving construction/civil works, contractors will develop specific procedures or plans so that adequate precautions are in place to prevent or minimize an outbreak of COVID-19, and what should be done if a worker gets sick.: • DPHE has oriented the contractor and labor on Covid-19 management including OHS (Occupational Health Safety). • Assessing the characteristics of the workforce, including those with underlying health issues or who may be otherwise at risk • Confirming workers are fit for work, to include temperature testing and refusing entry to sick workers • Considering ways to minimize entry/exit to site or the workplace, and limiting contact between workers and the community/general public • Training workers on hygiene and other preventative measures, and implementing a communication strategy for regular updates on COVID-19 related issues and the status of affected workers • Treatment of workers who are or should be self-isolating and/or are displaying symptoms • Assessing risks to continuity of supplies of medicine, water, fuel, food and PPE, taking into account international, national and local supply chains • Reduction, storage and disposal of medical waste • Adjustments to work practices, to reduce the number of workers and increase social distancing • Expanding health facilities on-site compared to usual levels, developing relationships with local health care facilities and organize for the treatment of sick workers • Building worker accommodations further apart, or having one worker accommodation in a more isolated area, which may be easily converted to quarantine and treatment facilities, if needed • Establishing a procedure to follow if a worker becomes sick (following WHO guidelines) • Implementing a communication strategy with the community, community leaders and local government in relation to COVID-19 issues on the site. For supporting health facilities, plans or procedures will be in place to address the following issues: • Obtaining adequate supplies of medical PPE, including gowns, aprons, curtains; medical masks and respirators (N95 or FFP2); gloves (medical, and heavy duty for cleaners); eye protection (goggles or face screens); hand washing soap and sanitizer; and effective cleaning equipment. Where relevant PPE cannot be obtained, the plan should consider viable alternatives, such as cloth masks, alcohol-based cleansers, hot water for cleaning and extra hand washing facilities, until such time as the supplies are available • Training medical staff on the latest WHO advice and recommendations on the specifics of COVID-19 • Conducting enhanced cleaning arrangements, including thorough cleaning (using adequate disinfectant) of catering facilities/canteens/food/drink facilities, latrines/toilets/showers, common areas, including door handles, floors and all surfaces that are touched regularly | No, land acquisition is not for this subproject household toilet establishment at the proposed DRP Camp_10 site. The ownership of the land is government and lands are currently empty. The land is selected with the recommendation of CiC, SMC & Local DPHE and assigned UN agencies. It is noted that no agro, non-agro establishments, assets, habitat would be displaced by this subproject interventions. The tents of the DRP be affected if any, appropriate mitigation measures (as per ESMF - RAP- GRM) would be taken place. So that there is no possibility of unrest - conflict situation to be raised. If the tents are required to shift and unavoidable, adequate consultation will be done with the DRP and Stakeholders. In the consultation session elaborately discussed on environmental and social aspects of project interventions, its above mentioned issues might be occurred at the project sites, habitat. The community and elites were very much welcomed, praised appreciated the DPHE-EMCRP initiatives on WASH sector sub projects. As per their opinion, the safe water and improved sanitation (construction of toilets) is one of the priority needs for them for secured and better livelihoods aspects. They opined that, it is not an Elephant corridor and no scope of Elephant/Human conflict the Elephant Response Team of Camp_10 also agreed with their opinion. By the consultation meeting, the participants from DRP community become aware and sensitized on E&S probable impact issues, precautions, child safety etc. Also discussed on, any chances of displacement of existing structures and relocations of local institutions (mosques, school/ learning centers). Team sincerely briefed the role of DRP to-do & not to-do, compensation mechanism if any objection and complaints. | Aiming to seek necessary support to accomplish household toilet scheme In the Camp_10 in the E&S Screening Process we have listed down the concerned social institutes/bodies working in the camp, intended project influence areas to enlist them for the possible inclusion in the management, and monitoring of the projects. List the name of social institutes/ bodies under the given categorization along with the following information. Use separate sheet for each category of social institute/body. The information can be collected through secondary sources such as RRRC/UN agencies or different development organizations that are involved with the DRP crisis projects, i.e. -Bangladesh Government agencies - Mr. Muhammad Mizanur Rahman RRRC Commissioner, CXB, Email rrccox@yahoo.com ………………………… Engr. Md. Ibne Mayaz Pramanik, DPHE, Executive Engineer, Cox’s Bazar, xendphecoxsbazar@gmail.com ……………………. Mohammad Salahuddin DC, Cox’s Bazar dccoxsbazar@mopa.gov.bd …………………………………………… Sarwar Kamal Camp-in-Charge & Executive Magistrate Camp_10 (Senior Asst. Secretary) camp 1 to10@rrrc.gov.bd Site Management: WASH Sector Focal : UNICEF and BRAC in coordinating WASH efforts
2 |  |  | A | 21.1912 | 92.1541 | As same as above | As same as above | As same as above | As same as above | As same as above
3 |  |  | A | 21.1913 | 92.1543 | As same as above | As same as above | As same as above | As same as above | As same as above
4 |  |  | E | 21.1868 | 92.154 | As same as above | As same as above | As same as above | As same as above | As same as above
5 |  |  | E | 21.1866 | 92.1535 | As same as above | As same as above | As same as above | As same as above | As same as above
6 |  |  | E | 21.1866 | 92.1532 | As same as above | As same as above | As same as above | As same as above | As same as above
7 |  |  | E | 21.1864 | 92.153 | As same as above | As same as above | As same as above | As same as above | As same as above
8 |  |  | E | 21.1861 | 92.1534 | As same as above | As same as above | As same as above | As same as above | As same as above
9 |  |  | E | 21.1865 | 92.1523 | As same as above | As same as above | As same as above | As same as above | As same as above
10 |  |  | E | 21.1873 | 92.1527 | As same as above | As same as above | As same as above | As same as above | As same as above
11 |  |  | E | 21.1872 | 92.1529 | As same as above | As same as above | As same as above | As same as above | As same as above
12 |  |  | C | 21.1905 | 92.1552 | As same as above | As same as above | As same as above | As same as above | As same as above
13 |  |  | C | 21.1907 | 92.1548 | As same as above | As same as above | As same as above | As same as above | As same as above
14 |  |  | C | 21.1904 | 92.154 | As same as above | As same as above | As same as above | As same as above | As same as above
15 |  |  | C | 21.1904 | 92.1539 | As same as above | As same as above | As same as above | As same as above | As same as above
16 |  |  | C | 21.1904 | 92.1537 | As same as above | As same as above | As same as above | As same as above | As same as above
17 |  |  | B | 21.1943 | 92.1535 | As same as above | As same as above | As same as above | As same as above | As same as above
18 |  |  | B | 21.1946 | 92.1535 | As same as above | As same as above | As same as above | As same as above | As same as above
19 |  |  | B | 21.1942 | 92.1542 | As same as above | As same as above | As same as above | As same as above | As same as above
20 |  |  | B | 21.1944 | 92.1544 | As same as above | As same as above | As same as above | As same as above | As same as above
21 |  |  | B | 21.1937 | 92.154 | As same as above | As same as above | As same as above | As same as above | As same as above
22 |  |  | B | 21.1935 | 92.1542 | As same as above | As same as above | As same as above | As same as above | As same as above
23 |  |  | B | 21.1934 | 92.1535 | As same as above | As same as above | As same as above | As same as above | As same as above
24 |  |  | B | 21.1931 | 92.1545 | As same as above | As same as above | As same as above | As same as above | As same as above
25 |  |  | B | 21.1925 | 92.155 | As same as above | As same as above | As same as above | As same as above | As same as above
26 |  |  | B | 21.1928 | 92.1549 | As same as above | As same as above | As same as above | As same as above | As same as above
27 |  |  | B | 21.1917 | 92.1545 | As same as above | As same as above | As same as above | As same as above | As same as above
28 |  |  | B | 21.1916 | 92.155 | As same as above | As same as above | As same as above | As same as above | As same as above
29 |  |  | B | 21.1922 | 92.155 | As same as above | As same as above | As same as above | As same as above | As same as above
30 |  |  | A | 21.1921 | 92.1516 | As same as above | As same as above | As same as above | As same as above | As same as above
31 |  |  | A | 21.192 | 92.1515 | As same as above | As same as above | As same as above | As same as above | As same as above
32 |  |  | A | 21.1918 | 92.1518 | As same as above | As same as above | As same as above | As same as above | As same as above
33 |  |  | A | 21.1921 | 92.1518 | As same as above | As same as above | As same as above | As same as above | As same as above
34 |  |  | A | 21.1914 | 92.1518 | As same as above | As same as above | As same as above | As same as above | As same as above
35 |  |  | A | 21.1914 | 92.1517 | As same as above | As same as above | As same as above | As same as above | As same as above
36 |  |  | A | 21.1911 | 92.1518 | As same as above | As same as above | As same as above | As same as above | As same as above
37 |  |  | A | 21.1909 | 92.152 | As same as above | As same as above | As same as above | As same as above | As same as above
38 |  |  | A | 21.1914 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
39 |  |  | A | 21.1917 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
40 |  |  | A | 21.1939 | 92.1525 | As same as above | As same as above | As same as above | As same as above | As same as above
41 |  |  | A | 21.1932 | 92.153 | As same as above | As same as above | As same as above | As same as above | As same as above
42 |  |  | A | 21.1935 | 92.1522 | As same as above | As same as above | As same as above | As same as above | As same as above
43 |  |  | A | 21.1931 | 92.1525 | As same as above | As same as above | As same as above | As same as above | As same as above
44 |  |  | A | 21.193 | 92.152 | As same as above | As same as above | As same as above | As same as above | As same as above
45 |  |  | A | 21.1928 | 92.1519 | As same as above | As same as above | As same as above | As same as above | As same as above
46 |  |  | A | 21.1923 | 92.1529 | As same as above | As same as above | As same as above | As same as above | As same as above
47 |  |  | A | 21.1928 | 92.1527 | As same as above | As same as above | As same as above | As same as above | As same as above
48 |  |  | A | 21.1927 | 92.1538 | As same as above | As same as above | As same as above | As same as above | As same as above
49 |  |  | A | 21.1922 | 92.1532 | As same as above | As same as above | As same as above | As same as above | As same as above
50 |  |  | A | 21.1911 | 92.1528 | As same as above | As same as above | As same as above | As same as above | As same as above
51 |  |  | A | 21.191 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
52 |  |  | C | 21.1905 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
53 |  |  | C | 21.1904 | 92.1526 | As same as above | As same as above | As same as above | As same as above | As same as above
54 |  |  | C | 21.1902 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
55 |  |  | C | 21.1901 | 92.1525 | As same as above | As same as above | As same as above | As same as above | As same as above
56 |  |  | C | 21.1892 | 92.1521 | As same as above | As same as above | As same as above | As same as above | As same as above
57 |  |  | C | 21.1889 | 92.152 | As same as above | As same as above | As same as above | As same as above | As same as above
58 |  |  | C | 21.1884 | 92.1522 | As same as above | As same as above | As same as above | As same as above | As same as above
59 |  |  | C | 21.1883 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
60 |  |  | C | 21.1885 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
61 |  |  | C | 21.188 | 92.1524 | As same as above | As same as above | As same as above | As same as above | As same as above
62 |  |  | C | 21.188 | 92.1531 | As same as above | As same as above | As same as above | As same as above | As same as above
63 |  |  | C | 21.1879 | 92.1532 | As same as above | As same as above | As same as above | As same as above | As same as above
64 |  |  | C | 21.1885 | 92.1532 | As same as above | As same as above | As same as above | As same as above | As same as above
65 |  |  | C | 21.1892 | 92.1528 | As same as above | As same as above | As same as above | As same as above | As same as above
66 |  |  | C | 21.1878 | 92.1534 | As same as above | As same as above | As same as above | As same as above | As same as above
67 |  |  | C | 21.1896 | 92.1537 | As same as above | As same as above | As same as above | As same as above | As same as above
68 |  |  | C | 21.1897 | 92.1533 | As same as above | As same as above | As same as above | As same as above | As same as above
69 |  |  | C | 21.1892 | 92.154 | As same as above | As same as above | As same as above | As same as above | As same as above
70 |  |  | C | 21.189 | 92.1543 | As same as above | As same as above | As same as above | As same as above | As same as above
71 |  |  | C | 21.1888 | 92.1543 | As same as above | As same as above | As same as above | As same as above | As same as above
72 |  |  | C | 21.1883 | 92.1535 | As same as above | As same as above | As same as above | As same as above | As same as above
73 |  |  | C | 21.188 | 92.1538 | As same as above | As same as above | As same as above | As same as above | As same as above
74 |  |  | C | 21.1901 | 92.1555 | As same as above | As same as above | As same as above | As same as above | As same as above
75 |  |  | C | 21.1899 | 92.1547 | As same as above | As same as above | As same as above | As same as above | As same as above
76 |  |  | C | 21.19 | 92.1543 | As same as above | As same as above | As same as above | As same as above | As same as above
77 |  |  | D | 21.1892 | 92.1551 | As same as above | As same as above | As same as above | As same as above | As same as above
78 |  |  | D | 21.1893 | 92.1557 | As same as above | As same as above | As same as above | As same as above | As same as above
79 |  |  | D | 21.1894 | 92.1562 | As same as above | As same as above | As same as above | As same as above | As same as above
80 |  |  | D | 21.1895 | 92.1563 | As same as above | As same as above | As same as above | As same as above | As same as above
81 |  |  | D | 21.1878 | 92.1551 | As same as above | As same as above | As same as above | As same as above | As same as above
82 |  |  | D | 21.1884 | 92.1564 | As same as above | As same as above | As same as above | As same as above | As same as above
83 |  |  | E | 21.1868 | 92.1558 | As same as above | As same as above | As same as above | As same as above | As same as above
84 |  |  | E | 21.187 | 92.1554 | As same as above | As same as above | As same as above | As same as above | As same as above
85 |  |  | E | 21.1872 | 92.1553 | As same as above | As same as above | As same as above | As same as above | As same as above
86 |  |  | E | 21.1864 | 92.1549 | As same as above | As same as above | As same as above | As same as above | As same as above
87 |  |  | E | 21.1869 | 92.1549 | As same as above | As same as above | As same as above | As same as above | As same as above
88 |  |  | E | 21.1874 | 92.1544 | As same as above | As same as above | As same as above | As same as above | As same as above
89 |  |  | E | 21.1871 | 92.1541 | As same as above | As same as above | As same as above | As same as above | As same as above
90 |  |  | E | 21.1871 | 92.1571 | As same as above | As same as above | As same as above | As same as above | As same as above
91 |  |  | E | 21.1871 | 92.1567 | As same as above | As same as above | As same as above | As same as above | As same as above
92 |  |  | E | 21.1867 | 92.1567 | As same as above | As same as above | As same as above | As same as above | As same as above
93 |  |  | E | 21.1872 | 92.1526 | As same as above | As same as above | As same as above | As same as above | As same as above
94 |  |  | E | 21.1861 | 92.1519 | As same as above | As same as above | As same as above | As same as above | As same as above
95 |  |  | E | 21.1865 | 92.1519 | As same as above | As same as above | As same as above | As same as above | As same as above
96 |  |  | E | 21.1868 | 92.1516 | As same as above | As same as above | As same as above | As same as above | As same as above
97 |  |  | E | 21.1872 | 92.1518 | As same as above | As same as above | As same as above | As same as above | As same as above
98 |  |  | F | 21.1876 | 92.1575 | As same as above | As same as above | As same as above | As same as above | As same as above
99 |  |  | F | 21.1888 | 92.1565 | As same as above | As same as above | As same as above | As same as above | As same as above
100 |  |  | F | 21.1879 | 92.1573 | As same as above | As same as above | As same as above | As same as above | As same as above