## শিমুলকান্দি ভূমি অফিস
Monthly Progress Report
Financial Year : 2017-18
Name of Project: Construction of Shimulkandi Bhumi office Building at Bhairab Upazila, Kishoregonj.
Reporting Month:June/2019
District: Kishoreganj.
Upazila: Bhairab.
Sl No. | Name of Scheme/Union | Name of Contractor | Estimated Cost (in Taka) | Original Contract Value(in Taka) | Revised Contract Value(in Taka) | Date of Commencement(as per W/O) | Actual Date of Commencement | Date of Completion(as per W/O) | Actual Date of Completion | Physical Progress(%) |  | Financial Progress(in Taka) |  | Fund Required(as per Physical Progress) | Remarks
[10 empty] | Upto Previous Month | Upto Reporting Month | Total Fund Received | Total Fund Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Construction of Shimulkandi Bhumi office Building at Bhairab Upazila, Kishoregonj. | M/S Mominul Haque, Bhairab, Kishoreganj. | 10084000 | 9075600 | - | 16.04.18 | - | 15.02.19 | - | 100% | 0% |  | 2546651 | -
[8 empty] | Total Tk. |  |  |  |  | 2546651
| Accountant |  | Sub-Asstt, Engineer | [6 empty] | Upazila Engineer
| LGED |  | LGED | [6 empty] | Bhairab, Kishoreganj.
| Bhairab, Kishoreganj. |  | Bhairab, Kishoreganj.

## PRMMP বধ্যবূমি
Monthly Progress Report
Financial Year : 2017-18
Name of Project: Construction of Panaullarchar Boddobhumi Under Bhairab Upazila, Kishoreganj.
Reporting Month: June/2019
District: Kishoreganj.
Upazila: Bhairab.
Sl No. | Name of Scheme/Union | Name of Contractor | Estimated Cost (in Taka) | Original Contract Value(in Taka) | Revised Contract Value(in Taka) | Date of Commencement(as per W/O) | Actual Date of Commencement | Date of Completion(as per W/O) | Actual Date of Completion | Physical Progress(%) |  | Financial Progress(in Taka) |  | Fund Required(as per Physical Progress) | Remarks
[10 empty] | Upto Previous Month | Upto Reporting Month | Total Fund Received | Total Fund Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Construction of Panaullarchar Boddobhumi Under Bhairab Upazila, Kishoreganj. | M/S Shahil Enterprise |  | 2254560.3 | - | 30.06.2018 | - | 29.10.2018 | - | 100% | 100% | 0 | 1177079.22 | -
[8 empty] | Total Tk. |  |  |  | 0 | 1177079.22
| Accountant |  | Sub-Asstt, Engineer | [6 empty] | Upazila Engineer
| LGED |  | LGED | [6 empty] | Bhairab, Kishoreganj.
| Bhairab, Kishoreganj. |  | Bhairab, Kishoreganj.

## Shimulkandi GC
Monthly Progress Report
Financial Year : 2017-18
Name of Project: Improvement of Shimulkandi Growth Center, Upazila: Bhairab, Dist: Kishoreganj.
Reporting Month: June/2019
District: Kishoreganj.
Upazila: Bhairab.
Sl No. | Name of Scheme/Union | Name of Contractor | Estimated Cost (in Taka) | Original Contract Value(in Taka) | Revised Contract Value(in Taka) | Date of Commencement(as per W/O) | Actual Date of Commencement | Date of Completion(as per W/O) | Actual Date of Completion | Physical Progress(%) |  | Financial Progress(in Taka) |  | Fund Required(as per Physical Progress) | Remarks
[10 empty] | Upto Previous Month | Upto Reporting Month | Total Fund Received | Total Fund Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Improvement of Shimulkandi Growth Center, Upazila: Bhairab, Dist: Kishoreganj. | M//S Mominul Haque | 0 | 10494816.339 | - | 0:00 | 20.02.2018 | 19.02.2019 | 0 | 100% | 100% | 0 | 0 | -
[8 empty] | Total Tk. |  |  |  | 0 | 0
| Accountant |  | Sub-Asstt, Engineer | [6 empty] | Upazila Engineer
| LGED |  | LGED | [6 empty] | Bhairab, Kishoreganj.
| Bhairab, Kishoreganj. |  | Bhairab, Kishoreganj.

## Upazila Mukkt Bhaban (2)
Monthly Progress Report
Financial Year : 2017-18
Name of Project: Construction of Upazila Muktijoddha Complex Bhaban at Bhairab Upazila, Dist: Kishoreganj.
Reporting Month: June/2019
District: Kishoreganj.
Upazila: Bhairab.
Sl No. | Name of Scheme/Union | Name of Contractor | Estimated Cost (in Taka) | Original Contract Value(in Taka) | Revised Contract Value(in Taka) | Date of Commencement(as per W/O) | Actual Date of Commencement | Date of Completion(as per W/O) | Actual Date of Completion | Physical Progress(%) |  | Financial Progress(in Taka) |  | Fund Required(as per Physical Progress) | Remarks
[10 empty] | Upto Previous Month | Upto Reporting Month | Total Fund Received | Total Fund Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Construction of Upazila Muktijoddha Complex Bhaban at Bhairab Upazila, Dist: Kishoreganj. | M//S Mominul Haque | 0 | 19214113.5 | - | 0:00 | - | 0:00 | 0 | 100% | 0% | 0 | 0 | -
[8 empty] | Total Tk. |  |  |  | 0 | 0
| Accountant |  | Sub-Asstt, Engineer | [6 empty] | Upazila Engineer
| LGED |  | LGED | [6 empty] | Bhairab, Kishoreganj.
| Bhairab, Kishoreganj. |  | Bhairab, Kishoreganj.

## Upazila Complex Bhaban
Monthly Progress Report
Financial Year : 2016-17
Name of Project: Construction of Upazila Extension Administrative & Hall room building Project, LGED.
Reporting Month: June/2019
District: Kishoreganj.
Upazila: Bhairab.
Sl No. | Name of Scheme/Union | Name of Contractor | Estimated Cost (in Taka) | Original Contract Value(in Taka) | Revised Contract Value(in Taka) | Date of Commencement(as per W/O) | Actual Date of Commencement | Date of Completion(as per W/O) | Actual Date of Completion | Physical Progress(%) |  | Financial Progress(in Taka) |  | Fund Required(as per Physical Progress) | Remarks
[10 empty] | Upto Previous Month | Upto Reporting Month | Total Fund Received | Total Fund Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Const. of Upazila Extension Administrative & Hall room building at Upazila Bhairab, Dist: Kishoreganj. | M/S R-TA Enterprise | 46827678 | 39757204.66 | - | 10.08.2016 | - | 9.11.2017 | - | 75% | 85% | 33157233 | 33157233 | -
[8 empty] | Total Tk. |  |  |  | 33157233 | 33157233
| Accountant |  | Sub-Asstt, Engineer | [6 empty] | Upazila Engineer
| LGED |  | LGED | [6 empty] | Bhairab, Kishoreganj.
| Bhairab, Kishoreganj. |  | Bhairab, Kishoreganj.