## VRRP
Contract Status of Village Road Rehabilitation Project (VRRP)
District : |  |  | Gaibandha | [18 empty] | Date of Reporting: | 2021-01-10
Sl. No. | Financial Year | Date of Approval | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Name of Contractor | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Less/ Above (%) | Elapse Day to Contract | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Revised Work Completion Date | Elapse Day (%) | Revised [E] Day in (%) | Phy. Progress (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Revised Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Upazila: |  |  | 1. Gaibandha Sadar
1 | FY 2020-21 | 2020-10-15 | 20-21/W-713 | 1 | 132245044 | Konarpara Ghat to Manosh regulator Road | Md. Arif rayhan, Gaibandha | 2300 | 3720 | 1420 | 48,33,769.00 | 4592080.55 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-13 |  | -5.085% |  | 10% | - |  |  | 59 | -44209 | -3
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
1 | Sub-Total: |  | -1 |  |  | Not Contacted Amount | 0 |  |  | 1.42 | 0 | 4592080.55 | #DIV/0! |  | 0 | Fin. Pgr. (%) | - |  |  |  | 10% | [6 empty] | 0 | 0 | 0 | 0
Upazila: |  |  | 2. Gobindaganj
1 | FY 2020-21 | 2020-10-15 | 20-21/W-1294 | 1 | 132304141 | Talukkanupur UP at NHW Samaspara-Jamalpur hat Road | Rahed Ent, Gaibandha | 1275 | 2680 | 1405 | 55,81,617.00 | 5302536.15 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-28 |  | -4.054% |  | 10% | - |  |  | 74 | -44209 | -3
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
1 | Sub-Total: |  | -1 |  |  | Not Contacted Amount | 0 |  |  | 1.405 | 0 | 5302536.15 | #DIV/0! |  | 0 | Fin. Pgr. (%) | - |  |  |  | 10% | [6 empty] | 0 | 0 | 0 | 0
Upazila: |  |  | 3. Fulchhari
1 | FY 2018-19 | 2019-03-06 | 18-19/ W-04 | 1 | 132214016 | Purba Salua H/O Mozibar- (H/O Osman Munsi) Purba Salua Road | M/S PAMEL TRADERS | 0 | 1014 | 1014 | 5494150 | 5219442.5 | -5% | 81 | 5207167 | 2019-05-26 | 2019-07-10 |  | 1322% |  | 100% | - | Final Bill Paid |  | 45 | -43611 | 595 |  | 1014 | 5219442.5 | 5207167
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
1 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 1.014 | 5494150 | 5219442.5 | -5% |  | 5207167 | Fin. Pgr. (%) | 99.76% |  |  |  | 100% | [6 empty] | 1 | 1.014 | 5219442.5 | 5207167
Upazila: |  |  | 4. Palashbari
1 | FY 2018-19 | 2019-03-06 | 18-19/ W-06 | 1 | 132675070 | Mostafujer Abu Talab House to Moraripur Nururzzan House Road | Bhai Bhai Construction, Rangpur | 0 | 285 | 285 | 820775 | 779736.25 | -5% | 89 | 779735 | 2019-06-03 | 2019-06-26 |  | 2552% |  | 100% | - | Final Bill Paid |  | 23 | -43619 | 587 |  | 285 | 779736.25 | 779735
2 | FY 2020-21 | 2020-10-15 | 20-21/W-1299 | 1 | 132674063 | Horinathpur chowmatha to kumidpur 2 No. Govt. Pry. School via putimari taluk kew Bari Road | M/S Rumi Const, Rangpur | 0 | 1645 | 1645 | 61,73,733.00 | 5865046.35 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-28 |  | -4.054% |  |  | - |  |  | 74 | -44209 | -3
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
2 | Sub-Total: |  | -1 |  |  | Not Contacted Amount | 0 |  |  | 1.93 | 820775 | 6644782.6 | 709.6% |  | 779735 | Fin. Pgr. (%) | 11.73% |  |  |  | 11.73% | [6 empty] | 1 | 0.285 | 779736.25 | 779735
Upazila: |  |  | 5. Sadullapur
1 | FY 2018-19 | 2019-01-07 | 272771 18-19/W-03 | 1 | 132824023 | Mohishbandhi Hat - Rahmatpur GC via Rasulpur Hat Road | Md.Shamsul Alam, Gaibandha | 0 | 530 | 530 | 1943783 | 1846593.85 | -5% | 71 | 1845191 | 2019-03-19 | 2019-05-18 |  | 1105% |  | 100% | - | Final Bill Paid |  | 60 | -43543 | 663 |  | 530 | 1846593.85 | 1845191
2 | FY 2020-21 | 2020-10-15 | 20-21/W-714 | 1 | 132825050 | Taraf kamal-Rasulpur Bazar Road | M/S Omi Const, Kurigram | 0 | 700 | 700 | 20,34,433.00 | 1932711.35 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-13 |  | -5.085% |  | 0% | - |  |  | 59 | -44209 | -3
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
2 | Sub-Total: |  | -1 |  |  | Not Contacted Amount | 0 |  |  | 1.23 | 1943783 | 3779305.2 | 94.43% |  | 1845191 | Fin. Pgr. (%) | 48.82% |  |  |  | 48.86% | [6 empty] | 1 | 0.53 | 1846593.85 | 1845191
Upazila: |  |  | 6. Shaghata
1 | FY 2018-19 | 2019-01-07 | 272769 18-19/W-01 | 1 | 132884063 | Saghata-Gaibandha R&H Road at Jharavarsha - Ghuridaha U.P. Office Road | Md. Shamim Ahmed Mondal, Saghata, Gaibandha | 0 | 1490 | 1490 | 5041304 | 5845757.55 | 15.96% | 69 | 5837890 | 2019-03-17 | 2019-05-31 |  | 886.7% |  | 100% | - | Final Bill Paid |  | 75 | -43541 | 665 |  | 1490 | 5845757.55 | 5837890
2 | FY 2018-19 | 2019-01-07 |  | 2 | 132884026 | Bonarpara Saghatta Road - Bilbosta Road |  | 0 | 325 | 325 | 1112125 | 1e-18 | -100% | 69 |  | 2019-03-17 | 2019-05-31 |  | 886.7% |  | 100% | - | Final Bill Paid |  | 75 | -43541 | 665 |  | 325 | 1e-18 | 0
3 | FY 2018-19 | 2019-01-07 | 272770 18-19/W-02 | 1 | 132884041 | Thoikorer para H/O Samad Member-WAPDA Embankment Road | M.S S. S Engineering & Construction, Rangpur | 0 | 1300 | 1300 | 4853423 | 9236248.65 | 90.3% | 63 | 4475063 | 2019-03-11 | 2019-05-10 |  | 1118% |  | 100% | - | Final Bill Paid |  | 60 | -43535 | 671 |  | 1300 | 9236248.65 | 4475063
4 | FY 2018-19 | 2019-01-07 |  | 2 | 132885049 | Falia - Panchpur Road |  | 700 | 1930 | 1230 | 4868944 | 1e-18 | -100% | 63 | 4464991 | 2019-03-11 | 2019-05-10 |  | 1118% |  | 100% | - | Final Bill Paid |  | 60 | -43535 | 671 |  | 1230 | 1e-18 | 4464991
5 | FY 2020-21 | 2020-10-15 | 20-21/W-1295 | 1 | 132885064 | Dimla padumsahor shenpara-Hafizia Madrasha Road | M/S ABD Bricks, Gaibandha | 0 | 1309 | 1309 | 43,02,177.00 | 4087068.15 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-13 |  | -5.085% |  | 10% | - |  |  | 59 | -44209 | -3
6 | FY 2020-21 | 2020-10-15 | 20-21/W-1296 | 1 | 132884038 | Boliarber GPS - Kamalerpara- Falia Pucca Road | Mst. Dil Afruja Banu Suiti, Gaibandha | 0 | 1020 | 1020 | 38,81,327.00 | 3687260.65 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-13 |  | -5.085% |  | 20% | - |  |  | 59 | -44209 | -3
7 | FY 2020-21 | 2020-10-15 | 20-21/W-1297 | 1 | 132885026 | Shankorgonj UZR-Abdullah memorial School Road | M/S Sapan Tr, Gaibandha | 0 | 1950 | 1950 | 75,48,354.00 | 7170936.3 | #VALUE! | 90 |  | 2021-01-13 | 2021-04-13 |  | -3.333% |  | 10% | - |  |  | 90 | -44209 | -3
8 | FY 2020-21 | 2020-10-15 | 20-21/W-1298 | 1 | 132885155 | Late Saidur Rahman UP Chairman House - Gatia Pucca Road | M/S anaf Tr, Saghata, Gaibandha | 0 | 1120 | 1120 | 37,74,758.00 | 3586020.1 | #VALUE! | 90 |  | 2021-01-13 | 2021-03-13 |  | -5.085% |  | 0% | - |  |  | 59 | -44209 | -3
9 | FY 2020-21 | 2020-10-15 | 20-21/W-27 | 1 | 132885101 | Bhangamore N/S - Vangamore H/O Saidur rahman UP Chairman Road | Rabbi Ent, Rangpur | 0 | 1540 | 1540 | 95,88,301.00 | 9108885.95 | #VALUE! | 90 |  | 2021-01-13 | 2021-04-13 |  | -3.333% |  | 10% | - |  |  | 90 | -44209 | -3
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
9 | Sub-Total: |  | -5 |  |  | Not Contacted Amount | 0 |  |  | 11.284 | 15875796 | 42722177.35 | 169.1% |  | 14777944 | Fin. Pgr. (%) | 34.59% |  |  |  | 41.8% | [6 empty] | 4 | 4.345 | 15082006.2 | 14777944
Upazila: |  |  | 7. Sundarganj
1 | FY 2018-19 | 2019-03-06 | 18-19/ W-05 | 1 | 132915086 | Bolai Samas Road | Bhai Bhai Construction, Rangpur | 0 | 689 | 689 | 1956808 | 1858968.284 | -5% | 89 | 1854954 | 2019-06-03 | 2019-07-30 |  | 1030% |  | 100% | - | Final Bill Paid |  | 57 | -43619 | 587 |  | 689 | 1858968.284 | 1854954
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  |  | - |  |  | - |  |  | 0 | 0 | -
1 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 0.689 | 1956808 | 1858968.284 | -5% |  | 1854954 | Fin. Pgr. (%) | 99.78% |  |  |  | 100% | [6 empty] | 1 | 0.689 | 1858968.284 | 1854954
17 | Grand Total: |  | -9 |  |  | Not Contacted Amount | 0 |  |  | 18.972 | 26091312 | 70119292.634 | 168.7% |  | 24464991 | Fin. Pgr. (%) | 34.89% |  |  | 100% | 40.72% |  |  |  | -59.28% |  |  | 8 | 6.863 | 24786747.084 | 24464991
Fund Received: | [6 empty] | Total Sch. No., 100% Completed Sch. Nos., Length, Cont.-A & A-Paid | 17 | 8 | 6.863 | 24786747.084 | 24464991 | [8 empty] | Cash in Hand: | 9
Date: | 2019-05-21 |  |  | 2019-05-29 |  | 2019-12-24 | 2020-11-08 | [15 empty] | Total:
Tk. | 5000000 |  |  | 5000000 |  | 10000000 | 4465000 | [15 empty] | 24465000
Comments if any:
[15 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  |  |  | Amount Required upto June (Tk.) | Remarks
FY 2018-19
FY 2019-20
FY 2020-21
FY 2021-22
1. Gaibandha Sadar
2. Gobindaganj
3. Fulchhari
4. Palashbari
5. Sadullapur
6. Shaghata
7. Sundarganj

## Bridge
Contract Status of Bridge Maintenance (GoB Maintenance)
District : |  | Gaibandha | [16 empty] | Date of Reporting: | 2021-01-10
Sl. No. | Category of Maintenance | Date of Approval | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Name of Contractor | At Chainage (m) | Span Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Less/ Above (%) | Elapse Day to Contract | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progress (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Upazila: |  | 1. Gaibandha Sadar
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 2. Gobindaganj
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 3. Fulchhari
1 | EM_Bridge | 2020-09-02 |  | 1 | 132213001 | Re-Lunching of 27.45m of Steel Bridge on Udakhali UP H/Q-Sigria Bazar Road | Md. Rased Khan menon | 1200 | 27.45 | 600000 | 598814.33 | -0.1976% | 52 |  | 2020-10-24 | 2020-11-23 | 260% | 100% | - |  |  | 30 | 78
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
1 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 27.45 | 600000 | 598814.33 | -0.1976% |  | 0 | Fin. Pgr. (%) | - |  | 100%
Upazila: |  | 4. Palashbari
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 5. Sadullapur
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 6. Shaghata
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 7. Sundarganj
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
1 | Grand Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 27.45 | 600000 | 598814.33 | -0.1976% |  | 0 | Fin. Pgr. (%) | - |  | 100% |  |  |  | 15/12
Fund Received: | [17 empty] | Cash in Hand: | 0
Date: | [19 empty] | Total:
Tk. | [19 empty] | 0
Comments if any:
[14 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  | Amount Required upto June (Tk.) | Remarks
PM_Bridge
Re-hab._Bridge
EM_Bridge
CO_Bridge
1. Gaibandha Sadar
2. Gobindaganj
3. Fulchhari
4. Palashbari
5. Sadullapur
6. Shaghata
7. Sundarganj

## Culvert
Contract Status of Culvert Maintenance (GoB Maintenance)
District : |  | Gaibandha | [16 empty] | Date of Reporting: | 2021-01-10
Sl. No. | Category of Maintenance | Date of Approval | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Name of Contractor | At Chainage (m) | Span Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Less/ Above (%) | Elapse Day to Contract | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progress (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Upazila: |  | 1. Gaibandha Sadar
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 2. Gobindaganj
1 | Re-hab._Culvert | 2020-09-02 | 493113 | 1 | 132304079 | 1x3.00mx2.00m RCC Box Culvert on Barsho at Panitola Rd.-Dhanial madrasha Road via Akhira | M/S Shine Traders | 30 | 3 | 983866 | 934672.7 | -5% | 63 |  | 2020-11-04 | 2021-02-03 | 73.63% | 100% | - |  |  | 91 | 67
2 | Re-hab._Culvert | 2020-09-02 | 493114 | 1 | 132305126 | 1x2.00mx2.00m RCC Box Culvert on Panitola-Kamdia road-Dublagari Road | Md. Shamsul Islam | 5 | 2 | 803294 | 763129.3 | -5% | 67 |  | 2020-11-08 | 2021-02-07 | 69.23% | 100% | - |  |  | 91 | 63
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
2 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 5 | 1787160 | 1697802 | -5% |  | 0 | Fin. Pgr. (%) | - |  | 100%
Upazila: |  | 3. Fulchhari
1 | Re-hab._Culvert | 2020-09-02 | 493117 | 1 | 132213013 | 1x1.50mx1.50m RCC Box Culvert on Udakhali UP Office (Near Food Godown) - School Bazar Road | M/S Shamim Ent | 345 | 1.5 | 696929 | 662082.55 | -5% | 73 |  | 2020-11-14 | 2021-02-13 | 62.64% | 0% | Very Slow Progress |  |  | 91 | 57
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
1 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 1.5 | 696929 | 662082.55 | -5% |  | 0 | Fin. Pgr. (%) | - |  | 0%
Upazila: |  | 4. Palashbari
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
Upazila: |  | 5. Sadullapur
1 | CO_Culvert | 2020-08-05 | 380622 | 1 | 132822013 | 1no. Single Vent 4.00mx2.50m RCC Box Culvert on Madarganj GC- Laxmipur GC Road Via Kantanagar | M/s. Tuna Enterprise | 13055 | 4 | 714605 | 714605 | 0% | -200 |  | 2020-01-18 | 2020-04-18 | 393.4% | 100% | - |  |  | 91 | 358
2 | Re-hab._Culvert | 2020-09-02 | 493116 | 1 | 132822004 | 3.00mx2.50m Box Culvert on Jamlarjan-Thutiapukur Road via Pachar Bazar GC (Sadullapur Part: Ch.00m-10050m) Road | Hasan Mahmud Rasel | 4151 | 3 | 1654010 | 1571309.5 | -5% | 74 |  | 2020-11-15 | 2021-02-14 | 61.54% | 30% | - |  |  | 91 | 56
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
2 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 7 | 2368615 | 2285914.5 | -3.492% |  | 0 | Fin. Pgr. (%) | - |  | 51.88%
Upazila: |  | 6. Shaghata
1 | CO_Culvert | 2020-08-05 | 419097 | 1 | 13288008 | 3.00mx4.50mx4.00m RCC Box Culvert on Hodia UP H/Q - Jumarbari H/Q at ch.5935m | M/S Al Rabby Traders | 5935 | 4.5 | 4592285 | 4592285 | 0% | -108 |  | 2020-04-19 | 2020-05-18 | 917.2% | 55% | Time Expired |  |  | 29 | 266
2 | Re-hab._Culvert | 2020-09-02 | 493115 | 1 | 132883004 | 1x3.00mx2.50m RCC Box Culvert on Baltoli FRB-Ullah Bharatkhali UP Road | M/S Galaxy Telecom | 1166 | 3 | 1197548 | 1137670.6 | -5% | 80 |  | 2020-11-21 | 2021-02-20 | 54.95% | 10% | Very Slow Progress |  |  | 91 | 50
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
2 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 7.5 | 5789833 | 5729955.6 | -1.034% |  | 0 | Fin. Pgr. (%) | - |  | 46.07%
Upazila: |  | 7. Sundarganj
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
[12 empty] | - | - |  |  |  | - |  | - |  |  | 0 | -
0 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 0 | 0 | 0 | - |  | 0 | Fin. Pgr. (%) | - |  | 0
7 | Grand Total: |  | 0 |  |  | Not Contacted Amount | 0 |  | 21 | 10642537 | 10375754.65 | -2.507% |  | 0 | Fin. Pgr. (%) | - |  | 53.23% |  |  |  | 15/12
Fund Received: | [17 empty] | Cash in Hand: | 4000000
Date: | 2020-10-27 | [18 empty] | Total:
Tk. | 4000000 | [18 empty] | 4000000
Comments if any:
[14 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  | Amount Required upto June (Tk.) | Remarks
PM_Culvert
Re-hab._Culvert
EM_Culvert
CO_Culvert
1. Gaibandha Sadar
2. Gobindaganj
3. Fulchhari
4. Palashbari
5. Sadullapur
6. Shaghata
7. Sundarganj

## Road
Contract Status of Rural Road Maintenance (GoB Maintenance)
District : |  | Gaibandha | [17 empty] | Date of Reporting: | 2021-01-10
Sl. No. | Category of Maintenance | Date of Approval | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Name of Contractor | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Less/ Above (%) | Elapse Day to Contract | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progress (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila: |  | 1. Gaibandha Sadar
1 | CO Road | 2020-07-26 | 380611 | 1 | 132243016 | Gidari UP Office – Dariapur GC Road | M/s. Logno Enterprise | 5350 | 6350 | 1000 | 876259 | 876259 | 0% | -190 | 876259 | 2020-01-18 | 2020-03-18 | 596.7% | 100% | - | Final Bill Paid |  | 60 | 358
2 | CO Road | 2020-07-26 | 380612 | 1 | 132243024 | Ghagoa UP Office – Gidari UP via Foot Bridge Road | Hazi And Sons | 0 | 500 | 500 | 642728 | 642728 | 0% | -200 | 642728 | 2020-01-08 | 2020-03-07 | 623.7% | 100% | - | Final Bill Paid |  | 59 | 368
3 | CO Road | 2020-07-26 | 380625 | 1 | 132244026 | Madanerpara - Baguria kheyaghat Road | M/S. Anik Traders | 0 | 2612 | 2612 | 371204 | 371204 | 0% | -190 | 362631 | 2020-01-18 | 2020-03-17 | 606.8% | 100% | - | Final Bill Paid |  | 59 | 358
4 | CO Road | 2020-07-26 | 380683 | 1 | 132242006 | Laxmipur-Kamarjani Road | M/S. Ghagot enterprise | 0 | 6000 | 6000 | 1518091 | 1518091 | 0% | -190 | 1512875 | 2020-01-18 | 2020-04-17 | 397.8% | 100% | - | Final Bill Paid |  | 90 | 358
5 | CO Road | 2020-07-26 | 419098 | 1 | 132242001 | Gaibandha-Laxmipur Road | M/S Tahity Enterprise, Rangpur | 0 | 5750 | 5750 | 18778366 | 18778366 | 0% | -34 | 18777851 | 2020-06-22 | 2020-10-02 | 198% | 100% | - | Final Bill Paid |  | 102 | 202
6 | CO Road | 2020-07-26 | 419099 | 1 | 132242001 | Gaibandha-Laxmipur Road | M/S Tahity & ZHD (JV), Goshpara, Sadar, Kurigram | 5750 | 10000 | 4250 | 18463933 | 18463933 | 0% | -34 | 18451961 | 2020-06-22 | 2020-10-22 | 165.6% | 100% | - | Final Bill Paid |  | 122 | 202
[8 empty] | 10300 | 11762 | 1462 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
7 | CO Road | 2020-07-26 | 419100 | 1 | 132242001 | Gaibandha-Laxmipur Road | Pradeep kumar sarker gaibandha | 10000 | 10300 | 300 | 6073400 | 6073400 | 0% | -96 | 6073400 | 2020-04-21 | 2020-07-14 | 314.3% | 100% | - |  |  | 84 | 264
8 | Re-Seal | 2020-09-02 | 493098 | 1 | 132243004 | Badiakhali UP Office –Chalkbarul Bazar Road | Mony Enterprise | 0 | 2500 | 2500 | 5618411 | 5337490.45 | -5% | 76 |  | 2020-11-17 | 2021-02-01 | 71.05% | 15% | Progress Slow |  |  | 76 | 54
9 | Over-Lay | 2020-09-02 | 493099 | 1 | 132242010 | Tulshi ghat-Pacherbazar GC via Khur Dokomurpur Bazar Road | Icon Construction & Builders | 0 | 2000 | 2000 | 6544416 | 6217195.2 | -5% | 68 |  | 2020-11-09 | 23-01-21 | 82.67% | 95% | - |  |  | 75 | 62
10 | Over-Lay | 2020-09-02 | 495965 | 1 | 132243022 | Ghagoa UP office to Dariapur GC Road | M.S.S Engineering &Construction | 1880 | 3880 | 2000 | 5035771 | 4783982.45 | -5% | 70 |  | 2020-11-11 | 25-01-21 | 80% | 30% | Slow Progress |  |  | 75 | 60
11 | Re-Seal | 2020-09-02 | 492903 | 1 | 132242009 | Tulsighat hat-Ramchandrapur Palli Health Center Road | Satota Traders | 1100 | 3520 | 2420 | 4614532 | 4383805.4 | -5% | 9 | 3500000 | 2020-09-11 | 2021-08-01 | 37.35% | 95% | - |  |  | 324 | 121
12 | Over-Lay | 2020-09-02 | 492965 | 1 | 132244007 | Banglabazar-Nakailhat Road | Md. Abul Kalam Hakkani | 0 | 1865 | 1865 | 4916244 | 4670431.8 | -5% | 63 | 4000000 | 2020-11-04 | 2021-01-03 | 111.7% | 95% | Time Expired |  |  | 60 | 67
13 | Over-Lay | 2020-09-02 | 492969 | 1 | 132245009 | Shapla Dhankal-Shadullahpur R&H Road | M/S Rimon Enterprise | 0 | 805 | 805 | 2021875 | 1920781.25 | -5% | 67 |  | 2020-11-08 | 2021-01-07 | 105% | 90% | Time Expired |  |  | 60 | 63
14 | Over-Lay | 2020-09-02 | 492980 | 1 | 132244036 | Perapur Road-WDB Embk Road | M/S Rakib Traders | 0 | 300 | 300 | 789927 | 750430.65 | -5% | 70 | 750430 | 2020-11-11 | 2021-01-10 | 100% | 100% | - | Final Bill Paid |  | 60 | 60
15 | Over-Lay | 2020-09-02 | 492984 | 1 | 132244005 | R&H Burirghat-Sadullapur Thana Border Road | Md. Abul Kalam Hakkani | 0 | 1000 | 1000 | 3093845 | 2939152.75 | -5% | 63 |  | 2020-11-04 | 2021-01-03 | 111.7% | 40% | Time Expired |  |  | 60 | 67
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
15 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 34.764 | 79359002 | 77727250.95 | -2.056% |  | 54948135 | Fin. Pgr. (%) | 70.69% |  | 86.36%
Upazila: |  | 2. Gobindaganj
1 | CO Road | 2020-07-26 | 380676 | 1 | 132914197 | Panch bibi pucca Road ( Dharmopur) -Anayet pur via Dharmapur Road | M/S. Ovi Arjun Enterprise | 0 | 1405 | 1405 | 2650737 | 2650737 | 0% | -202 | 2649576 | 2020-01-06 | 2020-03-05 | 627.1% | 100% | - | Final Bill Paid |  | 59 | 370
2 | CO Road | 2020-07-26 | 380691 | 1 | 132302001 | Gobindagonj-Mohimagonj Road | M/S. Yanur Traders | 0 | 1500 | 1500 | 4818509 | 4818509 | 0% | -190 | 1480000 | 2020-01-18 | 2020-04-01 | 483.8% | 100% | - |  |  | 74 | 358
3 | CO Road | 2020-07-26 | 380693 | 1 | 132302004 | Kamdia hat GC-Panitala hat GC Road | M/S Das Traders | 4500 | 9016 | 4516 | 1840038 | 1840038 | 0% | -160 | 1838814 | 2020-02-17 | 2020-05-16 | 368.5% | 100% | - | Final Bill Paid |  | 89 | 328
[8 empty] | 10785 | 13000 | 2215 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
4 | CO Road | 2020-07-26 | 380695 | 1 | 132303001 | Mohimagonj U.P-Gobindagonj Road via Sarder hat Road | Md. Azad Construction | 1670 | 5470 | 3800 | 5379354 | 5379354 | 0% | -182 | 3500000 | 2020-01-26 | 2020-04-25 | 388.9% | 100% | - |  |  | 90 | 350
5 | CO Road | 2020-07-26 | 380697 | 1 | 132303001 | Mohimagonj U.P-Gobindagonj Road via Sarder hat Road | Md.Mokaddesh Ali Badu | 5470 | 11768 | 6298 | 14592112 | 14592112 | 0% | -145 | 14552764 | 2020-03-03 | 2020-06-02 | 344% | 100% | - | Final Bill Paid |  | 91 | 313
6 | CO Road | 2020-07-26 | 447301 | 1 | 132303013 | Kamardaha U.P (Fashitola) - Kochashahar hat Road | M/S Momin &Shihab JV | 0 | 6500 | 6500 | 19169458 | 19169458 | 0% | -46 |  | 2020-06-10 | 2020-10-08 | 178.3% | 100% | - |  |  | 120 | 214
7 | Over-Lay | 2020-09-02 | 495967 | 1 | 132302001 | Gobindagonj-Mohimagonj Road | M/S Asraf International | 6450 | 7650 | 1200 | 5910281 | 5614766.95 | -5% | 70 |  | 2020-11-11 | 25-01-21 | 80% | 20% | Critical |  |  | 75 | 60
8 | Re-Hab. Road | 2020-09-02 | 493104 | 1 | 132303025 | Katabari UP-Bagulagari Hat Road | Bikash Garments | 1594 | 2200 | 606 | 5664087 | 5380882.65 | -5% | 67 | 3000000 | 2020-11-08 | 22-01-21 | 84% | 100% | - |  |  | 75 | 63
9 | Over-Lay | 2020-09-02 | 492993 | 1 | 132302001 | Gobindagonj-Mohimagonj Road | M/S Sabbir Traders | 11400 | 12750 | 1350 | 4897496 | 4652621.2 | -5% | 66 | 4000000 | 2020-11-07 | 2021-01-06 | 106.7% | 100% | - |  |  | 60 | 64
10 | Over-Lay | 2020-09-02 | 493081 | 1 | 132304061 | Bailgao - Chalita Kashirchara Road | M/SRozaEnterprise | 2135 | 3150 | 1015 | 2285669 | 2171385.55 | -5% | 74 |  | 15-11-20 | 14-01-21 | 93.33% | 100% | - |  |  | 60 | 56
11 | Over-Lay | 2020-09-02 | 497727 | 1 | 132304203 | Panch Bibi pucca Road-Kamdia bazar via Kamdia Mosque Road | M/S Modina Traders | 0 | 500 | 500 | 1748089 | 1660684.55 | -5% | 90 |  | 2020-12-01 | 31-01-21 | 65.57% | 20% | Progress Slow |  |  | 61 | 40
12 | Over-Lay | 2020-09-02 | 493089 | 1 | 132305014 | Dalimgari-Chatinchura Road | M/S Rashedul Enterprise | 0 | 725 | 725 | 1919169 | 1823210.55 | -5% | 67 |  | 2020-11-08 | 2021-01-07 | 105% | 100% | - |  |  | 60 | 63
13 | Over-Lay | 2020-09-02 | 493090 | 1 | 132304092 | Taraf Kamal (R&H) -Rampura Raod via Rampur RNGPS Road | M/S Ekramul Hoq | 0 | 840 | 840 | 2741783 | 2604693.85 | -5% | 66 | 2300000 | 2020-11-07 | 2021-01-06 | 106.7% | 100% | - |  |  | 60 | 64
14 | Over-Lay | 2020-09-02 | 493091 | 1 | 132304042 | Kamdia-Pachbibi Road to Para via Teroil School Road | M/S Nafi Niloy Traders | 0 | 1500 | 1500 | 3195951 | 3036153.45 | -5% | 68 | 2800000 | 2020-11-09 | 2021-01-08 | 103.3% | 100% | - |  |  | 60 | 62
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
14 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 33.97 | 76812733 | 75394606.75 | -1.846% |  | 36121154 | Fin. Pgr. (%) | 47.91% |  | 92.28%
Upazila: |  | 3. Fulchhari
1 | Over-Lay | 2020-09-02 | 495963 | 1 | 132212002 | Gunvary GC-Badiakhali R&H Road | M/S Nannu Enterprise | 0 | 6350 | 6350 | 14808204 | 14067793.8 | -5% | 70 |  | 2020-11-11 | 2021-03-10 | 50.42% | 60% | - |  |  | 119 | 60
2 | Over-Lay | 2020-09-02 | 495966 | 1 | 132212001 | Fulchari Upa-zila H/Q Gunvary GC Road | M/S Pumpa | 0 | 3770 | 3770 | 6675966 | 6342167.7 | -5% | 80 |  | 21-11-20 | 2021-02-05 | 65.79% | 40% | - |  |  | 76 | 50
3 | Re-Seal | 2020-09-02 | 492914 | 1 | 132213013 | Udakhali UP office (Near Food godown) - School Bazar Road | Md. Ansar Ali | 0 | 1210 | 1210 | 2970287 | 2821772.65 | -5% | 67 |  | 2020-11-08 | 2021-01-07 | 105% | 10% | Time Expired |  |  | 60 | 63
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
3 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 11.33 | 24454457 | 23231734.15 | -5% |  | 0 | Fin. Pgr. (%) | - |  | 48.47%
Upazila: |  | 4. Palashbari
1 | CO Road | 2020-07-26 | 380601 | 1 | 132672003 | Tulshighat GC-Nakihat GC Road | Hazi And Sons | 1630 | 4000 | 2370 | 845596 | 845596 | 0% | -200 | 843303 | 2020-01-08 | 2020-03-07 | 623.7% | 100% | - |  |  | 59 | 368
2 | CO Road | 2020-07-26 | 380604 | 1 | 132674033 | Rangpur Bogra - NHW -college Road | M/S. Razin Traders | 0 | 700 | 700 | 1228861 | 1228861 | 0% | -190 |  | 2020-01-18 | 2020-03-18 | 596.7% | 90% | Time Expired |  |  | 60 | 358
3 | CO Road | 2020-07-26 | 380685 | 1 | 132672001 | Palashbari Upazila H/Q-Fakirhat GC Road | M/s, Khondoker Enterprise | 8300 | 12200 | 3900 | 6122995 | 6122995 | 0% | -193 | 6115510 | 2020-01-15 | 2020-04-15 | 396.7% | 100% | - | Final Bill Paid |  | 91 | 361
4 | CO Road | 2020-07-26 | 380682 | 1 | 132673004 | Barishal UP Office-Ratter Bazer Sluice Gate Road | M/s. utsa Enteprise | 0 | 4380 | 4380 | 1022864 | 1022864 | 0% | -190 | 987831 | 2020-01-18 | 2020-04-02 | 477.3% | 100% | - | Final Bill Paid |  | 75 | 358
5 | CO Road | 2020-07-26 | 380684 | 1 | 132673017 | Harinathpur UP Office – Kazir Bazar Road via Kumidpur Bazar Road | MS Sazzad Hossain | 2195 | 4280 | 2085 | 1539031 | 1539031 | 0% | -193 | 1538693 | 2020-01-15 | 2020-03-15 | 601.7% | 100% | - | Final Bill Paid |  | 60 | 361
6 | Re-Seal | 2020-09-02 | 493106 | 1 | 132673010 | Kalibari GC-Idilpur UP office via Ambari Road | M/S Shahrial Construction | 0 | 1060 | 1060 | 8535587 | 8108807.65 | -5% | 74 |  | 15-11-20 | 14-02-21 | 61.54% | 25% | Progress Slow |  |  | 91 | 56
7 | Re-Seal | 2020-09-02 | 492918 | 1 | 132672004 | Palashbari Upazila H/Q-Chattra GC Road via Kishorgari UP Office Road | Md. Abu Sayid Mahabub | 0 | 2100 | 2100 | 4142012 | 3934911.4 | -5% | 74 |  | 15-11-20 | 14-01-21 | 93.33% | 25% | Critical |  |  | 60 | 56
8 | Re-Seal | 2020-09-02 | 492924 | 1 | 132672006 | Thutiapukur RHW-Pachabazar GC Road | M/S Ekramul Hoq | 0 | 1235 | 1235 | 2160923 | 2052876.85 | -5% | 66 |  | 2020-11-07 | 2021-01-06 | 106.7% | 90% | Time Expired |  |  | 60 | 64
9 | Re-Seal | 2020-09-02 | 492932 | 1 | 132673019 | Harinathpur UP office-Miabazar Road | Md. Anisur Rahman | 0 | 2000 | 2000 | 3256315 | 3093499.25 | -5% | 74 |  | 15-11-20 | 14-01-21 | 93.33% | 30% | Slow Progress |  |  | 60 | 56
10 | Re-Seal | 2020-09-02 | 492962 | 1 | 132674039 | Pabnapur MP House- Talukgorabandha via Charerhat Road | M/S Ohi Enterprise | 0 | 1160 | 1160 | 2785478 | 2646204.1 | -5% | 68 |  | 2020-11-09 | 2021-01-08 | 103.3% | 40% | Time Expired |  |  | 60 | 62
11 | Over-Lay | 2020-09-02 | 493092 | 1 | 132673018 | Horinathpur UP office-Harinabari Bazar Road | M/S Hiru Traders | 0 | 1240 | 1240 | 3060372 | 2907353.4 | -5% | 74 |  | 15-11-20 | 14-01-21 | 93.33% | 60% | - |  |  | 60 | 56
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
11 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 22.23 | 34700034 | 33502999.65 | -3.45% |  | 9485337 | Fin. Pgr. (%) | 28.31% |  | 57.39%
Upazila: |  | 5. Sadullapur
1 | CO Road | 2020-07-26 | 380686 | 1 | 132822013 | Madarganj GC - Luxmipur GC via Kantanagar Road | Md. Khademul Islam Jewel | 10443 | 16390 | 5947 | 14915844 | 14915844 | 0% | -168 |  | 2020-02-09 | 2020-06-09 | 277.7% | 100% | - |  |  | 121 | 336
2 | CO Road | 2020-07-26 | 380703 | 1 | 132822007 | Bamondanga GC - Naldanga GC Road | M/S. Utsa Enterprise | 0 | 1110 | 1110 | 11548622 | 11548622 | 0% | -181 |  | 2020-01-27 | 2020-05-22 | 300.9% | 40% | Time Expired | RHD Transfer |  | 116 | 349
3 | Over-Lay | 2020-09-02 | 495971 | 1 | 132822008 | Sadullapur-Tulshighat Road | M/S Kabbo Enterprise | 0 | 5700 | 5700 | 11909586 | 11314106.7 | -5% | 70 |  | 2020-11-11 | 2021-03-10 | 50.42% | 50% | - |  |  | 119 | 60
4 | Re-Seal | 2020-09-02 | 492936 | 1 | 132822004 | Jamlarjan-Thutiapukur Road via Pachar Bazar GC (Sadullapur Part:Ch.00m-10050m) Road | M/S Vai vai Traders | 2215 | 4244 | 2029 | 3808359 | 3617941.05 | -5% | 67 |  | 2020-11-08 | 2021-01-07 | 105% | 50% | Time Expired |  |  | 60 | 63
5 | Re-Seal | 2020-09-02 | 492951 | 1 | 132823005 | Kamrapara UP Office-Sadullapur Naldanga Road | M/S Nannu Enterprise | 0 | 1000 | 1000 | 1829719 | 1738233.05 | -5% | 70 |  | 2020-11-11 | 2021-01-10 | 100% | 20% | Critical |  |  | 60 | 60
6 | Widening Road | 2020-09-02 | 493097 | 1 | 132824019 | Sadullapur-Naldanga Road from Garmin Bank Road | Md. Shheb Hossain Mona | 1045 | 1542 | 497 | 2199127 | 2089170.65 | -5% | 63 |  | 2020-11-04 | 2021-01-03 | 111.7% | 90% | Time Expired |  |  | 60 | 67
7 | EM Road | 2020-10-27 |  | 1 | 132825009 | Sadullahpur Naldanga Road - Kismat Khejur via Maruadaha | M/S Mafi Const, Sadullapur | 125 | 200 | 75 | 498218 | 497668 | -0.1104% | 51 | 497668 | 2020-12-17 | 2020-01-16 | -7.143% | 100% | - | Final Bill Paid |  | -336 | 24
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
7 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 16.358 | 46709475 | 45721585.45 | -2.115% |  | 497668 | Fin. Pgr. (%) | 1.088% |  | 65.02%
Upazila: |  | 6. Shaghata
1 | CO Road | 2020-07-26 | 380696 | 1 | 132882001 | Badiakhali Bridge R&H - Jumarbari Hat GC Road | M/S Shammi Builders | 0 | 5328 | 5328 | 4123595 | 4123595 | 0% | -168 | 4116102 | 2020-02-09 | 2020-06-09 | 277.7% | 100% | - | Final Bill Paid |  | 121 | 336
2 | CO Road | 2020-07-26 | 380698 | 1 | 132882001 | Badiakhali Bridge R&H-Jumarbari Hat GC Road | M/S. Milon Enterprise | 15302 | 16400 | 1098 | 2838802 | 2838802 | 0% | -190 | 2685316 | 2020-01-18 | 2020-04-18 | 393.4% | 100% | - | Final Bill Paid |  | 91 | 358
3 | CO Road | 2020-07-26 | 380700 | 1 | 132883004 | Baltoli FRB-Ullah Bharatkhali UP Road | M/s. Autul Enterprise | 0 | 3897 | 3897 | 2196492 | 2196492 | 0% | -181 | 2185171 | 2020-01-27 | 2020-03-22 | 634.5% | 100% | - | Final Bill Paid |  | 55 | 349
4 | CO Road | 2020-07-26 | 380702 | 1 | 132882007 | Bharatkhali R&H-Nayabondar-Badiakhali GC Road | Md. Touhidul Islam JV | 0 | 3970 | 3970 | 1703006 | 1703006 | 0% | -155 | 1667750 | 2020-02-22 | 2020-05-15 | 389.2% | 100% | - | Final Bill Paid |  | 83 | 323
5 | CO Road | 2020-07-26 | 419096 | 1 | 132883008 | Holdia UP - Jumarbari H/Q | M/S Naz Traders | 4425 | 6496 | 2071 | 2861703 | 2861703 | 0% | -104 |  | 2020-04-13 | 2020-05-18 | 777.1% | 15% | Time Expired |  |  | 35 | 272
6 | Over-Lay | 2020-09-02 | 495969 |  | 132882004 | Bonarapar GC-Mohimaganj GC Road | Nazib Traders | 440 | 4000 | 3560 | 12273719 | 11660033.05 | -5% | 76 |  | 17-11-20 | 17-03-21 | 45% | 25% | - |  |  | 120 | 54
7 | Over-Lay | 2020-09-02 | 495970 |  | 132882004 | Bonarapar GC-Mohimaganj GC Road | M/S Sadia & Brothers | 4000 | 7640 | 3640 | 10813507 | 10272831.65 | -5% | 74 |  | 15-11-20 | 2021-03-15 | 46.67% | 45% | - |  |  | 120 | 56
8 | Re-Hab. Road | 2020-09-02 | 493111 |  | 132883001 | Saghata GC-Kachua UP Office via Ullah Sonatala Bazar Road | M/S Zaman Construction | 2450 | 4674 | 2224 | 8423346 | 8002178.7 | -5% | 67 |  | 2020-11-08 | 2021-02-07 | 69.23% | 40% | - |  |  | 91 | 63
9 | Re-Hab. Road | 2020-09-02 | 493112 |  | 132883019 | Barokona Bazar(Badiakhali Bridge R&H-Jumarbari GCCR at hapania)-Mohimagonj UP Office Via Satitala | Md. Touhidul Islam | 0 | 1328 | 1328 | 8832299 | 8390684.05 | -5% | 68 |  | 2020-11-09 | 2021-02-08 | 68.13% | 35% | - |  |  | 91 | 62
[8 empty] | 2820 | 4252 | 1432 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
10 | Widening Road | 2020-09-02 | 493105 |  | 132884019 | Mandura-Bharatkhali Road | M/S Joy Bijoy Enterprise | 1280 | 2800 | 1520 | 5568797 | 5290357.15 | -5% | #VALUE! |  | 17-11-20 | 2021-02-01 | #VALUE! | 20% | #VALUE! |  |  | #VALUE! | #VALUE!
11 | Over-Lay | 2020-09-02 | 493095 |  | 132885058 | Badiakhali Jumarbari GCCR-Futani Bazar Road | M/S Ovi Alif Enterprise | 0 | 457 | 457 | 1288889 | 1224444.55 | -5% | #VALUE! |  | 15-11-20 | 14-01-21 | #VALUE! | 20% | #VALUE! |  |  | #VALUE! | #VALUE!
12 | Re-Hab. Road | 2020-09-02 | 493096 |  | 132885154 | Bonarpara GC-Katucha hat R&H Rd. at H/O Samsul- Centerl Shaid Minnar Road | Golden Construction | 0 | 400 | 400 | 3101159 | 2946101.05 | -5% | 80 |  | 21-11-20 | 20-01-21 | 83.33% | 70% | - |  |  | 60 | 50
13 | EM Road | 2020-11-02 |  |  | 132882001 | Badiakhali Bridge R&H - Hapania Road | Md. Touhidul Islam | 9 | 25 | 16 | 311166 | 310666 | -0.1607% | 45 | 310165 | 2020-12-17 | 2021-01-15 | 82.76% | 100% | - | Final Bill Paid |  | 29 | 24
[8 empty] | 0 |  | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
13 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 30.941 | 64336480 | 61820894.2 | -3.91% |  | 10964504 | Fin. Pgr. (%) | 17.74% |  | 46.33%
Upazila: |  | 7. Sundarganj
1 | Over-Lay | 2020-09-02 | 493093 |  | 132915014 | WAPDA Embankment – Pachpir Hat Road | Md. Mahomudun Nobi | 0 | 1380 | 1380 | 4352845 | 4135202.75 | -5% | 70 |  | 2020-11-11 | 2021-01-10 | 100% | 40% | Slow Progress |  |  | 60 | 60
2 | Over-Lay | 2020-09-02 | 493094 |  | 132915053 | Chicha Pacca Road(Near H/O Rahaman Member)-Dulal Mouza Road | Md.Touhidul Islam | 0 | 736 | 736 | 2626018 | 2494717.1 | -5% | 68 |  | 2020-11-09 | 2021-01-08 | 103.3% | 100% | - |  |  | 60 | 62
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
-
2 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 2.116 | 6978863 | 6629919.85 | -5% |  | 0 | Fin. Pgr. (%) | - |  | 62.58%
District Office
1 | Off-Pavement | 2020-06-25 |  |  |  | LCS |  | 0 | 325000 | 325000 | 25050000 | 17886325 | -28.6% | 6 | 6826961 | 2020-07-01 | 2021-06-30 | 53.02% | 60% | - |  |  | 364 | 193
2 | On-Pavement | 2020-06-25 | 481678 |  |  | On Pavement Routine Maintenance at 7 Upazilas Part-A. Supplying of Emulsion Bricks Stone Chips Sand Gunny Bags Bamboos Cement etc. For On-pavement Routine Maintenance under Gaibandha District. | M/S MOHIMA ENTERPRISE | 0 | 100000 | 100000 | 3000000 | 2874995.6 | -4.167% | 77 | 491700 | 2020-09-10 | 2021-06-30 | 41.64% | 65% | - |  |  | 293 | 122
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
[10 empty] | 0 |  |  | - | - |  |  |  | - |  | - |  |  | 0 | -
2 | Sub-Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 425 | 28050000 | 20761320.6 | -25.98% |  | 7318661 | Fin. Pgr. (%) | 35.25% |  | 60.69%
65 | Grand Total: |  | 0 |  |  | Not Contacted Amount | 0 |  |  | 576.709 | 361401044 | 344790311.6 | -4.596% |  | 119335459 | Fin. Pgr. (%) | 34.61% |  | 70.27% |  |  |  | 15/12
Fund Received: | [18 empty] | Cash in Hand: | 664541
Date: | 2020-08-03 |  |  | 2020-12-07 | [16 empty] | Total:
Tk. | 90000000 |  |  | 30000000 | [16 empty] | 120000000
Comments if any:
[15 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  | Amount Required upto June (Tk.) | Remarks
Money need
Re-Seal
Over-Lay
Re-Hab. Road
Widening Road
EM Road
CO Road
CO Structure
Off-Pavement
On-Pavement
1. Gaibandha Sadar
2. Gobindaganj
3. Fulchhari
4. Palashbari
5. Sadullapur
6. Shaghata
7. Sundarganj