## Civil Works
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
[41 empty] | 100 | 2021-01-10
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks | Gap between Bank Per. Security and Completion date | DPP Length | DPP Cost | Total Contract days | daily target | Days spent till now |  | Targeted progress | Achived Progress | Gap Between achivement
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
| 2018-19 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/GAI-S/UNR/ 18-19/W-06 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3600m-4150m & 4496m-7600m. including Costruction of 10 U- drain (.600mx0.625m) Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3660m, 3984m, 4030m, 4073m, 5197m, 6115m, 6280m, 6695m, 7525m & 7591m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | M/S Basundhara, Kurigram | 3600.00 4496.00 | 4150.00 7600.00 | 3.654 | 6 | 29444723.57 | 991093.47 | 30435817.04 | 29438902.5 | 991097.41 | 30429999.91 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-04-21 |  | 2020-12-31 | 75% | 12094800 | 2302600 | 14397400 | 1934341 | 368259 | 2302600 | 16700000 | 54.88% | 1500m WBM Complete. 1200m AS Complete. ISG on going | 254 | 4 | 367.364 | 352 | 0.28409 | 616 | 175% | 100% | 75% | 25%
| 2020-21 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/SAD/UNR/ 20-21/W-136 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.7627m-8057m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | MD. SHAHID RANA JV | 7627 | 8057 | 0.43 |  | 4238910 |  | 4238910 |  |  | 3353774.307 |  |  | 2020-11-10 | 2020-11-24 | 2020-11-30 | 2021-11-29 |  | 2021-12-29 | 20%
| 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-09 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.0.00m-2000m. including Costruction of 7 Nos U-Drain khorda Rasulpur-Chandiapur Road at Ch.85m, 526m, 880m, 925m, 1048m, 1343m, & 1835m. and 1Nos (2.00x2.00) m Cross Drainges Structure under khorda Rasulpur-Chandiapur Road at Ch.710.0m. Under Shdullapur, District Gaibandha. | Md.Khademul Islam Jewel, Gaibandha | 0 | 2000 | 2 | 6.2 | 16764810.71 | 1868067 | 18632877.71 | 17548454.17 | 1064613.71 | 18613067.88 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-09-17 |  | 2020-10-15 | 100% | 12173900 | 2288050 | 14461950 | 1926054 | 361996 | 2288050 | 16750000 | 89.99% | Work Complete | 28 | 2 | 183.682 | 501 | 0.1996 | 616 | 123% | 100% | 100% | 0%
2: 2019-20; 3: Gaibandha; 4: Shadullapur; 5: Union Road-BC; 6: PRO/GAI/SAD/UNR/18-19/W-69; 7: 132823001; 8: Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.2000m-4000m. including 6Nos (0.625x0.600) m U-Drain on Khorda Rasulpur-Chandiapur Road at Ch: 2920m,2953m,3089m,3393m, 3582m & 3743m and 1x2.00mx2.00 m RCC Box Culvert at Ch: 2645m under khorda Rasulpur-Chandiapur Road under Shdullapur, District Gaibandha.; 37: package holded | [8 empty] | 0% | 0%
| 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-10 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.1235m-3235. including Costruction of 1 Nos U-Drain 0.600mx0.625m Mohisbandi-Mirpur Road at Ch.2725.0m.Under Shdullapur, District Gaibandha. | M/S SAJIN TRADERS JV | 1235 | 3235 | 2 | 0.6 | 17379171 | 145336 | 17524507 | 17391992.65 | 127964.94 | 17519957.59 |  |  | 2019-04-18 | 2019-05-08 | 2019-05-14 | 2020-03-21 |  | 2020-04-19 | 100% | 9841196 | 2228152 | 12069348 | 1840948 | 387204 | 2228152 | 14297500 | 81.61% | Work Completed | 29 | 2 | 183.682 | 318 | 0.31447 | 613 | 192.8% | 100% | 100% | 0%
2: 2019-20; 3: Gaibandha; 4: Shadullapur; 5: Union Road-BC; 6: PRO/GAI/SAD/UNR/18-19/W-70; 7: 132823002; 8: Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.0m-1250m. including Costruction of 2Nos (0.625x0.600) m U-Drain on Mohishbandhi-Mirpur Road at Ch: 52m & 946m Under Shdullapur, District Gaibandha.; 37: package holded | [8 empty] | 0% | 0%
| 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-12 | 132823017 | Improvement of Bituminous Road on Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. Ch.2627m-3627m. including Costruction of 2 Nos U-Drain 0.600mx0.625m ,at Ch.2768m,3110m and Costruction of 1 Nos (2.00mx2.00m)Cross Drainges Structure and Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. 3260.0mUnder Shdullapur, District Gaibandha. | Md. Mahomudun Nobi, Pirganj, Rangpur | 2627 | 3627 | 1 | 3.6 | 7673417 | 1106313 | 8779730 | 7289746.1 | 1050997.35 | 8340743.45 |  |  | 2019-03-21 | 2019-04-07 | 2019-04-13 | 2020-03-08 |  | 2020-03-31 | 100% | 5511343.59 | 1203622.41 | 6714966 | 1000461.77 | 203130.23 | 1203592 | 7918558 | 94.94% | Final Bill Paid | 23 | 1 | 91.841 | 336 | 0.29762 | 644 | 191.7% | 100% | 100% | 0%
2: 2020-21; 3: Gaibandha; 4: Saghata; 5: Union Road-BC; 6: PRO/GAI/SAG/UNR/20-21/W-135; 7: 132883015; 8: Improvement of Bhangamora Bazar-School bazar – Padumshahor UP Road at Ch: 3526m-6386m Under Upazila:Saghata, District: Gaibandha.; 9: Md.Shamim Ahammed Mondal JV; 10: 3526; 11: 6386; 12: 2.86; 14: 26773265; 16=14+15: 26773265; 19=17+18: 26690000.17; 22: 2020-11-10; 23: 2020-11-23; 24: 2020-11-29; 25: 2021-11-28; 27: 2021-11-30; 28: 10%; 37: NOA Issued |  | 2.85 | 261.7468 |  | 0.27027 | 48 | 12.97% |  |  | 0%
3: Gaibandha; 4: Fulchori; 5: Union Road-BC; 7: 132213003; 8: Erandabari U.P H/Q-Algarchar bazar |  | 1.08 | 99.1883 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Union Road-BC; 7: 132213011; 8: Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S |  | 2.5 | 229.6025 | [6 empty] | 0%
| 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 71 | 132823004 | Improvement of Bhatgram UP office –Jamalpur Bazar Road at Ch: 00m-2000m including Construction of 11 Nos (0.625x0.600) m U-Drain at Ch: 45m, 320m, 472m, 775m, 800m,1265m, 1360m, 1430m, 1550m, 1785m &1919m and 1x2.50mx2.00 m RCC Box Culvert on at Ch: 1275m Under Upazila:Sadullapur, District: Gaibandha | M/S Mafi Construction Sadullapur, Gaibandha | 0 | 2000 | 2 | 14.3 | 16679589 | 2485578 | 19165167 | 14006744.15 | 2283645.85 | 16290390 |  |  | 2020-05-11 | 2020-05-18 | 2020-05-28 | 2021-05-28 |  | 2022-05-17 | 70% | 7281690 | 1609155 | 8890845 | 1317914 | 291241 | 1609155 | 10500000 |  | ISG on going |  | 2 | 183.682 | [6 empty] | 0%
| 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 68 | 132823009 | Improvement of Naldanga GC-Ramzibon UP officeRoad at Ch: 1500m-2500m including Construction of 1Nos (0.625x0.600) m U-Drain Under Upazila:Sadullapur, District:Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 1500 | 2500 | 1 | 1 | 9588269 | 164366 | 9752635 | 8126474.979 |  | 8126474.979 |  |  | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 |  | 2021-05-13 | 90% | 4717796 | 899500 | 5617296 | 755463 | 144037 | 899500 | 6516796 | 80.19% | WBM Running |  | 1 | 91.841 | [6 empty] | 0%
| 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 72 | 132823015 | Improvement of Dholvanga-Mohipur Bazar Road at Ch: 00m-1000m including Construction of 2 Nos (0.625x0.600) m U-Drain at Ch: 355m & 388m and 1x2.50mx2.00 m RCC Box Culvert at Ch: 330m Under Upazila:Sadullapur, District: Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 0 | 1000 | 1 | 5.3 | 9822898 | 1226329 | 11049227 | 9095523.665 |  | 9095523.665 |  |  | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 |  | 2021-05-13 | 30% | 707634 | 134472 | 842106 | 112999 | 21473 | 134472 | 976578 | 10.74% | Cross Drain & Pallisiding work Complete |  | 1 | 91.841 | [6 empty] | 0%
3: Gaibandha; 4: Sadar; 5: Village Road-BC; 7: 132244025; 8: Jugir ghat-Badsharghat Road. |  | 2.9 | 250.6215 | [6 empty] | 0%
3: Gaibandha; 4: Sadar; 5: Village Road-BC; 7: 132245056; 8: Salam bazar- Balayata bazar via Mouza malibari Edghah |  | 2.5 | 216.053 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Village Road-BC; 7: 132884061; 8: Trimohoni Khayaghat-Ullasonatola bazar Rd. |  | 3 | 259.2636 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Village Road-BC; 7: 132884024; 8: Durgapur Sazahan Ali Govt. primary School - Pass Durgapur Govt. Primary School |  | 2.2 | 190.1266 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Village Road-BC; 7: 132884038; 8: Boliarber GPS - Kamalerpara- Falia Pucca road |  | 2.38 | 205.6825 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-BC; 7: 132914077; 8: Shaker Bazar-Wapda Embankment via Baraikandi road |  | 4 | 345.6848 | [6 empty] | 0%
| 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI/GAI-S/VR/18-19/W-07 | 132244011 | Improvement of Bituminous Carpeting Road on Fulbari-Badiakhali hat Road At Ch0.00m-1623m. &2300m-3100m. including Costruction of 10 U- drain (0.600mx0.625m) Fulbari-Badiakhali hat Road atCh0.00m-1623m. &2300m-3100m. Under Gaibandha Sadar Upazila, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 2300 | 1623 3100 | 2.423 | 6 | 22031940.04 | 1000431.53 | 23032371.57 | 22027478.06 | 1000435.54 | 23027913.6 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-03-24 |  | 2020-12-31 | 95% | 11900400 | 2349800 | 14250200 | 1962327 | 387473 | 2349800 | 16600000 | 72.09% | WBM Complete. Mobilization for Carpeting. | 282 | 3.5 | 302.4742 | 324 | 0.30864 | 616 | 190.1% | 100% | 95% | 5%
| 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI /GAI-S/VR/18-19/W-08 | 132244021 | Improvement of Bituminous Carpeting Road on Ruper –Eslighat via Pramanik para Road at Ch.1500m-2980m including Costruction of 3 U- drain (0.600mX0.625m) at Ch.1280m,2300m,2640m. Under Gaibandha Sadar Upazila, District Gaibandha. | RSL Enterprise, gaibandha | 1500 | 2980 | 1.48 | 1.8 | 16529257.77 | 302110 | 16831367.77 | 16518512.1 | 302111.17 | 16820623.27 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-04-21 |  | 2020-04-23 | 100% | 11472451 | 2253310 | 13725761 | 1904749 | 348561 | 2253310 | 15979071 | 95% | Final Bill Paid | 2 | 3 | 259.2636 | 352 | 0.28409 | 616 | 175% | 100% | 100% | 0%
| 2018-19 | Gaibandha | Shadullapur | Village Road-BC | PRO/GAI/SAD/VR/18-19/W-11 | 132824014 | Improvement of Bituminous Road on Shdullapur Dhaperhat G.C road at Boxigonj Bazar toDhaperhat-Madarhat Road via Ambagan Road at Ch.0.00m-2480m. including Costruction of 11 Nos U-Drain 0.600mx0.625m at Ch.335m,720m,877m,1190m,1300m,1388m,1477m,1765m,1880m,1972m,&2226m. Under Shdullapur, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 | 2480 | 2.48 | 6.6 | 20485874 | 1361706 | 21847580 | 20563288.22 | 1361711.78 | 21925000 |  |  | 2019-04-18 | 2019-05-15 | 2019-05-21 | 2020-05-02 |  | 2020-07-31 | 100% | 13273661 | 2504677 | 15778338 | 2107080 | 397597 | 2504677 | 18283015 | 83.39% | Work Complete | 90 | 2.48 | 214.3246 | 353 | 0.28329 | 606 | 171.7% | 100% | 100% | 0%
| 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-13 | 132885163 | Improvement of Bituminous Road on Gatia H/O Taibor Master-Chitholia H/O Mahatab Member Road at Ch.0.00m-800m. including Costruction of 4 Nos U-Drain 0.600mx0.625m at Ch20m,135m,290m,&700m Under Saghata, District Gaibandha. | Md. Jakir Hossain, Gaibandha | 0 | 800 | 0.8 | 2.4 | 7459743 | 304702 | 7764445 | 7086755.8 | 282523.35 | 7369279.15 |  |  | 2019-03-21 | 2019-04-15 | 2019-04-21 | 2020-04-06 |  | 2019-12-29 | 100% | 5007817 | 994738 | 6002555 | 839420 | 155318 | 994738 | 6997293 | 94.95% | Final Bill Paid | -99 | 0.8 | 69.137 | 357 | 0.28011 | 636 | 178.2% | 100% | 100% | 0%
| 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-14 | 132884002 | Improvement of Bituminous Road on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Road at ch.600m-2930m. including Costruction of 10 Nos U-Drain 0.600mx0.625m at Ch.673m,735m,816m,925m,1387m,1760m,1920m,1987m,2150m,2493m.and Costruction of 3 Nos Slope Drain at Ch.1496m, 1745m, 2075m, and Costruction of 3 Nos (2.00mx2.00m) Cross Drainges Structure on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Roadat Ch.2395m,2590m, 2787m. Under Saghata, District Gaibandha. | M/S SAJIN TRADERS JV | 600 | 2930 | 2.33 | 22.5 | 18252469 | 3310465 | 21562934 | 20694775 | 853394.34 | 21548169.34 |  |  | 2019-04-18 | 2019-05-07 | 2019-05-13 | 2020-03-25 |  | 2020-04-23 | 100% | 11038037 | 2243231 | 13281268 | 1842848 | 400383 | 2243231 | 15524499 | 72.05% | Work Completed. | 29 | 2.85 | 246.3004 | 323 | 0.3096 | 614 | 190.1% | 100% | 100% | 0%
2: 2019-20; 3: Gaibandha; 4: Sadar; 5: Maintenance-LCS; 6: PRO/GAI/GAI_S/RMP/19-20/ MW-114; 7: 132245158; 8: Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Salam bazar- Balata bazar via Mouja malibari Eidgah at ch. 00-2500m; 10: 0; 11: 2500; 12: 2.5; 16=14+15: 1331224.49; 19=17+18: 1281224.49; 23: 2020-09-15; 25: 2022-09-14; 28: 10%; 31=29+30: 75200; 35=31+33: 75200; 37: LCS team Work on going, |  |  |  | 729 | 0.13717 | 117 | 16.05% | 16.05%
| 2019-20 | Gaibandha | Shadullapur | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-115 | 132823009 132823008 132823001 132823004 132823006 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Naldanga G.C.-Ramzibon U.P. office. Road at ch. 00-780m. 2. Idilpur U.P. office-Dhaperhat U.P. office road at ch. 00-2000m. 3. Khorda Rasulpur-chandiapur roadat ch. 00-1020m. 4. Bhatgram U.P office-Jamalpur Bazar at ch.00-2000m. 5 Chandiapur bazar-Rahmatpur GC via Rasulpur bazar at ch.00-2000m. |  | 0.00 0.00 0.00 0.00 0.00 | 780 2000 1020 2000 2000 | 7.8 |  |  |  | 3639329.09 |  |  | 3483329.08 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 15% |  |  | 198850 |  |  |  | 198850 | 0% | LCS team Work on going,
| 2019-20 | Gaibandha | Saghata | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-116 | 132885022 132885175 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Dighal Kandi- Digholkandi H/O Sonaullah Mirja at ch.00-2700m. 2. Chakili H/O Vikku sarker - Folia Bazar road at ch. 00-1900m. |  | 0.00 0.00 | 2700 1900 | 4.6 |  |  |  | 2374181.13 |  |  | 2282181.12 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% |  |  | 128350 |  |  |  | 128350 | 0% | LCS team Work on going,
| 2019-20 | Gaibandha | Fulchori | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-117 | 132213003 132213011 132214050 132215025 132215037 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Erandabari U.P H/Q-Algarchar bazar at ch.1170-2250m. 2. Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S at ch.00-2500m. 3. Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram at ch.1170-2000m. 4. Pachim Khatiamary H/O Jalal Member-Gucha gram at ch.00-1000m. 5 Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary at ch.00-950m. |  | 1170 0.00 1170 0.00 0.00 | 2250 2500 2000 1000 950 | 6.36 |  |  |  | 3210146.42 |  |  | 3082946.43 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 20% |  |  | 175350 |  |  |  | 175350 | 0% | LCS team Work on going
3: Gaibandha; 4: Saghata; 5: Village Road-HBB; 7: 132885022; 8: Dighal Kandi- Digholkandi H/O Sonaullah Mirja; 35=31+33: 75200 |  | 3.2 | 185.472 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Village Road-HBB; 7: 132214036; 8: Fulchari Kheyaghat-Tengrakandi Road |  | 1.6 | 92.736 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Village Road-HBB; 7: 132214050; 8: Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram |  | 0.83 | 48.1068 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Village Road-HBB; 7: 132215025; 8: Pachim Khatiamary H/O Jalal Member-Gucha gram |  | 1 | 57.96 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Village Road-HBB; 7: 132215037; 8: Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary |  | 0.95 | 55.062 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-HBB; 7: 132915057; 8: Ramdakua- Akotar Bazar |  | 0.5 | 28.98 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-HBB; 7: 132915057; 8: Kashem Bazar- Karent Bazar |  | 0.5 | 28.98 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-HBB; 7: 132915057; 8: Kashem Bazar- Mondoler hat |  | 0.5 | 28.98 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-HBB; 7: 132915057; 8: Kashem Bazar- Hazari hat |  | 1 | 57.96 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-HBB; 7: 132915058; 8: Koshim Bazar- Kagia Char Ahmed Nagar Bazar |  | 1 | 57.96 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Village Road-HBB; 7: 132915058; 8: Koshim Bazar-Vati Kapasia Nuton Asraon Bazar |  | 1.41 | 81.7236 | [6 empty] | 0%
| 2019-20 | Gaibandha | Sundargonj | Maintenance-LCS | PRO/GAI/SUN/RMP/19-20/ MW-113 | 132915058 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Kapashia UP Office to Kashim Bazar- WAPDA Embankment via H/O Nesab Chairman (Kajir Char Ahammed Nagar Bazar) road, at Ch. 00-2300m. |  | 0 | 2300 | 2.3 |  |  |  | 1327224.49 |  |  | 1281224.49 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% |  |  | 75200 |  |  |  | 75200 | 0% | LCS team Work on going,
3: Gaibandha; 4: Fulchori; 5: Large Market; 8: Purbo Fulchari Bazar |  |  | 62.7 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Large Market; 8: Sannasirchar Bazar |  |  | 62.7 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Large Market; 8: Kashem Bazar |  |  | 62.7 | [6 empty] | 0%
3: Gaibandha; 4: Sadar; 5: Medium Market; 8: Balua Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sadar; 5: Medium Market; 8: Puraton Badiakhali Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sadar; 5: Medium Market; 8: Lenga Bazar Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Medium Market; 8: Ullah Sonatola Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Medium Market; 8: Bhangamore |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Medium Market; 8: Falia Bottola Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Medium Market; 8: Ullah Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Medium Market; 8: Dhakin Digholkandi |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Medium Market; 8: Nayabondar Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Khatiamary Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Taltola Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Kayerhaat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Daluabari Haat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Jigabari Haat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Algharchar Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Medium Market; 8: Jhanjhor Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Shadullapur; 5: Medium Market; 8: Boxigonj Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Shadullapur; 5: Medium Market; 8: Naldanga kachari Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Medium Market; 8: Belka Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Medium Market; 8: Charoker Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Medium Market; 8: Domer Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Medium Market; 8: Moyej Mear Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Medium Market; 8: Jamaler Hat |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Shadullapur; 5: Medium Market; 8: Boxigonj Bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Shadullapur; 5: Medium Market; 8: Kantanagar bazar |  |  | 41.77 | [6 empty] | 0%
3: Gaibandha; 4: Saghata; 5: Small Market; 8: Futani Bazar |  |  | 26.11 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Small Market; 8: Moshamari Bazar |  |  | 26.11 | [6 empty] | 0%
3: Gaibandha; 4: Fulchori; 5: Small Market; 8: Katlamari Bazar |  |  | 26.11 | [6 empty] | 0%
3: Gaibandha; 4: Sundargonj; 5: Small Market; 8: Shokher Hat |  |  | 26.11 | [6 empty] | 0%
| 2018-19 | Kurigram | Chilmari | Union Road-BC | PRO/KUR/CHI/UNR/18-19/W-21 | 149093002 | Improvement of Bituminous Carpating Road On Thanahat up office – Balabarihat via Kajaldanga hat at Ch.2985m-3455m. Under Chilmari Upazila, District Kurigram. | Nakshi Mobile Palace,Krishnopur, Kurigram | 2985 | 3455 | 0.47 | 0 | 4159071 | 0 | 4159071 | 3951117.45 |  | 3951117.45 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-25 |  | 2020-05-14 | 100% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 75.44% | All Item Completed.Final Bill Sent to H/Q |  | 1.97 | 180.9268 | 273 | 0.3663 | 593 | 217.2% | 100% | 100% | 0%
| 2019-20 | Kurigram | Chilmari | Rehabilitation-Union Road | PRO/KUR/CHIL/UNR/19-20/RW-79 | 149093002 | Rehabilitation of Thanahat Up Office to Balabarihat via Kazaldanga Hat Road at Ch: 00m-1040m including Construction of 1Nos 1x3.00mx2.50mm RCC. Box Culvert at Ch: 15m and 1Nos 1x0.625mx0.600mm U-Drain at Ch: 760m and 1Nos 1x2.50mx2.00m m RCC. Box Culvert at Ch: 820m under Upazila:Chilmari, District:Kurigram | Md.Abul Hossain, Shaheb Bazar,Groramara,Rajshahi. | 0 | 1040 | 1.04 | 7.5 | 4492492 | 1915132 | 6407624 | 3187498.28 | 1915132 | 5102630.28 |  |  | 2020-07-04 | 2020-04-21 | 2020-05-15 | 2021-02-14 |  | 2021-04-14 | 0% | [8 empty] | WO Issued | [9 empty] | 0%
| 2019-20 | Kurigram | Nageswari | Union Road-BC | PRO/KUR/NAG/UNR/19-20/W-80 | 149613039 | Improvement of Ramkhana UP office to Sealkanda bazar Road at Ch: 1000m-2776m including Construction of 1Nos 1x2.00mx2.00m RCC. Box Culvert at Ch: 1727m and 4Nos 1x0.6250mx 0.625m m RCC. Box Culvert at Ch: 1080m,1390m,2022m & 2118.00m Under Upazila: Nageswari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 1000 | 2776 | 1.776 | 6.5 | 16305564 | 1149239 | 17454803 | 14035591.24 | 942642.23 | 14978233.472 |  |  | 2020-02-26 | 2020-03-15 | 2020-05-23 | 2021-05-22 |  | 2021-03-19 | 20% | [8 empty] | Ch: 0.1000-2.276km Box Cutting Completed,Sand Filling Running. |  | 3 | 275.523 | 433 | 0.23095 | 301 | 69.52% | 69.52% | 20% | 49.52%
3: Kurigram; 4: Nageswari; 5: Union Road-BC; 7: 149613041; 8: Hasnabad UP Office - Newashi GC. |  | 2 | 183.682 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Union Road-BC; 7: 149773010; 8: Burirhat-Gharialdanga UP office. |  | 1.45 | 133.1694 | [6 empty] | 0%
| 2018-19 | Kurigram | Chilmari | Village Road-BC | PRO/KUR/CHI/VR/18-19/W-20 | 149095036 | Improvement of Bituminous Carpating Road on Kutigram Madrasha Pacca Rd – Kachkol CARE Bridge via Eblus Chairman house Road Ch. 00m-790m. & Link Road 0.00-230.0m. Under Chilmari Upazila, District Kurigram. | M/S. S. T Enterprise, Nageswari, Kurigram | 0 0 | 790 230 | 1.02 | 0 | 7735062 | 0 | 7735062 | 7348308.9 | 0 | 7348308.9 | 0 | 0 | 2019-05-05 | 2019-05-26 | 2019-06-03 | 2020-02-25 |  | 2020-05-19 | 65% | 2668854 | 0 | 2668854 | 0 | 0 | 0 | 2668854 | 36.32% | Ch. 0.00-1.020km sand filling , Sub-base & WBM completed. [Time Extension/Performcane Security Procedure Under Process ] | 84 | 1.45 | 125.3107 | 275 | 0.36364 | 595 | 216.4% | 100% | 65% | 35%
| 2018-19 | Kurigram | Sadar | Village Road-BC | PRO/KUR/KUR-S/VR/18-19/W-22 | 149525128 | Improvement of Bituminous Carpating Road on Paramali Dr. Sahabuddin Tepoti to Rajarhat Ch.000-1930m & at Ch.1585 Link Road Ch.0.00-264.0m including Contruction of 04 Nos. (0.625mx0.600m) U-Drain on Paramali Dr. Sahabuddin Tepoti to Rajarhat Road at Ch.90m,730m,1250m & 1770m . Kurigram Sader Upzila,District Kurigram | Md. Mahmud Alam Liton, Fulbari Pourashova,Fulbari | 0 0 | 1930 264 | 2.19 | 2.5 | 16229100 | 514550.2 | 16743650.2 | 16241461.24 | 501008.14 | 16742469.38 | 0 | 0 | 2019-05-15 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 2021-05-27 | 65% | 9164025 | 0 | 9164025 | 0 | 0 | 0 | 9164025 | 54.74% | Ch. 0.00-2.190km sand filling Sub-base & WBM completed,3 Nos U-Drain completed. Turffing Work Running. [ Time Extension/Performcane Security Procedure Under Process ] | 362 | 3 | 259.2636 | 366 | 0.27322 | 591 | 161.5% | 100% | 65% | 35%
| 2018-19 | Kurigram | Bhurungamari | Village Road-BC | PRO/KUR/BUR/VR/18-19/W-24 | 149064036 | Improvement of Bituminous Carpating Road on Milon Bazar – Baladfia Bazar (End point H/O Nasir Uddin) at Ch.00-2000.0m. including Contruction of 03 Nos. 0.625mx0.600m U-Drain at Ch.1003m, 1685m Under Bhurungamari Upazila, District Kurigram., | M/S. Hamid Traders, Hospitalpara, Kurigram Sadar, Kurigram | 0 | 2000 | 2 | 1.88 | 14468747 | 275159 | 14743906 | 13429170.35 | 260283.77 | 13689454.12 | 0 | 0 | 2019-05-15 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 2020-11-20 | 100% | 9370863 | 233117 | 9603980 | 0 | 0 | 0 | 9603980 | 70.16% | All Item Completed.Final Bill Sent to H/Q | 174 | 2 | 172.8424 | 366 | 0.27322 | 591 | 161.5% | 100% | 100% | 0%
| 2018-19 | Kurigram | Nageswari | Village Road-BC | PRO/KURI/NAW/VR/18-19/W-25 | 149615083 | Improvement of Bituminous Carpating Wabda Bazar – Berubari Abashon Road at Ch.00.0-1200.00m Under Nageswari Upazila, District Kurigram. ` | M/S. Fahim Traders, RK Road, Sadar Kurigram | 0 | 1200 | 1.2 | 0 | 9114248.72 | 0 | 9114248.72 | 8658536.55 | 0 | 8658536.55 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-27 |  | 2020-05-07 | 100% | 6573373 | 0 | 6573373 | 0 | 0 | 0 | 6573373 | 75.92% | All Item Completed.Final Bill Sent to H/Q | 70 | 2 | 172.8424 | 275 | 0.36364 | 593 | 215.6% | 100% | 100% | 0%
| 2018-19 | Kurigram | Rajibpur | Village Road-BC | PRO/KURI/RJP/VR/18-19/W-26 | 149084053 | Improvement of Bituminous Carpating Road on By Tangalipara- Pakhiura road at Ch.0.00-2000.0m.Under Rajibpur Upzila, District Kurigram. | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 0 | 2000 | 2 | 0 | 15018035 | 0 | 15018035 | 14211257.3 |  | 14211257.3 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-07 | 2020-05-30 |  | 29-05-2020 26-02-2021 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Ch. 0.00-2.000km sand filling completed. AS Layer Running. [ Time Extension/Performcane Procedure Security Under Process ] | #VALUE! | 2 | 172.8424 | 366 | 0.27322 | 591 | 161.5% | 100% | 20% | 80%
| 2018-19 | Kurigram | Ulipur | Village Road-BC | PRO/KURI/ULP/VR/18-19/W-27 | 149944098 | Improvement of Bituminous Carpating Road on Ramramhat Mosque – Hatiar Mela WAPDA Embankment via Kokire para road at Ch.0.00-2080.0m including Contruction Of 2 Nos.0.600mx0.625m U-Drain at Ch.??, ??m. and Contruction Of 1 Nos.Cross Drainge Structure at Ch.1485.0m. Under Ulipur Upzila, District Kurigram. | Milu Nowroj Abu Bakar, College Road, Kurigram Sadar, Kurigram | 0 | 2080 | 2.08 | 4.2 | 17817664.39 | 1159563.14 | 18977227.53 | 15698506.57 | 1143205.21 | 16841711.78 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 28-05-2020 31-01-2021 | 55% | 8981947 | 0 | 8981947 | 0 | 0 | 0 | 8981947 | 53.33% | Sand filling & Sub-base Up to 1950m, WMB 1950m Running .3 Nos U-Drain/1.Nos Cross Drain Completed,Palisading work 400m Completed . [ Time Extension/Performcane Security Procedure Under Process ] | #VALUE! | 3 | 259.2636 | 366 | 0.27322 | 591 | 161.5% | 100% | 55% | 45%
| 2018-19 | Kurigram | Rajarhat | Village Road-BC | PRO/KURI/RAJ/VR/18-19/W-28 | 149775079 | Improvement of Bituminous Carpating Road on Mondir Mouja at H/O Nousher Ali- Khamar GPS Road at Ch.0.00m-2725.0m under Fulbari Upazila, District Kurigram. | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 0 | 2725 | 2.725 | 0 | 21122799.06 | 0 | 21122799.06 | 18424739.36 | 0 | 18424739.36 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 21-05-2020 21-11-2020 | 40% | 5779701 | 0 | 5779701 | 0 | 0 | 0 | 5779701 | 31.37% | Ch.0.00-2.725km Sand filling work Completad, Sub-base Work running & wbm 1.000km RUNNING. [ Time Extension/Performcane Security Under Process ] | #VALUE! | 3 | 259.2636 | 366 | 0.27322 | 591 | 161.5% | 100% | 40% | 60%
| 2018-19 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/18-19/W-39 | 149185051 | Improvement of Bituminous Carpating Road On Bokultola Bazar-H/O Nobiul Road at Ch. 00m – 1070.00m including Construction of U-drain (600mm X 0.625mm) at Ch.131m. Under Fulbari Upazila, District Kurigram. | M/S. Milon Traders, Nilkhanto, Khalilgonj Bazar, Kurigram Sadar, Kurigram | 0 | 1070 | 1.07 | 0.6 | 8949548.12 | 100532 | 9050080.12 | 8502070.714 | 95505.4 | 8597576.114 | 0 | 0 | 2019-05-05 | 2019-05-30 | 2019-06-06 | 2020-02-28 |  | 2020-02-13 | 100% | 5143774 | 0 | 5143774 | 0 | 0 | 0 | 5143774 | 59.83% | All Item Completed. | -15 | 2 | 172.8424 | 274 | 0.36496 | 591 | 215.7% | 100% | 100% | 0%
| 2018-19 | Kurigram | Nageswari | Village Road-BC | PRO/KUR/NAG/VR/18-19/W-40 | 149614060 | Improvement of Bituminous Carpating Road on Kherbari More UZR-Boitulah More via Taleberhat Road at Ch.1000-4070m including Construction Of 9 Nos. 0.600mx0.625mU-Drain at.Ch.1400m, 1780m, 1940m, 2220m, 3300m, 2244m, 3550m, 3680m & 3840m,Under Nageswari Upazila, District Kurigram. | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 1000 | 4070 | 3.07 | 5.4 | 24836379.47 | 1048387.17 | 25884766.64 | 21156136.31 | 890699.56 | 22046835.87 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 |  | 2020-09-10 | 60% | 1057593 | 890699 | 1948292 | 0 | 0 | 0 | 1948292 | 8.837% | Ch. 1.000-4.000km Sand Filling, AS layer & WBM Completed,9 Nos U-Drain Completed. [ Time Extension/Performcane Security Procedure Under Process ] | 86 | 3 | 259.2636 | 366 | 0.27322 | 574 | 156.8% | 100% | 60% | 40%
| 2018-19 | Kurigram | Rajibpur | Village Road-BC | PRO/KUR/RAJI/VR/18-19/W-41 | 149084053 | Improvement of Bituminous Carpating Road on Tangalipara- Pakhiura road at Ch.2000-4000m.Under Rajibpur Upzila, District Kurigram. | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 2000 | 4000 | 2 | 0 | 10723064 |  | 10723064 | 9828649 |  | 9828649 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 |  | 2020-09-10 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Ch. 2.000-4.000km sand filling completed. AS Layer Running. | 86 | 2 | 172.8424 | 366 | 0.27322 | 574 | 156.8% | 100% | 25% | 75%
| 2018-19 | Kurigram | Bhurungamari | Village Road-BC | PRO/KUR/BHU/VR/18-19/W-42 | 149064003 | Improvement of Bituminous Carpating Road on R&H Trimohoni – Shingjhar Road at Ch.325.00-2685.00m. including Construction Of 1 Nos. (4x4.00x4.00) m Cross Drianges Structure at Ch 1702.00m. and Construction Of 1 Nos. (2.00x2.00) m Cross Drianges Structure and Construction Of 14 Nos.0.600mx0.625m U-Drain at Ch.636m,714m,935m,960m,1051m,1201m,1355m,1550m,2003m,2166m,2230m,2586m,2767m&3330m.Under Bhurungamari Upzila, District Kurigram. | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 325 | 2685 | 2.36 | 14.9 | 16522104 | 6439018 | 22961122 | 14962086.19 | 6239684.88 | 21201771.07 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 |  | 29-05-2020 28-02-2021 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Ch. 0.325-2.685km sand filling & Sub-base completed,8 Nos U-Drain( out of 14 Nos) completed.WBM Work Running. | #VALUE! | 2.36 | 203.954 | 366 | 0.27322 | 574 | 156.8% | 100% | 50% | 50%
| 2018-19 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/18-19/W-43 | 149775095 | Improvement of Bituminous Carpating Road on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.0.00m-2000.0m Under Rajarhat Upzila, District Kurigram. including Construction Of 2 nos. 0.600mx0.625m U-Drain on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.1667m, &1924m. under Rajarhat Upzila, District Kurigram. | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 0 | 2000 | 2 | 1.2 | 16290727 | 186745 | 16477472 | 14742059.38 | 168353.11 | 14910412.49 | 0 | 0 | 2019-05-27 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 2020-05-28 | 100% | 7373958 | 0 | 7373958 | 0 | 0 | 0 | 7373958 | 49.46% | All Item has been Completed. Final bill sent to HQ | -2 | 2 | 172.8424 | 366 | 0.27322 | 591 | 161.5% | 100% | 100% | 0%
| 2018-19 | Kurigram | Bhurungamari | Village Road-HBB | PRO/KUR/BUR/HBB/18-19/W-23 | 149064016 | Improvement of Bituminous Carpating Road on HBB from Pagla hat Bazar –Shangkose River Ghat at Ch.00-1390.0m. Under Bhurungamari Upazila, District Kurigram. | M/S. Akram Traders, Porchim Nageswari, Kurigram | 0 | 1390 | 1.39 | 0 | 7388648.15 | 0 | 7388648.15 | 7019215.6 | 0 | 7019215.6 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-27 |  | 2022-05-26 | 100% | 4290110 | 0 | 4290110 | 0 | 0 | 0 | 4290110 | 61.12% | All Item Completed.Final Bill Sent to H/Q | 819 | 1.4 | 81.144 | 275 | 0.36364 | 593 | 215.6% | 100% | 100% | 0%
3: Kurigram; 4: Sadar; 5: Village Road-BC; 7: 149525029; 8: Kawnia Ghat-Kaggipara G.P. School |  | 3 | 259.2636 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Village Road-BC; 7: 149524014; 8: Nowbash BWDB Emb.-Nayerhat Emb. |  | 3 | 259.2636 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Village Road-BC; 7: 149525043; 8: Shop of Abul at BWDB Embank.-Velurbazar |  | 1 | 86.4212 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Village Road-BC; 7: 149525031; 8: Char Boraibari Rd |  | 2 | 172.8424 | [6 empty] | 0%
3: Kurigram; 4: Fulbari; 5: Village Road-BC; 7: 149185057; 8: Boroloi Bazar-Amsa Bazar |  | 2 | 172.8424 | [6 empty] | 0%
| 2019-20 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/19-20/W- 81 | 149185050 | Improvement of Uttar Kashipur Shenpara – Kashem Bazar Via Ghugurhat Road at Ch: 00m-2500m including Construction of 3Nos 1x0.600mx0.600m m RCC. Box Culvert at at Ch: 90m,270m,1437m Under Upazila: Fulbari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 0 | 2500 | 2.5 | 3 | 21253035 | 317903 | 21570938 | 18298929.65 | 317903 | 18616832.65 |  |  | 2020-03-19 | 2020-03-29 | 2020-05-15 | 2021-05-14 |  | 2021-03-21 | 10% | [8 empty] | Box Cutting Completed,Sand Filling Running. |  | 2.5 | 216.053 | [6 empty] | 0%
| 2019-20 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/19-20/W- 82 | 149185060 | Improvement of H/O Shajamal – Bokultola Bazar Via Abder Tale House Road at Ch: 00m-545.00m including Construction of 2Nos U-Drain at Ch: 124m,375m Under Upazila: Fulbari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 0 | 545 | 0.545 | 2 | 4620972 | 211935 | 4832907 | 4027967.48 | 211935 | 4239902.48 |  |  | 2020-02-26 | 2020-03-16 | 2020-02-05 | 2020-02-11 |  | 2020-09-06 | 0% | [8 empty] | Box Cutting Completed. |  | 2 | 172.8424 | -34 | -2.9412 | 300 | -882.4% | -882.4% | 0% | -882.4%
3: Kurigram; 4: Bhurungamari; 5: Village Road-BC; 7: 149064020; 8: Thanaghat-Shahebganj Border Road |  | 3 | 259.2636 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Village Road-BC; 7: 149615081; 8: Baparitary-Horibolarkuti via H/O Nur Islam Master |  | 2 | 172.8424 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Village Road-BC; 7: 149614028; 8: Sarker tari UZR to Chanderhat |  | 2.5 | 216.053 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Village Road-BC; 7: 149614012; 8: Sadar Beparirghat - Momingonj bazar |  | 1.84 | 159.015 | [6 empty] | 0%
| 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W-65 | 149774012 | Improvement of Bituminus carpeting road Chandamari-Shyom Narayan at Biddyananda road at Ch: 1000m-2235m including 1 Nos(0.625X0.625)m U-Drain under Upazila: Rajarhat, District: Lalmonirhat. | M/S Khairul Enterprise | 1000 | 2235 | 1.235 | 1 | 6826143 | 101493 | 6927636 | 5907689.72 | 101493 | 6009182.72 |  |  | 2020-11-02 | 2020-02-17 | 2020-02-24 | 2020-08-23 |  | 2020-02-16 | 0% | [8 empty] | WO Issued |  | 2 | 172.8424 | 188 | 0.53191 | 328 | 174.5% | 100% | 0% | 100%
2: 2019-20; 3: Kurigram; 4: Rajarhat; 5: Rehabilitation-Village Road; 6: PRO/KUR/RAJA/VR/19-20/RW-66; 7: 149774012; 8: Rehabilitation of Chandamari-Shyom Narayan at Biddyananda road at Ch:00m-1000m under Upazila: Rajarhat, District: Lalmonirhat.; 9: M/S Khairul Enterprise; 10: 0; 11: 1000; 12: 1; 14: 2479051; 16=14+15: 2479051; 17: 2030770.61; 19=17+18: 2030770.61; 22: 2020-11-02; 23: 2020-02-17; 24: 2020-02-24; 25: 2020-08-23; 27: 2020-09-13; 28: 0%; 37: WO Issued |  |  |  | 188 | 0.53191 | 328 | 174.5% | 100% | 0% | 100%
3: Kurigram; 4: Rajarhat; 5: Village Road-BC; 7: 149774029; 8: Rajmallihat hat-Nazimkhan UP (Jorsarar hat) via Battalarhat. |  | 3 | 259.2636 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Rajarhat; 5: Village Road-BC; 6: PRO/KUR/RAJA/VR/19-20/W- 105; 7: 149774008; 8: Improvement of Rajmallir hat-Shakoa GPS road Ch: 00 m-1985.00m including Construction of 2x3.00mx3.00m Rcc.Box Culvert and 2 Nos0.925x0.925m U-Drain at Ch: 00 m-1985.00m Under Upazila: Razarhat, District:Kurigram.; 10: 0; 11: 1985; 12: 1.985; 13: 9.8; 14: 17188824; 15: 2342534; 16=14+15: 19531358; 37: Tender evaluation on going |  | 2 | 172.8424 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Village Road-BC; 7: 149775058; 8: Ramratan Mouza - Chinai UP gat road |  | 1 | 86.4212 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Rajarhat; 5: Village Road-BC; 6: PRO/KUR/RAJA/VR/19-20/W- 104; 7: 149775066; 8: Improvement of WAPDA Emb.at Chaturvuj Mouza-Makli Mouja at Brahmmon para road Ch: 00m-2000m Under Upazila: Razarhat, District:Kurigram.; 10: 0; 11: 2000; 12: 2; 14: 18457590; 16=14+15: 18457590; 37: Tender evaluation on going |  | 2 | 172.8424 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Rajarhat; 5: Village Road-BC; 6: PRO/KUR/RAJA/VR/19-20/W-103; 7: 149774067; 8: Improvement of Nazimkhan -Forkerhat at Boroghat Madrasha More-Bottalahat road Ch: 00m-1000m including Construction of 3Nos 1x0.6250mx 0.625m m U-Drain at Ch: 630m,840m &982m Under Upazila: Razarhat, District:Kurigram; 10: 0; 11: 1000; 12: 1; 13: 3; 14: 9000125; 15: 312627; 16=14+15: 9312752; 37: Tender evaluation on going |  | 1 | 86.4212 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Ulipur; 5: Maintenance-LCS; 6: PRO/KUR/ULI/RMP/19-20/MW-112; 7: 149944076; 8: Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Mollahat-Panchim side of Mogholbacha UP simana road at Ulipur Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 4.000Km); 12: 4; 16=14+15: 1981199; 37: LCS team formation ongoing, Estimate approved on 19-03-20 |  | 3 | 259.2636 | [6 empty] | 0%
| 2019-20 | Kurigram | Sadar | Maintenance-LCS | PRO/KUR/ULI/RMP/19-20/MW-111 | 149525026 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Panchgachi Bazer-Nayani Para Sarak at Kurigram Sadar Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 1.650Km) |  |  |  | 1.65 |  |  |  | 1114033 | [20 empty] | LCS Team appointed,Estimate approved on 19-03-20
3: Kurigram; 4: Ulipur; 5: Village Road-BC; 7: 149944136; 8: Bozra U.P. office-Babur hat |  | 3 | 259.2636 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Rowmari; 5: Village Road-BC; 6: PRO/KUR/ROW/VR/19-20/W- 106; 7: 149795038; 8: Improvement of Shaydabad to Shiber Dhangi FCD road Ch: 1000m-2000m Under Upazila: Rowmari, District:Kurigram.; 10: 1000; 11: 2000; 12: 1; 14: 7923918; 16=14+15: 7923918; 37: Tender evaluation on going |  | 1 | 86.4212 | [6 empty] | 0%
3: Kurigram; 4: Rowmari; 5: Village Road-BC; 7: 149795077; 8: Saidabad Bazar- west side Pakhiura hat via Komorvangi GPS |  | 2.2 | 190.1266 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Rowmari; 5: Village Road-BC; 6: PRO/KUR/ROW/VR/19-20/W-89; 7: 149794017; 8: Improvement of Boalmari Modho Mosque –Changtapara Via Danguapara Road at Ch: 1000m-3000m Under Upazila:Rowmari, District:Kurigram; 9: M/S Hamid Traders; 10: 1000; 11: 3000; 12: 2; 14: 17170453; 16=14+15: 17170453; 17: 15980384.43; 19=17+18: 15980384.43; 22: 2020-02-26; 23: 2020-03-16; 24: 2020-05-23; 25: 2021-05-22; 27: 2021-05-14; 28: 0%; 37: WO Issued |  | 2 | 172.8424 | 432 | 0.23148 | 300 | 69.44% | 69.44% | 0% | 69.44%
| 2019-20 | Kurigram | Bhurungamari | Village Road-HBB | PRO/KUR/BUR/VR/19-20/W- 98 | 149064029 | Improvement of Dhaldanga Bazar-Shilkhuri Kheya ghat road (HBB) Ch: 1200m-2250m including Construction of 1x2.00mx 2.00m RCC. Box Culvert on Ch: 1540m under Upazila:Bhurungamari, District:Kurigram. |  | 1200 | 2250 | 1.05 | 2.5 | 5160645 | 758362 | 5919007 | 5172960.88 |  | 5172960.88 |  |  | 2020-12-04 | 2020-04-21 | 2020-05-15 | 2021-09-14 |  | 2021-09-05 | 70% | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 3000000 | 57.99% | Ch. 1200-2000km HBB completed. Ch.2000-2250 Running. |  | 1.05 | 60.858 | [6 empty] | 0%
2: 2020-21; 3: Kurigram; 4: Rajarhat; 5: Village Road-BC; 6: PRO/KURI/RAJA/VR/ 19-20/W-130; 8: Improvement of Bazar Gate of Nazimkhan Union- Dangghat Kali Mondir via Ratiram Pathanpara GPS Road. road Ch: 0.0m-1580m including Construction of 1Nos 0.625m x 0.625m U-Drain at Ch: 427 m Under Upazila: Rajarhat, District:Kurigram.; 10: 0; 11: 1580; 12: 1.58; 13: 1; 14: 13888297; 15: 101493; 16=14+15: 13989790; 37: Estimate approved on 20-7-20 |  | 1.5 | 86.94 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Large Market; 8: Panga |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Chilmari; 5: Large Market; 8: Jorgach Hat |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Chilmari; 5: Large Market; 8: Thana Hat |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Chilmari; 5: Large Market; 8: Fakirar Hat |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Ulipur; 5: Large Market; 8: Sunamgonj Hat |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Ulipur; 5: Large Market; 8: Mollar Hat |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Rajibpur; 5: Large Market; 8: Rajibpur GC |  |  | 62.7 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Sadar; 5: Large Market; 6: PRO/KURI/SAD/LM/19-20/W-110; 8: Construction of Jatiner Hat Upazila: Sadar, District: Kurigram (03 nos LCS group); 16=14+15: 9805786; 37: Contact will be signed soon. Estimate approved on 19-03-20 |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Large Market; 8: Panchgachi Hat |  |  | 62.7 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Medium Market; 8: Burirhat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Medium Market; 8: Sharisabari Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Medium Market; 8: Chandamari Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Medium Market; 8: Dangrar Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Medium Market; 8: Chowrahat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Medium Market; 8: Rajmallirhat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Chilmari; 5: Medium Market; 8: karai Barisal |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Chilmari; 5: Medium Market; 8: Kachkol hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Medium Market; 8: Chilakhana Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Medium Market; 8: Egaromatha Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Medium Market; 8: Berubari Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Medium Market; 8: Schooler Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Medium Market; 8: Monigonj Bazar |  |  | 41.77 | [6 empty] | 0%
2: 2019-20; 3: Kurigram; 4: Ulipur; 5: Medium Market; 6: PRO/KURI/ULI/MM/2019-20/W-61; 8: Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram; 9: Gouribala and Bimala Rani; 16=14+15: 2577497; 19=17+18: 2577497; 23: 2019-12-22; 24: 2019-12-29; 25: 2020-12-28; 28: 35%; 29: 800000; 30: 0; 31=29+30: 800000; 32: 0; 33: 0; 34=32+33: 0; 35=31+33: 800000; 36: 31.04%; 37: Male Toilet : (Septic Tank & Soak Well) on Going.Female : Earrth Work On Going. Est. Approved on 20-11-19 |  |  | 41.77 | 372 | 0.26882 | 385 | 103.5% | 100% | 35% | 65%
2: 2019-20; 3: Kurigram; 4: Ulipur; 5: Medium Market; 6: PRO/KURI/ULI/MM/2019-20/W-62; 8: Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram; 9: Sagorika Bala and Anju Begum; 16=14+15: 2579493; 19=17+18: 2579493; 23: 2019-12-22; 24: 2019-12-29; 25: 2020-12-28; 28: 35%; 29: 800000; 30: 0; 31=29+30: 800000; 32: 0; 33: 0; 34=32+33: 0; 35=31+33: 800000; 36: 31.01%; 37: Multipurpose Shed : Column On Going.Est. Approved on 20-11-19 |  |  |  | 372 | 0.26882 | 385 | 103.5% | 100% | 35% | 65%
2: 2019-20; 3: Kurigram; 4: Ulipur; 5: Medium Market; 6: PRO/KURI/ULI/MM/2019-20/W-87; 8: Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram; 9: Joymala begum and Beuty Begum; 16=14+15: 534466; 19=17+18: 534466; 23: 2020-01-12; 24: 2020-01-19; 25: 2020-07-18; 28: 80%; 29: 200000; 30: 0; 31=29+30: 200000; 32: 0; 33: 0; 34=32+33: 0; 35=31+33: 200000; 36: 37.42%; 37: Ground Raising : Earth Work On Going. Est. Approved on 26-12-19 |  |  |  | 188 | 0.53191 | 364 | 193.6% | 100% | 80% | 20%
| 2020-21 | Kurigram | Sadar | Maintenance-LCS | PRO/KUR/KUR_S/RMP/19-20/ MW-122 | 149525029 | i)Kawnia Ghat-Kaggipara G.P. School |  | 1500 | 4500 | 3 |  | 1311672.96 |  | 1311672.96 | [20 empty] | Estimate approved on 15-7-20
| 2020-21 | Kurigram | Rajarhat | Maintenance-LCS | PRO/KUR/RAJA/RMP/19-20/ MW-123 | 149775054 149774065 | i)Amtoli Bazar to Sakhoa GPS road. ii)Dino Bazar rail line to Amtail Bazar via Narayam Nember House. |  | 0 0 | 1800 1000 | 2.8 |  | 1587940.81 |  | 1587940.81 | [20 empty] | Estimate approved on 15-7-20
| 2020-21 | Kurigram | Rajibpur | Maintenance-LCS | PRO/KUR/RAJIRMP/19-20/ MW-124 | 149084006 | i) Boraidangi Collage Road. |  | 0 | 0.825 | 0.825 |  | 713992.18 |  | 713992.18 | [20 empty] | Estimate approved on 15-7-20
3: Kurigram; 4: Rowmari; 5: Medium Market; 8: Saydabad Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rowmari; 5: Medium Market; 8: Lawbari hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rowmari; 5: Medium Market; 8: Baraikandhi Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Fulbari; 5: Medium Market; 8: Boroloi Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Fulbari; 5: Medium Market; 8: Shiber Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Fulbari; 5: Medium Market; 8: Bokultala Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Fulbari; 5: Medium Market; 8: Ghogurhat Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Medium Market; 8: Sardob RDRS Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Medium Market; 8: Rajarhat Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Medium Market; 8: Hazir Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Medium Market; 8: Nayer Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Medium Market; 8: Shimultala Wapda Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Medium Market; 8: Valur Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 5: Medium Market; 8: Char Boraibari Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Bhurungamari; 5: Medium Market; 8: Baldia Bazar |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Bhurungamari; 5: Medium Market; 8: Choudhurir Hat |  |  | 41.77 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Small Market; 8: Kalirhat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Small Market; 8: Fulkhar Chakla |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Small Market; 8: Amtola Bazar |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Small Market; 8: Kalirhat Bazar |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Rajarhat; 5: Small Market; 8: Battalar Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Small Market; 8: Taleber Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Small Market; 8: Wapda Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Small Market; 8: Chander Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Small Market; 8: Shialkanda Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Small Market; 8: Daknirpat Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Nageswari; 5: Small Market; 8: Mina Bazar |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 5: Small Market; 8: New Annandapur Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Sadar; 5: Small Market; 8: masterer Hat |  |  | 26.11 | [6 empty] | 0%
3: Kurigram; 4: Bhurungamari; 5: Small Market; 8: Muktijodha Hat B |  |  | 26.11 | [6 empty] | 0%
| 2018-19 | Rangpur | Kaunia | Union Road-BC | PRO/RAN/KAU/UNR/18-19/W-16 | 185423012 | Improvement of Bituminous Carpeting Road on Sarai Up office (Zahir) to Eakota Bazar Via Udaynarayon Machari Govt.Primary School at Ch.2375m-3055m. Under Kaunia Upazila, District Rangpur. | M/S. Nila Enterprise, Shalbon, Rangpur | 2375 | 3055 | 0.68 | 0 | 5430014.69 | 0 | 5430014.69 | 5158514.25 | 0 | 5158514.25 | 0 | 0 | 2019-03-19 | 2019-04-09 | 2019-04-16 | 2020-02-15 |  | 2020-03-24 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Box cutting complete | 38 | 1 | 91.841 | 312 | 0.32051 | 642 | 205.8% | 100% | 20% | 80%
| 2018-19 | Rangpur | Gangachara | Union Road-BC | PRO/RAN/GAN/UNR/18-19/W-17 | 185273020 | Improvement of Bituminous Carpeting Road on Kolkando UP (Binbina Ferrighat)-Abuliahat Upto Kaliganj Upazila Border (Tusvander UP) Road at Ch 00-2350m. including Costruction of 3 U- drain at Ch 00-2350m Under Gangachara Upazila, District Rangpur. | M/S. Onto & Tahity (JV), Rangpur | 0 | 2350 | 2.35 | 4.8 | 19971756.68 | 1573720 | 21545476.68 | 18763031.63 | 1476418.6 | 20239450.23 | 0 | 0 | 2019-04-15 | 2019-04-30 | 2019-05-06 | 2020-05-05 | - | 2020-06-03 | 95% | 15791217 | 0 | 15791217 | 2614777 | 0 | 2614777 | 18405994 | 90.94% | WBM Complete | 29 | 4.2 | 385.7322 | 371 | 0.26954 | 621 | 167.4% | 100% | 95% | 5%
2: 2019-20; 3: Rangpur; 4: Kaunia; 5: Union Road-BC; 6: PRO/RAN/KAU/UNR/19-20/W-74; 7: 185423013; 8: Improvement of Bituminous carpeting Road on Sarai UP- Bhahishwler More bazar via Naira Pry.School Road at Ch: 1412m-3412m including Construction of 1Nos (0.625x0.625) m U-Drain at Ch: 1775m,2247m, 2537m,2590m & 3155m and 1Nos 3x4.50mx4.00 m RCC Box Culvert at Ch: 2127m and 1Nos 1x2.00mx2.00 m RCC Box Culvert at Ch: 2901m Under Upazila:Kaunia, District: Rangpur; 10: 1412; 11: 3412; 12: 2; 13: 22.5; 14: 18739034; 15: 6076156; 16=14+15: 24815190; 37: Evaluation on going, Tender opening date 17-2-20 |  | 2 | 183.682 | [6 empty] | 0%
3: Rangpur; 4: Kaunia; 5: Village Road-BC; 7: 185424016; 8: Haragach pucca road-Joybangla Bazar Rd. |  | 0.84 | 72.5938 | [6 empty] | 0%
2: 2020-21; 3: Rangpur; 4: Kaunia; 5: Village Road-BC; 6: PRO/RAN/KAU/VR/20-21/W-137; 7: 185424058; 8: Improvement of Bituminous carpeting on Jummarpar R&H - Mirbag Gramen Bank More Bazar. Road at Ch:00m-1482m including Construction of 2Nos 0.625x0.625 m U-Drain at Ch:315m & 465m Under Kaunia Upazila , District: Rangpur.; 10: 0; 11: 1482; 12: 1.482; 13: 2; 14: 13006125; 15: 271764; 16=14+15: 13277889; 37: Estimate approved on 20-8-20 |  | 2.35 | 203.0898 | [6 empty] | 0%
2: 2020-21; 3: Rangpur; 4: Kaunia; 5: Village Road-BC; 6: PRO/RAN/KAU/VR/20-21/W-138; 7: 185424060; 8: Improvement of Bituminous carpeting Road on Topical GC hat - Branter bazar via Gopidanga GPS. Road at Ch: 00m-2785m including Construction of 3Nos 0.625x0.625 m Drainage Structure at Ch:640m,1383m &1814m and 1Nos 1x1.500x1.50 m RCC Box Culvert at Ch: 551m and 1x2.00x2.00 m RCC Box Culvert at Ch: 128m 2x4.50x4.00 m RCC Box Culvert at Ch: 910m and 3x4.50x4.00 m RCC Box Culvert at Ch: 1607m Under Under Kaunia Upazila , District: Rangpur.; 10: 0; 11: 2785; 12: 2.785; 13: 32.8; 14: 23976518; 15: 9984639; 16=14+15: 33961157; 37: Estimate approved on 20-8-20 |  | 2.5 | 216.053 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Village Road-BC; 7: 185275115; 8: Bagerhat to Sankordho Hafazia Madrasha |  | 1 | 86.4212 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Village Road-BC; 7: 185275107; 8: Balatary Chowpati - Joydeb Dolapara Road |  | 2 | 172.8424 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Village Road-HBB; 7: 185275134; 8: Betgari Kachua UZR near Patakhowa more - Sudhuir Master's house road |  | 1.72 | 99.6912 | [6 empty] | 0%
| 2018-19 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/18-19/W-15 | 185424019 | Improvement of Bituminous carpeting Road on Kutirghat Bazar-Sonaton Shaidar Darogar Chatal Road at Ch 00-1715m. including Costruction of 1 no U- drain (.600mx0.625m) at Ch 1120m. Under Kaunia Upazila, District Rangpur. | Md. Hafizur Rahman Burirhat, Rangpur. | 0 | 1715 | 1.715 | 0.6 | 13105734.48 | 106317 | 13212051.48 | 12748776.42 | 101028.9 | 12849805.32 |  |  | 2019-04-15 | 2019-04-30 | 2019-05-05 | 2020-03-22 |  | 2020-04-20 | 100% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 99.04% | Final bill paid | 29 | 3 | 259.2636 | 327 | 0.30581 | 621 | 189.9% | 100% | 100% | 0%
2: 2019-20; 3: Rangpur; 4: Kaunia; 5: Medium Market; 6: PRO/RAN/KAU/MM/19-20/W- 107; 8: Construction of Ekoter Hat Upazila:Kaunia, District: Rangpur, Under PROVATi3 Project.; 9: Mst Sahida Khatun and Mst. Merina Begum (LCS-1)/Mst. Dolena and Mst. Sheuli Begum(LCS-2); 16=14+15: 5032629; 19=17+18: 5032629; 23: 2020-07-21; 25: 2021-07-21; 28: 0%; 37: Contact signed on 21-7-20.Estimate approved on 15-03-20 |  |  | 41.77 | [6 empty] | 0%
| 2019-20 | Rangpur | Gangachara | Maintenance-LCS | PRO/RAN/GAN/RMP/19-20/MW-108 | 185275228 185275241 185275115 | (i) Rural road maintenance by LCS (Material & Wages) work on Char Nohali Bridger Bazar- Minar Bazar via Ashrayon Bazar (Bager hat) Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. (ii) Rural road maintenance by LCS (Material & Wages) work on Kutub hat(konabari) - Khamer mohona GPS via uttor kishamot Gonesh GPS Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. (iii) Rural road maintenance by LCS (Material & Wages) work on Bagerhat to Sankordho Hafazia Madrasha Sarak at Kaunia Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. (Length 1.000Km) | Mst. Ayouli Begum & Mst. Anufa Begum (LCS-01) |  |  | 9 |  |  |  | 4087239.65 |  |  | 1261167.96 |  |  |  | 2020-06-01 |  | 2022-05-31 |  |  | 0% | [8 empty] | Contract agreement signed of package #2, other 2 nos packages contract agreement is under process. Estimate approved on 15-3-20
| 2019-20 | Rangpur | Kaunia | Maintenance-LCS | PRO/RAN/KAU/RMP/19-20/MW-109 | 185423013 | Rural road maintenance by LCS (Material & Wages) work on Sarai UP-Bhahishwler more Bazar via Naira Pry. School Sarak at Kaunia Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | Mst. Rabeya Khatun & Mst. Rugina Begum |  |  | 2.275 |  |  |  | 1326724.49 |  |  | 1326724.49 |  |  |  | 2020-06-01 |  | 2022-05-31 |  |  | 0% | [8 empty] | Contract agreement signed. Estimate approved on 15-3-20
3: Rangpur; 4: Kaunia; 5: Medium Market; 8: Bhaier Hat |  |  | 41.77 | [6 empty] | 0%
3: Rangpur; 4: Kaunia; 5: Medium Market; 8: Bhutsora(Mirbag)Hat |  |  | 41.77 | [6 empty] | 0%
3: Rangpur; 4: Kaunia; 5: Medium Market; 8: Haqueer hat |  |  | 41.77 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Medium Market; 8: Babubazar |  |  | 41.77 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Medium Market; 8: Abuliarhat |  |  | 41.77 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Small Market; 8: Bagerhat |  |  | 26.11 | [6 empty] | 0%
3: Rangpur; 4: Gangachara; 5: Small Market; 8: Ichli Bazar(SKS Bazar) |  |  | 26.11 | [6 empty] | 0%
| 2018-19 | Nilphamari | Dimla | Union Road-BC | PRO/NIL/DIM/UNR/18-19/W-44 | 173123002 | Improvement of Bituminous carpeting Road of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164 km Under Dimla Upazila,District Nilphamari including Construction of 1Nos (2.00x2.00)m Cross Drainges Structure .at Ch.2287m and Construction of 2 Nos 7.00m Long.0.625mx0.625m U-Drain on Ch.2785,4011.0m of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164.00km Under Dimla Upazila,District Nilphamari | M/S. Misuk Enterprise, Food Office Road, Nilphamari. | 2255 | 4164 | 1.909 | 3.25 | 16925909.68 | 1073862.5 | 17999772.18 | 16669437.91 | 1057539.337 | 17726977.247 |  |  | 2019-07-27 | 2019-08-07 | 2019-08-13 | 2020-08-12 |  | 2020-08-31 | 70% | 10797551 | 0 | 10797551 | 648685 | 0 | 648685 | 11446236 | 64.57% | WBM & Structure completed | 19 | 1.5 | 137.7615 | 371 | 0.26954 | 522 | 140.7% | 100% | 70% | 30%
2: 2019-20; 3: Nilphamari; 4: Dimla; 5: Union Road-BC; 6: PRO/NIL/DIM/UNR/19-20/W-119; 7: 173123014; 8: Improvement of Bituminous carpeting Road of Naotara U.P Office-Motirbazar Rd. Ch: 950m-3250m including Construction of 1Nos 1x1.50mx 1.50 m U-Drain at Ch. 1159m and 2Nos 1mX0.6250mX 0.60m m U-Drain at Ch. 1389m under Upazila: Dimla, Dist: Nilphamari; 10: 950; 11: 3250; 12: 2.3; 13: 3; 14: 19781105; 15: 936387; 16=14+15: 20717492; 37: Evaluation ongoing, Tender opening date 13-08-20,Estimate Approved on 15-06-20 |  | 2.3 | 211.2343 | [6 empty] | 0%
| 2018-19 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/18-19/W-18 | 173124093 | Improvement of Bituminous carpeting Road on Ullarmore to Rahmangonj Bazar Road Under Gayabari Union at Ch.0.00m-2490m. including Construction of 2 Nos (1.50x1.50)m Box Culvert at Ch.142.00m & 630.0m and Construction of 1 Nos (2x3.00x3.00)m Box Culvert at Ch.197.00 m and Costruction of 1 Nos(1.500x1.00)m and Construction of 1 Nos (2x4.50x4.00) m Box Culvert at Ch.1922.00 m. and Costruction of 3 Nos(0.625x0.600) m U-Drain at Ch.50.0,480.0m&852m.Under Dimla Upazila,District Nilphamari. | JV of SA FE Shahipara, Nilphamari. | 0 | 2490 | 2.49 | 24.63 | 18674476.67 | 6963499.25 | 25637975.92 | 18551554.07 | 6917609.79 | 25469163.86 |  |  | 2019-06-24 | 2019-06-30 | 2019-07-06 | 05-07-2020 12-08-2020 |  | 2020-12-31 | 70% | 5022189 | 0 | 5022189 | 798820 | 0 | 798820 | 5821009 | 22.86% | WBM & Structure completed | #VALUE! | 2.47 | 213.4604 | #VALUE! | #VALUE! | 560 | #VALUE! | #VALUE! | 70% | #VALUE!
| 2018-19 | Nilphamari | Jaldhaka | Village Road-BC | PRO/NIL/JAL/VR/18-19/W-19 | 173365087 | Improvement of Bituminous Carpeting Road on Gabroli RNGPS-Tin Babul house via Rath Bazar Road at Ch 1000.0m-2650.0m including Costruction of 2 Nos (1.00x1.00) Box Culvert at Ch 1450.0m&1720.0m and Costruction of 1 Nos(2.00x2.00)m Box Culvert at Ch 2620.0m Under Jaldhaka Upazila,District Lilphamari. | M/S. Mohsena Enterprise, Monshapara, Nilphamari. | 1000 | 2650 | 1.65 | 4.8 | 13626801.7 | 1172872 | 14799673.7 | 12495688.82 | 1075512.29 | 13571201.11 |  |  | 2019-06-24 | 2019-07-09 | 2019-07-15 | 2020-07-14 |  | 2020-12-31 | 60% | 7136510 | 0 | 7136510 | 0 | 0 | 0 | 7136510 | 52.59% | WBM & Structure ongoing | 170 | 1.65 | 142.595 | 371 | 0.26954 | 551 | 148.5% | 100% | 60% | 40%
2: 2019-20; 3: Nilphamari; 4: Dimla; 5: Village Road-BC; 6: PRO/NIL/JAL/VR/19-20/W-120; 7: 173124012; 8: Improvement of Bituminous Carpeting Road on Dakhin Sonakhuli-Dalia Taltola road Ch: 2150m-3650m including 2Nos 1x1.50mx 1.50 m U-Drain at Ch.Ch: 2388 m & 2630m and 2Nos 1x0.6250mx 0.60m m U-Drain at Ch: 2210 m & 2270m under Upazila: Dimla, Dist: Nilphamari; 10: 2150; 11: 3650; 12: 1.5; 13: 5; 14: 13285714; 15: 1575024; 16=14+15: 14860738; 37: Evaluation ongoing, Tender opening date 13-08-20,Estimate Approved on 15-06-20 |  | 1.5 | 129.6318 | [6 empty] | 0%
3: Nilphamari; 4: Dimla; 5: Village Road-BC; 7: 173125089; 8: Kakina Chapani Madrasha-Tista Main Canal. |  | 2.7 | 233.3372 | [6 empty] | 0%
3: Nilphamari; 4: Dimla; 5: Village Road-BC; 7: 173124082; 8: Dkhi Sonakhuli - Vajonchur vai khamatpara |  | 2 | 172.8424 | [6 empty] | 0%
2: 2019-20; 3: Nilphamari; 4: Dimla; 5: Village Road-BC; 6: PRO/NIL/DIM/VR/19-20/W-125; 7: 173124083; 8: Improvement of Sonakhuli high School -Vendabari Road Ch: 00m-2155 m including 1Nos 1x3.00mx2.00m RCC. Box Culvert at Ch: 607m and 2Nos 1x1.50mx1.50m. RCC.Box Culvert at Ch: 720 m & 1167m and 1Nos 2x3.00mx2.00m RCC. Box Culvert at Ch: 206m Under Upazila: Dimla, District:Nilphamari.; 10: 0; 11: 2155; 12: 2.155; 13: 16; 14: 19440508; 15: 3953515; 16=14+15: 23394023; 37: Evaluation ongoing, Tender opening date 13-08-20,Estimate Approved on 15-06-20 |  | 2.5 | 216.053 | [6 empty] | 0%
2: 2019-20; 3: Nilphamari; 4: Dimla; 5: Village Road-HBB; 6: PRO/NIL/DIM/VR/19-20/W-121; 7: 173125117; 8: Improvement of HBB Road on Sovangong Bazar- Astaf Ali House via Azgar rice mill road, under Balapara union Ch: 330m-1385 m Under Upazila: Dimla, District:Nilphamari.; 10: 330; 11: 1385; 12: 1.055; 14: 5468148; 16=14+15: 5468148; 37: Evaluation ongoing, Tender opening date 13-08-20,Estimate Approved on 15-06-20 |  | 1 | 57.96 | [6 empty] | 0%
| 2020-21 | Nilphamari | Dimla | Maintenance-LCS | PRO/NIL/DIM/RMP/20-21/ MW-128 | 173123014 173124012 173125089 173124082 173124083 | i)Naotara U.P. Office-Motirbazar RD at ch. 3200-6400 m. ii)DakhinSonakhuli-DaliaTaltola at ch. 1500-3750 m. iii)Kakina Chapani Madrasha-Tista Main Canal at ch. 2700-3500 m. iv)Dkhin Sonakhuli-Vajonchur via Khamatpara at ch. 2000-4500 m. v)Sonakhuli High School- Vendabari at ch. 2500-3800 m. |  | 3200 1500 2700 2000 2500 | 6400 3750 3500 4500 3800 | 10.05 |  | 5070735.37 |  | 5070735.37 | [20 empty] | Estimate approved on 16-7-20
| 2020-21 | Nilphamari | Jaldhaka | Maintenance-LCS | PRO/NIL/JAL/RMP/20-21/ MW-129 | 173365064 173365066 | i)WDB Bundh to WDB Bundh via Moratista Syphon at ch. 00-1215 m. ii)Moratista Syphon to WDB Bundh ch. 00-1506 m. |  | 0.00 0.00 | 1215 1506 | 2.721 |  | 1586360.82 |  | 1586360.82 | [20 empty] | Estimate approved on 16-7-20
3: Nilphamari; 4: Dimla; 5: Large Market; 8: Tunirhat |  |  | 62.7 | [6 empty] | 0%
3: Nilphamari; 4: Dimla; 5: Large Market; 8: Babur hat |  |  | 62.7 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Large Market; 8: Bhabonchur Bazar |  |  | 62.7 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: Goulmunda Bazar |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: Balagrm Bazar |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: kharkati Hat |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: kaligonj Bangha bandhu Bazar |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: pathanpara hat |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: Diabari Hat |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: Dakligonj hat |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Medium Market; 8: Shibur hat |  |  | 41.77 | [6 empty] | 0%
3: Nilphamari; 4: Jaldhaka; 5: Small Market; 8: Kathali Nayer hat |  |  | 26.11 | [6 empty] | 0%
| 2018-19 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/18-19/W-02 | 152703010 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Koborstan to Sarkarhat Jongra UP Road at Ch. 00-2185m. Under Patgram Upazila, District Lalmonirhat. | M/S fahim Traders, Kurigram Sadar, Kurigram. | 0 | 2185 | 2.19 | 0 | 16143845 | 0 | 16143845 | 13964438.783 | 0 | 13964438.783 |  |  | 28-03-19 | 11-04-19 | 2019-04-18 | 2020-03-17 |  | 02-04-2020 16-01-2021 | 100% | 10949389 |  | 10949389 | 1694506 |  | 1694506 | 12643895 | 90.54% | ফাইনাল বিল পেশ করেছেন এবং ব্যংক গারান্টি বৃ্ধি করেছেন 16/01/2021 ইং পর্যন্ত। | #VALUE! | 2 | 183.682 | 341 | 0.29326 | 640 | 187.7% | 100% | 100% | 0%
| 2019-20 | Lalmonirhat | Hatibandha | Union Road-BC | PRO/LAL/HATI/UNR/19-20/W-78 | 152333016 | Improvement of Bituminous carpeting Road Sadhur Bazar-Guddimari Road at Ch: 1500m-3700m including Construction of 4Nos 1x 0.90mX0.900 m RCC Box Culvert at Ch: 2475m,2600m,3200m & 3640.00m and 1Nos 1x 2.0mX1.50 m RCC Box Culvert at Ch: 3030m Under Hatibandha Upazila ,District Lalmonirhat | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 1500 | 3700 | 2.2 | 5.2 | 21913908 | 1485646 | 23399554 | 19276008.958 |  | 19276008.958 |  |  | 18-03-20 | 2020-04-15 | 2020-04-22 | 2021-04-21 |  | 2021-07-22 | 5% |  |  | 0 |  |  | 0 | 0 | 0% | প্যালাসাইডিং এর পোষ্ট এর কাজ চলমান। প্রি-ওয়াক নেওয়া হবে। |  | 3 | 275.523 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Union Road-BC; 7: 152333018; 8: Patikapara up office to Dauabari up office |  | 2 | 183.682 | [6 empty] | 0%
| 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-57 | 152703020 | Improvement of Bituminous carpeting Road Jongra UP office (Futir Doba) to Sofinagadhat Road at Ch 00m-1000m. Under Patgram Upazila, District Lalmonirhat. | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 0 | 1000 | 1 | 0 | 8219318 | 0 | 8219318 | 7397386.2 |  | 7397386.2 |  |  | 2020-01-21 | 2020-02-18 | 2020-02-25 | 2021-02-24 |  | 2020-08-03 | 90% | 4224330 |  | 4224330 | 673992 |  | 673992 | 4898322 | 66.22% | WveøyweGg G KvR Pjgvb¦ |  | 1 | 91.841 | 372 | 0.26882 | 327 | 87.9% | 87.9% | 90% | -2.097%
| 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-55 | 152703019 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Kabarstanhat to Lalitarhat Kuchlibari UP Road at Ch: 1435m-3435m including Construction of 4Nos (1x2.00x1.50)m RCC.Box Culvert and 1 No (2x4.50x2.50)m RCC.Box Culvert Under Patgram Upazila ,District Lalmonirhat . | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 1435 | 3435 | 2 | 20.5 | 15769651 | 5125861 | 20895512 | 18805960.8 |  | 18805960.8 |  |  | 2020-02-12 | 2020-02-18 | 2020-02-25 | 2021-02-24 |  | 2021-08-15 | 30% | 4857995 |  | 4857995 | 786775 |  | 786775 | 5644770 | 30.02% | সাববেজ চলমান |  | 2 | 183.682 | 372 | 0.26882 | 327 | 87.9% | 87.9% | 30% | 57.9%
| 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-56 | 152703007 | Improvement of Bituminous carpeting Road on Kamerarhat Sreerampur UP via Dr.Hamidur Islam House Road at Ch: 900m-1995m Under Patgram Upazila ,District Lalmonirhat . | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 900 | 1995 | 1.095 | 0 | 9842242 | 0 | 9842242 | 8858017.8 |  | 8858017.8 |  |  | 2020-01-21 | 2020-02-28 | 2020-02-25 | 2021-02-24 |  | 2020-03-08 | 90% | 6795161 |  | 6795161 | 1071996 | 0 | 1071996 | 7867157 | 88.81% | WveøyweGg G KvR Pjgvb¦ |  | 1 | 91.841 | 362 | 0.27624 | 317 | 87.57% | 87.57% | 90% | -2.431%
2: 2019-20; 3: Lalmonirhat; 4: Hatibandha; 5: Village Road-BC; 6: PRO/LAL/HATI/VR/19-20/W-127; 7: 152334090; 8: Improvement of Singimari Nebru House-Uttor Baraipara Masque Rd. Road Ch: 1150m -3260m including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch: 2122 m & 2952m Under Upazila: Hatibandha, District:Lalmonirhat.; 10: 1150; 11: 3260; 12: 2.11; 13: 2.7; 14: 18321870; 15: 447885; 16=14+15: 18769755; 37: Estimate approved on June-20 |  | 2 | 172.8424 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Village Road-BC; 7: 152335023; 8: Singmari UP office-Goddimari UP. Border |  | 3 | 259.2636 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Village Road-BC; 7: 152335059; 8: Hatibandha U.Z.R. at dhubni mauza to dhubni Madrasha . |  | 2 | 172.8424 | [6 empty] | 0%
| 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-77 | 152704084 | Improvement of Bituminous carpeting Road on Kasirdanga-Bazar to 3 no Vothatkhata GPS Road at Ch: 00m-2000m including Construction of 6Nos 1x1.50x1.00 m RCC Box Culvert at Ch: 830m, 870m,1120m, 1200m,1566m &1800m and 3Nos 1x3.00x2.00 m RCC Box Culvert under Patgram Upazila ,District Lalmonirhat | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 0 | 2000 | 2 | 15.5 | 20081664 | 3573248 | 23654912 | 19520208.282 |  | 19520208.282 |  |  | 18-03-20 | 15-04-2020 | 22-04-2020 | 21-04-2021 |  | 24-03-2021 | 15% |  |  | 0 |  |  | 0 | 0 | 0% | Sand filling চলমান। |  | 2 | 172.8424 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Village Road-BC; 7: 152705132; 8: MD. Obrotulla House More - Lolitarhat High School. |  | 1 | 86.4212 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Village Road-BC; 7: 152705013; 8: Nabinagar BOP-Shofinogre Hat |  | 2 | 172.8424 | [6 empty] | 0%
| 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-76 | 152705059 | Improvement of Bituminous carpeting Road on Nayerhat Mosque to Zero point of Dhagram UP Road at Ch: 1000m-4000m including construction of 1Nos 1x2.00x2.50 m RCC Box Culvert at Ch: 1310m Under Patgram Upazila ,District Lalmonirhat | Md. Abdul Hossain, Ghoramara Rangpur. | 1000 | 4000 | 3 | 2.5 | 24550502 | 648343 | 25198845 | 21141830.755 |  | 21141830.755 |  |  | 18-03-20 | 30-04-20 | 2020-07-05 | 2021-06-02 |  | 29-04-21 | 20% | 3719537 |  | 3719537 | 611363 |  | 611363 | 4330900 | 20.48% | 500m সাববেজ চলমান |  | 3 | 259.2636 | [6 empty] | 0%
| 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-75 | 152705121 | Improvement of Bituminous carpeting Road on Lolitarhat – Liakot Prodhan House Via Kolshirmuk BOP & Graipul Road at Ch: 4000m-4950m Under Patgram Upazila ,District Lalmonirhat | GRP & RT (ZV), GL Roy Road, Rangpur. | 4000 | 4950 | 0.95 |  | 8246152 |  | 8246152 | 6982029.537 |  | 6982029.537 |  |  | 18-03-20 | 15-04-20 | 22-04-20 | 21-04-21 |  | 24-12-20 | 65% | 3832304 |  | 3832304 | 572449 |  | 572449 | 4404753 | 63.09% | সাববেজ চলমান |  | 2 | 172.8424 | [6 empty] | 0%
2: 2020-21; 3: Lalmonirhat; 4: Hatibandha; 5: Village Road-HBB; 6: PRO/LAL/HATI/VR-HBB/20-21/W-139; 7: 152334018; 8: Improvement of Karbalardighi R&H Road-Dakhalibandha Hat Road. Road Ch: 0.00m-2550.00m including Construction of 2Nos 2.00m x 1.50m Box culvert on Karbalardighi R&H Road-Dakhalibandha Hat Road. C/D st Ch: 1072 m & 2500m. Under Upazila: Hatibandha, District:Lalmonirhat.; 10: 0; 11: 2550; 12: 2.55; 13: 5; 14: 14089742; 15: 1470868; 16=14+15: 15560610; 37: Estimate approved on 16-8-20 |  | 2.64 | 153.0144 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Village Road-HBB; 7: 152704017; 8: Tangtindanga hat-H/O Khairul Islam |  | 3.2 | 185.472 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Large Market; 8: Nayer Hat |  |  | 62.7 | [6 empty] | 0%
2: 2020-21; 3: Lalmonirhat; 4: Hatibandha; 5: Large Market; 6: PRO/LAL/HAT/LM/20-21/W-134; 8: Construction of Muktijoddha Bazar (LCS-1,2,3); 16=14+15: 6206548; 37: Estimate approved on 13-8-20 |  |  | 62.7 | [6 empty] | 0%
2: 2020-21; 3: Lalmonirhat; 4: Patgram; 5: Medium Market; 6: PRO/LAL/PAT/MM/20-21/W-132; 8: Construction of Sharkarar Hat (LCS-1,2,3); 16=14+15: 7971629; 37: Estimate approved on 13-8-20 |  |  | 41.77 | [6 empty] | 0%
2: 2019-20; 3: Lalmonirhat; 4: Patgram; 5: Medium Market; 6: PRO/LAL/PAT/MM/2019-20/W-67; 8: Construction of Shafinagar Hat, Upazila: Patgram, District: Lalmonirhat; 16=14+15: 1025309; 19=17+18: 1025309; 23: 2020-10-07; 28: 0%; 29: 377500; 31=29+30: 377500; 34=32+33: 0; 35=31+33: 377500; 36: 36.82%; 37: অগ্রিম কিস্তি 50% প্রদান করা হয়েছে। ভ্যাট, আইটি, ল্যাব ও 10% ঠিকাদারের মুনাফা কেটে রাখা হয়েছে। (5,00,000.00 টাকার চাহিদার মধ্যে)। Est Approved on 21-11-19 |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Medium Market; 8: Burimari Hat |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Medium Market; 8: Kadhidanggahat |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Patgram; 5: Medium Market; 8: Loliterhat |  |  | 41.77 | [6 empty] | 0%
2: 2019-20; 3: Lalmonirhat; 4: Patgram; 5: Medium Market; 6: PRO/LAL/PAT/MM/2019-20/W-63; 8: Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat; 16=14+15: 1760898; 19=17+18: 1760898; 37: LCS Training Completed. Contract will be signed soon, Est Approved on 21-11-19 |  |  | 41.77 | [6 empty] | 0%
2: 2019-20; 3: Lalmonirhat; 4: Patgram; 5: Medium Market; 6: PRO/LAL/PAT/MM/2019-20/W-64; 8: Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat; 16=14+15: 1494432; 19=17+18: 1494432; 37: LCS Training Completed. Contract will be signed soon, Est Approved on 21-11-19 | [9 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Shaniajan New bazar |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Shaniajan bazar |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Cheatnai Hat |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Shadur Bazar |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Ghunti Bazar |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Dighirhat Bazar; 37: বাজার পরিদর্শন করে চুড়ান্ত মাষ্টার প্লান সংশ্লিষ্ট ব্যক্তিবর্গের মতামত গ্রহন করে পরবর্তী প্রয়োজনীয় ব্যবস্থা গ্রহনের জন্য প্রকল্প মহোদয় বরাবর প্রেরন করা হয়েছে। |  |  | 41.77 | [6 empty] | 0%
2: 2020-21; 3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 6: PRO/LAL/HAT/MM/20-21/W-133; 8: Construction of Nawdabash Hat (LCS-1,2,3); 16=14+15: 6855792; 37: Estimate approved on 13-8-20 |  |  | 41.77 | [6 empty] | 0%
3: Lalmonirhat; 4: Hatibandha; 5: Medium Market; 8: Jawranihat Bazar |  |  | 41.77 | [6 empty] | 0%
| 2020-21 | Lalmonirhat | Hatibandha | Maintenance-LCS | PRO/LAL/PAT/RMP/20-21/ MW-131 | 152703020 152705151 152705098 | i) Jongra UP office (Futir Doba) to Shafinagar hat road. Ii) Aftab More to Shofinogorhat via Hosnabad Community Clinic & Mokbul Jahanara Hossain GPS road. iii) Olerpar to Dahagram Chairman bari road. |  | 0 - 0 | 1000 - 1500 | 3.17 |  | 2012485.14 |  | 2012485.14 | [20 empty] | Estimate approved on July-20
| 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/18-19/W-03 | 152705151 | Improvement of Bituminous Carpeting Road on Altab More to Safinagarhat via Hasnabad Community Clinik & Mokbul Jahanara Hossin GPS at Ch. 700-1700m. Under Patgram Upazila, District Lalmonirhat. | M/S RML Enterprise, Hatibandha, Lalmonirhat. | 700 | 1700 | 1 | 0 | 6975415 | 0 | 6975415 | 6626644.25 | 0 | 6626644.25 |  |  | 2019-02-24 | 2019-03-18 | 2019-03-25 | 2020-03-24 |  | 2020-09-03 | 100% | 0 |  | 0 | 6625297 |  | 6625297 | 6625297 | 99.98% | ফাইনাল বিল হয়েছে। জামানত প্রদান করা হয়েছে। | 163 | 1 | 86.4212 | 372 | 0.26882 | 664 | 178.5% | 100% | 100% | 0%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR//18-19/W-04 | 152335060 | Improvement of Niz Sheck Sundor Jameh Mosue Applax Embankment road. Ch. 500m-1765m. including Construction of 7.00x0.900mx 0.900m Cross drain at Ch. 995m under Hatibandha Upazila, District Lalmonirhat. | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 500 | 1765 | 1.265 | 0.9 | 9940910 | 179692 | 10120602 | 8683000.48 | 156906.643 | 8839907.122 |  |  | 2019-03-28 | 2019-04-11 | 2019-04-18 | 2020-03-17 |  | 2020-04-09 | 100% | 0 | 0 | 0 | 8682822.84 | 156906.64 | 8839729.48 | 8839729.48 | 100% | ফাইনাল বিল হয়েছে। ‡cf‡g›U Gi mKj †jqv‡ii KvR mgvß n‡q‡Q¦ BD‡Wªb Gi KvR mgvß n‡q‡Q¦‡cÖv‡Uw±f IqvK© Gi KvR †kl n‡q‡Q, Nvm jvMv‡bv nqwb¦ mg¯Í wej wRIwe n‡Z cÖ`vb Kiv i‡q‡Q¦ | 23 | 2 | 172.8424 | 341 | 0.29326 | 640 | 187.7% | 100% | 100% | 0%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-05 | 152334015 | Improvement of Bituminous Carpeting Road on WAPDA Pucea road to Dimla Bordar road at Ch.0.00m-3000.0m. including Construction of 2.00x 2.00 Cross drain at Ch. 2415.00m and Construction of 2 Nos 7x0.900mx0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | M/S Islam Traders, Ghop Jossor, Lalmonirhat. | 0 | 3000 | 3 | 4.2 | 26653905.62 | 966016.9 | 27619922.52 | 23524180.35 | 880651.833 | 24404832.183 |  |  | 2019-03-28 | 2019-04-10 | 2019-04-17 | 2020-09-01 |  | 2020-10-01 | 98% | 18845417 |  | 18845417 | 3341965 |  | 3341965 | 22187382 | 90.91% | কার্পেটিং শেষ। টার্পিং এর কাজ চলমান। | 30 | 3 | 259.2636 | 510 | 0.19608 | 641 | 125.7% | 100% | 98% | 2%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/ HATI/VR/18-19/W-33 | 152335034 | Improvement of Bituminous carpeting Road on Patikapara Dowabari Up Boder To Kapil Member house Road at Ch. 00-1000m. including Construction of 2.00 Nos 0.900m x 0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | Borsha Enterprise, Patgram, Lalmonirhat | 0 | 1000 | 1 | 1.8 | 7409383.06 | 359383.98 | 7768767.04 | 7020944.669 | 359383.981 | 7380328.65 |  |  | 2019-04-16 | 2019-04-30 | 2019-06-10 | 2020-06-09 |  | 2020-07-28 | 97% | 5735704.6 | 359366.44 | 6095071.04 | 1036149 | 0 | 1036149 | 7131220.04 | 96.62% | ‡cf‡g›U Gi mKj ‡jqv‡ii KvR mgvß¦ gvwU I Uvwc©s Gi KvR Aviv¤¢ Ki‡e¦¦জামানত ‡`Iqv n‡q‡Q¦ | 49 | 1 | 86.4212 | 406 | 0.24631 | 621 | 153% | 100% | 97% | 3%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-34 | 152334068 | Improvement of Bituminous carpeting Road on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat. including(D): Construction of 2.00 Nos (2.50x2.50) m Cross Drainges Structure on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat.(Structure)(E): Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat. (Structure) | Anta & SH ZV, Patgram, Lalmonirhat | 0 | 2000 | 2 | 8 | 14532903 | 3136442 | 17669345 | 12863063.52 | 2771524.493 | 15634588.013 |  |  | 2019-05-29 | 2019-06-09 | 2019-06-10 | 2019-11-09 |  | 2019-12-05 | 100% | 12100676 | 0 | 12100676 | 1937636 | 0 | 1937636 | 14038312 | 89.79% | ফাইনাল বিল পেশ করেছেন | 26 | 2 | 172.8424 | 153 | 0.65359 | 581 | 379.7% | 100% | 100% | 0%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-35 | 152334088 | Improvement of Bituminous carpeting Road R&H Nowabab Uddin House-Laxmi Kanto Chokider House at Ch.0.00m-1000.00m. including Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure at Ch.661.00m. Under Hatibanhda Upazila, District Lalmonirhat. | Nakshi Mobail Palace, Sadar, Kurigram | 0 | 1000 | 1 | 3 | 7141226.17 | 1123449 | 8264675.17 | 6784164.9 | 1067276.417 | 7851441.317 |  |  | 2019-04-16 | 2019-05-14 | 2019-05-21 | 2020-03-01 |  | 2020-04-27 | 100% | 5437695.58 | 1067276.42 | 6504972 | 918412 | 0 | 918412 | 7423384 | 94.55% | ফাইনাল বিল হয়েছে। | 57 | 1 | 86.4212 | 292 | 0.34247 | 607 | 207.9% | 100% | 100% | 0%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-36 | 152335033 | Improvement of Bituminous carpeting Road Paschim Bisondai Mouza To Sattar Chairman House Road Ch 0.00m-2000.00m including Construction of 4.00 Nos 7.00x0.900x0.900 Cross drain At Ch.113m, 417m, 1280m, &2560m Under Hatibandha Upazila, District Lalmonirhat. | M/S Alahi Box, Kaligonj, Lalmonirhat | 0 | 2000 | 2 | 3.6 | 14144485 | 858869.5 | 15003354.5 | 12406869.348 | 645062.75 | 13051932.098 |  |  | 2019-06-17 | 19-06-19 | 2019-06-26 | 2020-05-25 |  | 2020-06-02 | 98% | 9654532.99 | 551528.01 | 10206061 | 1560362.01 | 93533.99 | 1653896 | 11859957 | 90.87% | ‡cf‡g›U Gi mKj ‡jqv‡ii KvR mgvß¦ †cÖv‡Uv±f IqvK© Gi KvR n‡e bv, Kvib Ab¨ cÖKí n‡Z eªxR n‡e¦¦ BD †Wªb Gi KvR mgvß n‡q‡Q¦ | 8 | 2 | 172.8424 | 341 | 0.29326 | 571 | 167.4% | 100% | 98% | 2%
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-45 | 152335061 | Improvement of Bituminous carpeting Road on Applax Badth to Dimla Border Road at Ch 0.00m-1800.0m including Construction of 3.00 Nos 0.900 X 0.900 Cross drain at Ch. 400.00m, 700.00m & 1000.00m on Applax Badth to Dimla Border Road. Under Hatibanhda Upazila, District Lalmonirhat. | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 0 | 1800 | 1.8 | 2.7 | 12752649 | 555765.89 | 13308414.89 | 11139339.451 | 435687.765 | 11575027.216 |  |  | 2019-07-08 | 2019-07-24 | 2019-07-31 | 2020-06-16 |  | 2020-07-15 | 100% | 8908214 |  | 8908214 | 1460261 |  | 1460261 | 10368475 | 89.58% | ফাইনাল বিল প্রেরন করেছেন। | 29 | 1.8 | 155.5582 | 328 | 0.30488 | 536 | 163.4% | 100% | 100% | 0%
| 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-46 | 152704023 | Improvement of Bituminous carpeting Road on Sarkarerhat Mosque to Borovita at Ch 0.00m-2500.0m. Under Patgram Upazila, District Lalmonirhat. | Fahim Traders, Kurigram Sadar, Kurigram | 0 | 2500 | 2.5 |  | 18846970 |  | 18846970 | 16388604.17 |  | 16388604.17 |  |  | 2019-07-08 | 2019-07-24 | 2019-07-31 | 16-06-2020 31-12-2020 (xen sent time ext. prayer) |  | 2020-07-16 | 70% | 0 |  | 0 | 10715326 |  | 10715326 | 10715326 | 65.38% | XEN issued letter to Contractor RE: Time ext./performance Security WvweøDweGg Gi KvR Pigvb¦ | #VALUE! | 2.5 | 216.053 | #VALUE! | #VALUE! | 536 | #VALUE! | #VALUE! | 70% | #VALUE!
| 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-47 | 152704034 | Improvement of Bituminous carpeting Road Dhobolsuti Mosque to Kamararhat Road at Ch 0.500m-3050.0m. Under Patgram Upazila, District Lalmonirhat. | Fahim Traders, Kurigram Sadar, Kurigram | 500 | 3050 | 2.55 |  | 18895406 |  | 18895406 | 16408287.34 |  | 16408287.34 |  |  | 2019-07-08 | 2019-07-24 | 2019-07-31 | 16-06-2020 31-12-2020 (xen sent time ext. prayer) |  | 2020-07-16 | 65% | 0 | 0 | 0 | 9393335.62 |  | 9393335.62 | 9393335.62 | 57.25% | XEN issued letter to Contractor RE: Time ext./performance Security সাববেজ চলমান | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 536 | #VALUE! | #VALUE! | 65% | #VALUE!
3: Jamalpur; 4: Dewanganj; 5: Union Road-BC; 7: 339153005; 8: Chikajani Up- Charmaguri hat road |  | 2 | 183.682 | [6 empty] | 0%
| 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-99 | 339153005 | Rural road maintenance by LCS (Material & Wages) work on Chikajani UP Office to Chirmashuri Hat Sarak at Ch. 0.00-7500.00m Dewangonj Upazila, Jamalpur District (15 nos LCS worker) |  | 0 | 7500 | 7.5 |  |  |  | 3466985 | [20 empty] | LCS group formed. Contact will be signed by this month. Estimate Approved on 5-3-20
3: Jamalpur; 4: Dewanganj; 5: Union Road-BC; 7: 339153016; 8: Kharma Naya Bazar RHD-TilokpurMollapara |  | 2 | 183.682 | [6 empty] | 0%
| 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-100 | 339153016 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD-Tilokpur Mollapara Sarak at Ch. 0.00-2190.00m Dewangonj Upazila, Jamalpur district (4 nos LCS worker) |  | 0 | 2190 | 2.19 |  |  |  | 844565 | [20 empty] | LCS group formed. Contact will be signed by this month. Estimate Approved on 5-3-20
3: Jamalpur; 4: Dewanganj; 5: Union Road-BC; 7: 339153011; 8: Dangdhara UP-Bottola Bazar. |  | 2 | 183.682 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Union Road-BC; 7: 339613007; 8: Ghoserpara UP (Beltoi Bazar)-Charshaguna Bazar Road. |  | 3.45 | 316.8514 | [6 empty] | 0%
3: Jamalpur; 4: Bakshigonj; 5: Union Road-BC; 7: 339073012; 8: Merurchar UP Office - Jabbergonj GC via Chinarchar Gudaraghat road |  | 1.7 | 156.1297 | [6 empty] | 0%
| 2018-19 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/18-19/W-29 | 339075094 | Improvement of Bituminous carpeting Road on Airmari-Kamalerbarti Road at Ch.00.0-2850.0m including Contruction Of 1 Nos.(3.50x2.50) Cross Drainges Structure at Ch.1290.0m and Contruction Of 2 Nos.U-Drain at Ch.140m,1915m Under Bakshiganj Upazila, District Jamalpur. | M/S. Lokman Hossain, 987, Choybaria, Gokornoghat, Brahmanbaria | 0 | 2850 | 2.85 | 5.3 | 26012268 | 1488161 | 27500429 | 25428918.47 | 1405081.53 | 27735520 | 901520 | 28637040 | 2019-05-15 | 2019-05-27 | 2019-06-02 | 01-06-2020 15-02-2021 |  | 2020-08-20 | 30% | 5048909 | 0 | 5048909 | 366372 | 0 | 366372 | 5415281 | 18.91% | Protective work on going | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 594 | #VALUE! | #VALUE! | 30% | #VALUE!
| 2018-19 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/18-19/W-30 | 339075012 | Improvement of Bituminous carpeting Road on Gazirpara-Derur Bill Road at Ch.00.0-2000.0m Under Bakshiganj Upazila, District Jamalpur. including Contruction Of 1 Nos. U-Drain on Gazirpara-Derur Bill Road at Ch.1640.0m Under Bakshiganj Upazila, District Jamalpur. | M/S. Bilkis Enterprise Melandah, Jamalpur. | 0 | 2000 | 2 | 0.6 | 17514896.19 | 106751 | 17621647.19 | 15704206.21 | 95866.95 | 15800073.16 | 2293635.84 | 18093709 | 2019-06-15 | 2019-06-27 | 2019-07-03 | 02-07-2020 31-12-2020 |  | 2024-06-26 | 100% | 14989602 |  | 14989602 | 1493260 |  | 1493260 | 16482862 | 91.1% | Final bill paid | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 563 | #VALUE! | #VALUE! | 100% | #VALUE!
| 2018-19 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ ISL/VR/18-19/W-31 | 339294014 | Improvement of Bituminous carpeting Road on Bulakipara-Goalaerchar Road at Ch.00.0-2800.0m Under Islampur Upazila, District Jamalpur. including Contruction Of 5 Nos.0.600x0.625 U-Drain on Bulakipara-Goalaerchar Road at 552m, 570m, 790m, 865m & 1350m Under Islampur Upazila, District Jamalpur. | M/S. Bilkis Enterprise Melandah, Jamalpur. | 0 | 2800 | 2.8 | 3 | 21880314 | 487259 | 22367573 | 20176056.34 | 449424.22 | 20625480.56 | 1793382.44 | 22418863 | 2019-06-15 | 2019-06-27 | 2019-07-03 | 02-07-2020 31-12-2020 |  | 2024-06-26 | 75% | 12771102 | 0 | 12771102 | 159768 | 0 | 159768 | 12930870 | 57.68% | Earth work on going | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 563 | #VALUE! | #VALUE! | 75% | #VALUE!
| 2018-19 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/18-19/W-32 | 339615037 | Improvement of Bituminous carpeting Road on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.00.0-1560m including Contuction Of 1 Nos.( 2x3.50x3.00m ) Cross Drainges Structure at Ch.887.0m and Contuction Of 1 Nos. (2x4.5x4.00m) Cross Drainges Structure at Ch.1219.0m and Contruction Of 6 Nos.0.750x0.750 RCC U-Drain on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.279m,705m,1082m,1139m,1281m,1377m Under Melandah Upazila, District Jamalpur. | M/S. Masum Constrution Chapatali, Sherpur Town, Sherpur. | 0 | 1560 | 1.56 | 22.6 | 16109475 | 6116386 | 22225861 | 14960841.55 | 3274302.46 | 18235144.01 | 1311883 | 19547027.01 | 2019-06-16 | 2019-06-30 | 2019-07-06 | 27-05-2020 31-11-2020 |  | 25-06-2020 27-12-2020 | 50% | 5581363 | 0 | 5581363 | 332634 | 0 | 332634 | 5913997 | 30.26% | Sub Grade test has been done at 1-3-20 | #VALUE! | 1.53 | 132.2244 | #VALUE! | #VALUE! | 560 | #VALUE! | #VALUE! | 50% | #VALUE!
| 2018-19 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/18-19/W-37 | 339154040 | Improvement of Bituminous carpeting Road on Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. including Construction Of 1 Nos.0.600mx0.625m U-Drain on Ch.1236.0m Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 930 | 2880 | 1.95 | 0.6 | 17332023 | 139931 | 17471954 | 14553724.76 | 117499.838 | 14671224.598 | 0 | 14671224.598 | 2019-05-30 | 2019-06-12 | 2019-06-18 | 13-05-2020 31-12-2020 |  | 2020-06-11 | 85% | 7218025 | 0 | 7218025 | 1151557 | 0 | 1151557 | 8369582 | 57.05% | 1 km WBM Complete and 0.95km maintenance stoped | #VALUE! | 2 | 172.8424 | #VALUE! | #VALUE! | 578 | #VALUE! | #VALUE! | 85% | #VALUE!
| 2018-19 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/18-19/W- 38 | 339154029 | Improvement of Bituminous carpeting Road on Bhatkhawa RHD-Amkhowa Bazar Road at Ch.0.00-3250.0m including Construction Of 1 Nos. 3.00x3.00 Cross Drainges Structure Bhatkhawa RHD-Amkhowa Bazar Road at Ch.512.0m Under Dewangonj Upazila, District Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 0 | 3250 | 3.25 | 3 | 29145742 | 1305867 | 30451609 | 24564023.395 | 1130084.458 | 25694107.853 | 531265.15 | 26225373.003 | 2019-05-30 | 2019-06-12 | 2019-06-18 | 13-05-2020 05-05-2021 |  | 2020-06-11 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Revised estimate decision pending | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 578 | #VALUE! | #VALUE! | 30% | #VALUE!
| 2019-20 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/19-20/W- 86 | 339154027 | Improvement of BC Road from Khorma naya Bazar via Vatipara Road from ch. 1300-2120.0m including 2Nos U-Drain (600X600mm) under Upazila Dewangonj, District- Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 1300 | 2120 | 0.82 | 2 | 7630923 | 211222 | 7842145 | 7057930.5 |  | 7057930.5 |  |  | 2020-02-24 | 2020-03-04 | 2020-03-10 | 2020-09-09 |  | 2020-12-30 | 20% | [10 empty] | 3 | 259.2636 | [5 empty] | 20% | -20%
| 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-101 | 339154027 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD- Molomgonj Bazar Vhatipara Sarak at Ch. 0.00-1500.00m Dewangonj Upazila, Jamalpur District (3 nos LCS worker) |  | 0 | 1500 | 1.5 |  |  |  | 630474 | [20 empty] | LCS group formed. Contact will be signed by this month. Estimate Approved on 5-3-20
| 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-102 | 339152003 | Rural road maintenance by LCS (Material & Wages) work on Pathorerchar RHD - Sanandabari GC Road at Ch. 0.00-1000.00m Dewangonj Upazila, Jamalpur District (2 nos LCS worker) |  | 0 | 1000 | 1 |  |  |  | 420383 | [20 empty] | LCS group formed. Contact will be signed by this month. Estimate Approved on 5-3-20
| 2019-20 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/19-20/W-88 | 339154032 | Improvement of BC Road from Chakpara FRB - Sharkerpara FRB via Amkhowa Bazar road from ch. 700.00-3340.00m including Construction of 8 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-3-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert under Upazila Dewanganj, District- Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 700 | 3340 | 2.64 | 43.22 | 29816655 | 13631951 | 43448606 | 38202193.5 |  | 38202193.5 |  |  | 2020-04-26 | 2020-04-29 | 2020-05-05 | 2021-05-04 |  | 2025-04-30 | 0% | [8 empty] | WO Issued |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Village Road-BC; 7: 339584061; 8: Teguria Bazar-Pakrul- Kolikandi Road |  | 3 | 259.2636 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Village Road-BC; 7: 339585035; 8: Nobbachar Bazar- Taguria h/o Khalek via Hidagari road. |  | 3 | 259.2636 | [6 empty] | 0%
| 2019-20 | Jamalpur | Madargonj | Village Road-BC | PRO/JAM/MAD/VR/19-20/W-85 | 339585030 | Improvement of BC Road from Gabergram Bazar Embankment- Bafatuddin Talukder High School road from ch. 3150-6240.00m including Construction of 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 2Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 2 Nos U-Drain(600X 600mm)under Upazila Madarganj, District- Jamalpur | M/S. Bilkis Enterprise & Md. Mizanur Rahman, Maderganj, Jamalpur. | 3150 | 6240 | 3.09 | 21.37 | 41239211 | 7541224 | 48780435 | 40250008.29 |  | 40250008.29 |  |  | 2020-04-26 | 2020-05-13 | 2020-05-19 | 2021-05-18 |  | 2021-08-05 | 10% | [10 empty] | 3 | 259.2636 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Village Road-BC; 7: 339584060; 8: Jonail-Koira UZR(Bow Bazar)-Khilkati via Purbo Shokhnagari |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Bakshigonj; 5: Village Road-BC; 7: 339075096; 8: Battajure Nuton Bazar-Battajore Paschimpara via Shamisaya school road |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Bakshigonj; 5: Village Road-BC; 7: 339074011; 8: Gazirpara-Kamalerbatti road. |  | 3 | 259.2636 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Village Road-BC; 7: 339615106; 8: Mahmudpur Bazar - Adbaria H/o Shanbania Via Purba Mahamudpur GPS Road. |  | 1.9 | 164.2003 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Village Road-BC; 7: 339614111; 8: Mahmudpur bazar-Imampur H/O Shahjahan member Road |  | 1 | 86.4212 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Village Road-BC; 7: 339615108; 8: Mahmudpur Bazer - Imampur UZR Road. |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Village Road-BC; 7: 339615107; 8: Nalsia (Khashimara) - Utter Khashimara GPS Road. |  | 1.3 | 112.3476 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Village Road-BC; 7: 339615072; 8: Bhaluka More UZR - Chinitola GPS Road. |  | 1.5 | 129.6318 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Village Road-BC; 7: 339614030; 8: Khashimara bazar-Purarchar(Shahin Bazar) Road. |  | 2.5 | 216.053 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339295009; 8: Deghair - Bhangbari Road |  | 2.5 | 216.053 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339295032; 8: Char Deghair Dakhil Madrasha-Mohez Mulla house road |  | 2.5 | 216.053 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339295033; 8: Char Shisua GPS-Changania RNGPS via Degahir road- |  | 3 | 259.2636 | [6 empty] | 0%
| 2019-20 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/19-20/W-83 | 339294035 | Improvement of BC Road from Napiterchar High School-Chandanpur village via Dasani Ferry Ghat road at ch. 00- 3000m. Including Construction of 2 Nos 1x0.600mx0.600m m U-Drain and 2 Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-2-vent-4.50m X 4.00m RCC Box Culvert under Islampur Upazila, District Jamalpur. | LE &ME (JV) Islampur, Jamalpur | 0 | 3000 | 3 | 21.28 | 32150814 | 7303197 | 39454011 | 33896614.39 | 0 | 33896614.39 |  |  | 2020-04-26 | 2020-05-20 | 2020-05-26 | 2021-05-08 |  | 2021-05-06 | 25% | 4863211 |  | 4863211 |  |  | 0 | 4863211 | 14.35% |  |  | 3 | 259.2636 | [6 empty] | 0%
| 2019-20 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/19-20/W-84 | 339294067 | Improvement of BC Road from Dattapara R&H - Napiterchar Bazar via Adorsha Gramm road at ch. 00-3000.00m including Construction of 1 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 1Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-3-vent-4.50m X 4.50m RCC Box Culvert under Upazila Islampur, District- Jamalpur | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 0 | 3000 | 3 | 30.56 | 33480233 | 10347691 | 43827924 | 36997789.33 | 0 | 36997789.33 |  |  | 2020-04-26 | 2020-05-20 | 2020-05-26 | 2021-04-27 |  | 2021-05-06 | 10% | [10 empty] | 3 | 259.2636 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339294085; 8: Kazla-Kathma Bazar road. |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339295017; 8: Kazla Kamar bari-Horindhora road. |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339294087; 8: Malmara Bazar-Napiterchar Bazar road. |  | 2 | 172.8424 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Village Road-BC; 7: 339294008; 8: Malmara - Bulakipara road. |  | 3 | 259.2636 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Large Market; 8: Mahmudpur |  |  | 62.7 | [6 empty] | 0%
2: 2019-20; 3: Jamalpur; 4: Madargonj; 5: Large Market; 6: PRO/JAM/MAD/ LM/19-20/W- 126; 8: Construction of Milon Bazar Upazila: Madarganj, Dist:Jamalpur (02 nos LCS group); 9: LCS-1, LCS-2; 16=14+15: 6013382; 37: LCS group formed. Contact will be signed by this month. Estimate Approved on 5-3-20 |  |  | 62.7 | [6 empty] | 0%
3: Jamalpur; 4: Dewanganj; 5: Large Market; 8: Khorma bazar |  |  | 62.7 | [6 empty] | 0%
3: Jamalpur; 4: Dewanganj; 5: Large Market; 8: Jhalur Char |  |  | 62.7 | [6 empty] | 0%
3: Jamalpur; 4: Dewanganj; 5: Large Market; 8: Sanandabari |  |  | 62.7 | [6 empty] | 0%
3: Jamalpur; 4: Dewanganj; 5: Large Market; 8: Molla Para Bazar |  |  | 62.7 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Bhabki Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Talukpara Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Jhawgora Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Gazipur Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Shahin Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Char Gobindi Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Nalsia bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Millon Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Millon Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Saguna Bzar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Kahetpara bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Tegharia Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Medium Market; 8: Gobindoganj Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Medium Market; 8: Duttapara Ananda Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Bakshigonj; 5: Medium Market; 8: Gazirpara Annanda Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Bakshigonj; 5: Medium Market; 8: parchim kamalerbatti Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Medium Market; 8: Nabbo Char Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Medium Market; 8: Teguria bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Medium Market; 8: Rayerchara Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Madargonj; 5: Medium Market; 8: Koali Kandi Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Dewanganj; 5: Medium Market; 8: Amkhowa Bazar |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Dewanganj; 5: Medium Market; 8: Char Maguri Hat |  |  | 41.77 | [6 empty] | 0%
3: Jamalpur; 4: Melandah; 5: Small Market; 8: Bhaluka(Tarankandi Bazar) |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Small Market; 8: Mondalpara Bazar |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Small Market; 8: Shirajabad Bazar |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Small Market; 8: Malmara Bazar |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Small Market; 8: Akota Bazar |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Small Market; 8: Napiterchar Bazar |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Islampur; 5: Small Market; 8: Bulakip (ara Bazar) |  |  | 26.11 | [6 empty] | 0%
3: Jamalpur; 4: Bakshigonj; 5: Small Market; 8: Merurchar |  |  | 26.11 | [6 empty] | 0%
0%
0%
0%
0%
0%
0%
0%
[6 empty] | Total packages: | 19 | Nos of Est. Pkgs: | 19 |  | 49.017 | 76.3 | 223124337.09 | 14266497 | 249272939.71 | 189788647.394 | 9318495.44 | 240561822.921 | 0 | 0 | [6 empty] | 76.17% | 105020725.59 | 21011307.41 | 67686354 | 17544604.77 | 3466672.23 | 11360095 | 147696260 | 56.76%
[6 empty] | Nos of Contract Signed: |  | NOS of Contract Signed: | 19 |  |  |  |  | NOS of Estimated packages: | 19 |  | NOS of Contract Signed: | 19 | [16 empty] | 61.4%
75200
198850
128350
175350
75200
652950

## Gaibandha
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Gaibandha
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
Union Road BC
1 | 2018-19 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/GAI-S/UNR/ 18-19/W-06 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3600m-4150m & 4496m-7600m. including Costruction of 10 U- drain (.600mx0.625m) Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3660m, 3984m, 4030m, 4073m, 5197m, 6115m, 6280m, 6695m, 7525m & 7591m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | M/S Basundhara, Kurigram | 3600.00 4496.00 | 4150.00 7600.00 | 3.654 | 6 | 29444723.57 | 991093.47 | 30435817.04 | 29438902.5 | 991097.41 | 30429999.91 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-04-21 | 0 | 2020-12-31 | 75% | 12094800 | 2302600 | 14397400 | 1934341 | 368259 | 2302600 | 16700000 | 54.88% | 1500m WBM Complete. 1200m AS Complete. ISG on going
2 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-09 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.0.00m-2.000m. including Costruction of 7 Nos U-Drain khorda Rasulpur-Chandiapur Road at Ch.85m, 526m, 880m, 925m, 1048m, 1343m, & 1835m. and 1Nos (2.00x2.00) m Cross Drainges Structure under khorda Rasulpur-Chandiapur Road at Ch.710.0m. Under Shdullapur, District Gaibandha. | Md.Khademul Islam Jewel, Gaibandha | 0 | 2000 | 2 | 6.2 | 16764810.71 | 1868067 | 18632877.71 | 17548454.17 | 1064613.71 | 18613067.88 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-09-17 | 0 | 2020-10-15 | 100% | 12173900 | 2288050 | 14461950 | 1926054 | 361996 | 2288050 | 16750000 | 89.99% | Work Complete
3 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-10 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.1235m-3235. including Costruction of 1 Nos U-Drain 0.600mx0.625m Mohisbandi-Mirpur Road at Ch.2725.0m.Under Shdullapur, District Gaibandha. | M/S SAJIN TRADERS JV | 1235 | 3235 | 2 | 0.6 | 17379171 | 145336 | 17524507 | 17391992.65 | 127964.94 | 17519957.59 | 0 | 0 | 2019-04-18 | 2019-05-08 | 2019-05-14 | 2020-03-21 | 0 | 2020-04-19 | 100% | 9841196 | 2228152 | 12069348 | 1840948 | 387204 | 2228152 | 14297500 | 81.61% | Work Completed
4 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-12 | 132823017 | Improvement of Bituminous Road on Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. Ch.2627m-3627m. including Costruction of 2 Nos U-Drain 0.600mx0.625m ,at Ch.2768m,3110m and Costruction of 1 Nos (2.00mx2.00m)Cross Drainges Structure Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. 3260.0mUnder Shdullapur, District Gaibandha. | Md. Mahomudun Nobi, Pirganj, Rangpur | 2627 | 3627 | 1 | 3.6 | 7673417 | 1106313 | 8779730 | 7289746.1 | 1050997.35 | 8340743.45 | 0 | 0 | 2019-03-21 | 2019-04-07 | 2019-04-13 | 2020-03-08 | 0 | 2020-03-31 | 100% | 5511343.59 | 1203622.41 | 6714966 | 1000461.77 | 203130.23 | 1203592 | 7918558 | 94.94% | Final Bill Paid
0 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 68 | 132823009 | Improvement of Naldanga GC-Ramzibon UP officeRoad at Ch: 1500m-2500m including Construction of 1Nos (0.625x0.600) m U-Drain Under Upazila:Sadullapur, District:Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 1500 | 2500 | 1 | 1 | 9588269 | 164366 | 9752635 | 8126474.979 | 0 | 8126474.979 | 0 | 0 | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 0 | 2021-05-13 | 70% | 4717796 | 899500 | 5617296 | 755463 | 144037 | 899500 | 6516796 | 80.19% | WBM Running
0 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-69 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.2000m-4000m. including 6Nos (0.625x0.600) m U-Drain on Khorda Rasulpur-Chandiapur Road at Ch: 2920m,2953m,3089m,3393m, 3582m & 3743m and 1x2.00mx2.00 m RCC Box Culvert at Ch: 2645m under khorda Rasulpur-Chandiapur Road under Shdullapur, District Gaibandha. | Khademul Islam Jewel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | package holded
0 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-70 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.0m-1250m. including Costruction of 2Nos (0.625x0.600) m U-Drain on Mohishbandhi-Mirpur Road at Ch: 52m & 946m Under Shdullapur, District Gaibandha. | M/S Sizin Traders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | package holded
0 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 71 | 132823004 | Improvement of Bhatgram UP office –Jamalpur Bazar Road at Ch: 00m-2000m including Construction of 11 Nos (0.625x0.600) m U-Drain at Ch: 45m, 320m, 472m, 775m, 800m,1265m, 1360m, 1430m, 1550m, 1785m &1919m and 1x2.50mx2.00 m RCC Box Culvert on at Ch: 1275m Under Upazila:Sadullapur, District: Gaibandha | M/S Mafi Construction='Civil Works'!I19 | 0 | 2000 | 2 | 14.3 | 16679589 | 2485578 | 19165167 | 14006744.15 | 2283645.85 | 16290390 | 0 | 0 | 43962 | 43969 | 43979 | 44344 | 0 | 44698 | 60% | 7281690 | 1609155 | 8890845 | 1317914 | 291241 | 1609155 | 10500000 | 0% | ISG on going
0 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 72 | 132823015 | Improvement of Dholvanga-Mohipur Bazar Road at Ch: 00m-1000m including Construction of 2 Nos (0.625x0.600) m U-Drain at Ch: 355m & 388m and 1x2.50mx2.00 m RCC Box Culvert at Ch: 330m Under Upazila:Sadullapur, District: Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 0 | 1000 | 1 | 5.3 | 9822898 | 1226329 | 11049227 | 9095523.665 | 0 | 9095523.665 | 0 | 0 | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 0 | 2021-05-13 | 30% | 707634 | 134472 | 842106 | 112999 | 21473 | 134472 | 976578 | 10.74% | Cross Drain & Pallisiding work Complete
| 2020-21 | Gaibandha | Saghata | Union Road-BC | PRO/GAI/SAG/UNR/20-21/W-135 | 132883015 | Improvement of Bhangamora Bazar-School bazar – Padumshahor UP Road at Ch: 3526m-6386m Under Upazila:Saghata, District: Gaibandha. | Md.Shamim Ahammed Mondal JV | 3526 | 6386 | 2.86 | 0 | 26773265 | 0 | 26773265 | 0 | 0 | 26690000.17 | 0 | 0 | 44145 | 44158 | 44164 | 44528 | 0 | 44530 | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NOA Issued
| 2020-21 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/SAD/UNR/ 20-21/W-136 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.7627m-8057m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | MD. SHAHID RANA JV | 7627 | 8057 | 0.43 | 0 | 4238910 | 0 | 4238910 | 0 | 0 | 3353774.307 | 0 | 0 | 44145 | 44159 | 44165 | 44529 | 0 | 44559 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NOA Issued
|  |  |  | Total: |  | NOS Est. Packages: | 9 | NOS Cont. Signed: | 7 |  | 15.944 | 37 | 138365053.28 | 7987082.47 | 146352135.75 | 102897838.214 | 5518319.26 | 138459931.951 | 0 | 0 | [6 empty] | 64.15% | 52328359.59 | 10665551.41 | 62993911 | 8888180.77 | 1777340.23 | 10665521 | 73659432 | 45.62%
Village Road BC
1 | 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI/GAI-S/VR/18-19/W-07 | 132244011 | Improvement of Bituminous Carpeting Road on Fulbari-Badiakhali hat Road At Ch0.00m-1623m. &2300m-3100m. including Costruction of 10 U- drain (0.600mx0.625m) Fulbari-Badiakhali hat Road atCh0.00m-1623m. &2300m-3100m. Under Gaibandha Sadar Upazila, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 2300 | 1623 3100 | 2.423 | 6 | 22031940.04 | 1000431.53 | 23032371.57 | 22027478.06 | 1000435.54 | 23027913.6 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-03-24 | 0 | 2020-12-31 | 95% | 11900400 | 2349800 | 14250200 | 1962327 | 387473 | 2349800 | 16600000 | 72.09% | WBM Complete. Mobilization for Carpeting.
2 | 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI /GAI-S/VR/18-19/W-08 | 132244021 | Improvement of Bituminous Carpeting Road on Ruper –Eslighat via Pramanik para Road at Ch.1500m-2980m including Costruction of 3 U- drain (0.600mX0.625m) at Ch.1280m,2300m,2640m. Under Gaibandha Sadar Upazila, District Gaibandha. | RSL Enterprise, gaibandha | 1500 | 2980 | 1.48 | 1.8 | 16529257.77 | 302110 | 16831367.77 | 16518512.1 | 302111.17 | 16820623.27 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-04-21 | 0 | 2020-04-23 | 100% | 11472451 | 2253310 | 13725761 | 1904749 | 348561 | 2253310 | 15979071 | 95% | Final Bill Paid
3 | 2018-19 | Gaibandha | Shadullapur | Village Road-BC | PRO/GAI/SAD/VR/18-19/W-11 | 132824014 | Improvement of Bituminous Road on Shdullapur Dhaperhat G.C road at Boxigonj Bazar toDhaperhat-Madarhat Road via Ambagan Road at Ch.0.00m-2480m. including Costruction of 11 Nos U-Drain 0.600mx0.625m at Ch.335m,720m,877m,1190m,1300m,1388m,1477m,1765m,1880m,1972m,&2226m. Under Shdullapur, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 | 2480 | 2.48 | 6.6 | 20485874 | 1361706 | 21847580 | 20563288.22 | 1361711.78 | 21925000 | 0 | 0 | 2019-04-18 | 2019-05-15 | 2019-05-21 | 2020-05-02 | 0 | 2020-07-31 | 100% | 13273661 | 2504677 | 15778338 | 2107080 | 397597 | 2504677 | 18283015 | 83.39% | Work Complete
4 | 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-13 | 132885163 | Improvement of Bituminous Road on Gatia H/O Taibor Master-Chitholia H/O Mahatab Member Road at Ch.0.00m-800m. including Costruction of 4 Nos U-Drain 0.600mx0.625m at Ch20m,135m,290m,&700m Under Saghata, District Gaibandha. | Md. Jakir Hossain, Gaibandha | 0 | 800 | 0.8 | 2.4 | 7459743 | 304702 | 7764445 | 7086755.8 | 282523.35 | 7369279.15 | 0 | 0 | 2019-03-21 | 2019-04-15 | 2019-04-21 | 2020-04-06 | 0 | 2019-12-29 | 100% | 5007817 | 994738 | 6002555 | 839420 | 155318 | 994738 | 6997293 | 94.95% | Final Bill Paid
5 | 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-14 | 132884002 | Improvement of Bituminous Road on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Road at ch.600m-2930m. including Costruction of 10 Nos U-Drain 0.600mx0.625m at Ch.673m,735m,816m,925m,1387m,1760m,1920m,1987m,2150m,2493m.and Costruction of 3 Nos Slope Drain at Ch.1496m, 1745m, 2075m, and Costruction of 3 Nos (2.00mx2.00m) Cross Drainges Structure on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Roadat Ch.2395m,2590m, 2787m. Under Saghata, District Gaibandha. | M/S SAJIN TRADERS JV | 600 | 2930 | 2.33 | 22.5 | 18252469 | 3310465 | 21562934 | 20694775 | 853394.34 | 21548169.34 | 0 | 0 | 2019-04-18 | 2019-05-07 | 2019-05-13 | 2020-03-25 | 0 | 2020-04-23 | 100% | 11038037 | 2243231 | 13281268 | 1842848 | 400383 | 2243231 | 15524499 | 72.05% | Work Completed.
|  |  |  | Total: |  | NOS Est. Packages: | 5 | NOS Cont. Signed: | 5 |  | 9.513 | 39.3 | 84759283.81 | 6279414.53 | 91038698.34 | 86890809.18 | 3800176.18 | 90690985.36 | 0 | 0 | [6 empty] | 98.73% | 52692366 | 10345756 | 63038122 | 8656424 | 1689332 | 10345756 | 73383878 | 80.92%
Maintenance by LCS
0 | 2019-20 | Gaibandha | Sundargonj | Maintenance-LCS | PRO/GAI/SUN/RMP/19-20/ MW-113 | 132915058 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Kapashia UP Office to Kashim Bazar- WAPDA Embankment via H/O Nesab Chairman (Kajir Char Ahammed Nagar Bazar) road, at Ch. 00-2300m. | 0 | 0 | 2300 | 2.3 | 0 | 0 | 0 | 1327224.49 | 0 | 0 | 1281224.49 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 0 | 0 | 75200 | 0 | 0 | 0 | 75200 | 0% | LCS team Work on going,
0 | 2019-20 | Gaibandha | Sadar | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-114 | 132245158 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Salam bazar- Balata bazar via Mouja malibari Eidgah at ch. 00-2500m | 0 | 0 | 2500 | 2.5 | 0 | 0 | 0 | 1331224.49 | 0 | 0 | 1281224.49 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 0 | 0 | 75200 | 0 | 0 | 0 | 75200 | 0% | LCS team Work on going,
0 | 2019-20 | Gaibandha | Shadullapur | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-115 | 132823009 132823008 132823001 132823004 132823006 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Naldanga G.C.-Ramzibon U.P. office. Road at ch. 00-780m. 2. Idilpur U.P. office-Dhaperhat U.P. office road at ch. 00-2000m. 3. Khorda Rasulpur-chandiapur roadat ch. 00-1020m. 4. Bhatgram U.P office-Jamalpur Bazar at ch.00-2000m. 5 Chandiapur bazar-Rahmatpur GC via Rasulpur bazar at ch.00-2000m. | 0 | 0.00 0.00 0.00 0.00 0.00 | 780 2000 1020 2000 2000 | 7.8 | 0 | 0 | 0 | 3639329.09 | 0 | 0 | 3483329.08 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 15% | 0 | 0 | 198850 | 0 | 0 | 0 | 198850 | 0% | LCS team Work on going,
0 | 2019-20 | Gaibandha | Saghata | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-116 | 132885022 132885175 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Dighal Kandi- Digholkandi H/O Sonaullah Mirja at ch.00-2700m. 2. Chakili H/O Vikku sarker - Folia Bazar road at ch. 00-1900m. | 0 | 0.00 0.00 | 2700 1900 | 4.6 | 0 | 0 | 0 | 2374181.13 | 0 | 0 | 2282181.12 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 0 | 0 | 128350 | 0 | 0 | 0 | 128350 | 0% | LCS team Work on going,
0 | 2019-20 | Gaibandha | Fulchori | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-117 | 132213003 132213011 132214050 132215025 132215037 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Erandabari U.P H/Q-Algarchar bazar at ch.1170-2250m. 2. Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S at ch.00-2500m. 3. Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram at ch.1170-2000m. 4. Pachim Khatiamary H/O Jalal Member-Gucha gram at ch.00-1000m. 5 Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary at ch.00-950m. | 0 | 1170 0.00 1170 0.00 0.00 | 2250 2500 2000 1000 950 | 6.36 | 0 | 0 | 0 | 3210146.42 | 0 | 0 | 3082946.43 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 20% | 0 | 0 | 175350 | 0 | 0 | 0 | 175350 | 0% | LCS team Work on going
|  |  |  | Total: |  | NOS Est. Packages: | 5 | NOS Cont. Signed: | 0 |  | 23.56 | 0 | 0 | 0 | 11882105.62 | 0 | 0 | 11410905.61 | 0 | 0 | [6 empty] | 14.23% | 0 | 0 | 652950 | 0 | 0 | 0 | 652950 | 0%
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
UNC-BC |  | 9 | 7 | 15.944 | 37 | 138365053.28 | 7987082.47 | 146352135.75 | 102897838.214 | 5518319.26 | 138459931.951 | 0 | 64.15% | 52328359.59 | 10665551.41 | 62993911 | 8888180.77 | 1777340.23 | 10665521 | 73659432 | 45.62%
Village-BC |  | 5 | 5 | 9.513 | 39.3 | 84759283.81 | 6279414.53 | 91038698.34 | 86890809.18 | 3800176.18 | 90690985.36 | 0 | 98.73% | 52692366 | 10345756 | 63038122 | 8656424 | 1689332 | 10345756 | 73383878 | 80.92%
Maintenance-LCS |  | 5 | 0 | 23.56 | 0 | 0 | 0 | 11882105.62 | 0 | 0 | 11410905.61 | 0 | UPDATE after WO
| Total: | 19 | 12 | 49.017 | 76.3 | 223124337.09 | 14266497 | 249272939.71 | 189788647.394 | 9318495.44 | 240561822.921 | 0 | 74.15% | 105020725.59 | 21011307.41 | 126032033 | 17544604.77 | 3466672.23 | 21011277 | 147043310 | 61.12% | 61.12%
Unallocated Packages:
|  | Gaibandha | Saghata | Union Road-BC |  | 132883015 | Bhangamore bazar-school bazar- Padumshahor UP
|  | Gaibandha | Fulchori | Union Road-BC |  | 132213003 | Erandabari U.P H/Q-Algarchar bazar
|  | Gaibandha | Fulchori | Union Road-BC |  | 132213011 | Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S
|  | Gaibandha | Shadullapur | Union Road-BC |  | 132823004 | Bhatgram U.P office-Jamalpur Bazar
|  | Gaibandha | Shadullapur | Union Road-BC |  | 132823009 | Naldanga G.C.-Ramzibon U.P.office.
|  | Gaibandha | Shadullapur | Union Road-BC |  | 132823015 | Dholvanga-Mohipur Bazar
|  | Gaibandha | Sadar | Village Road-BC |  | 132244025 | Jugir ghat-Badsharghat Road.
|  | Gaibandha | Sadar | Village Road-BC |  | 132245056 | Salam bazar- Balayata bazar via Mouza malibari Edghah
|  | Gaibandha | Saghata | Village Road-BC |  | 132884061 | Trimohoni Khayaghat-Ullasonatola bazar Rd.
|  | Gaibandha | Saghata | Village Road-BC |  | 132884024 | Durgapur Sazahan Ali Govt. primary School - Pass Durgapur Govt. Primary School
|  | Gaibandha | Saghata | Village Road-BC |  | 132884038 | Boliarber GPS - Kamalerpara- Falia Pucca road
|  | Gaibandha | Sundargonj | Village Road-BC |  | 132914077 | Shaker Bazar-Wapda Embankment via Baraikandi road
|  | Gaibandha | Saghata | Village Road-HBB |  | 132885022 | Dighal Kandi- Digholkandi H/O Sonaullah Mirja
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132214036 | Fulchari Kheyaghat-Tengrakandi Road
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132214050 | Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132215025 | Pachim Khatiamary H/O Jalal Member-Gucha gram
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132215037 | Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Ramdakua- Akotar Bazar
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Karent Bazar
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Mondoler hat
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Hazari hat
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915058 | Koshim Bazar- Kagia Char Ahmed Nagar Bazar
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915058 | Koshim Bazar-Vati Kapasia Nuton Asraon Bazar
|  | Gaibandha | Fulchori | Large Market |  |  | Purbo Fulchari Bazar
|  | Gaibandha | Fulchori | Large Market |  |  | Sannasirchar Bazar
|  | Gaibandha | Sundargonj | Large Market |  |  | Kashem Bazar
|  | Gaibandha | Sadar | Medium Market |  |  | Balua Hat
|  | Gaibandha | Sadar | Medium Market |  |  | Puraton Badiakhali Hat
|  | Gaibandha | Sadar | Medium Market |  |  | Lenga Bazar Hat
|  | Gaibandha | Saghata | Medium Market |  |  | Ullah Sonatola Bazar
|  | Gaibandha | Saghata | Medium Market |  |  | Bhangamore
|  | Gaibandha | Saghata | Medium Market |  |  | Falia Bottola Bazar
|  | Gaibandha | Saghata | Medium Market |  |  | Ullah Bazar
|  | Gaibandha | Saghata | Medium Market |  |  | Dhakin Digholkandi
|  | Gaibandha | Saghata | Medium Market |  |  | Nayabondar Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Khatiamary Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Taltola Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Kayerhaat
|  | Gaibandha | Fulchori | Medium Market |  |  | Daluabari Haat
|  | Gaibandha | Fulchori | Medium Market |  |  | Jigabari Haat
|  | Gaibandha | Fulchori | Medium Market |  |  | Algharchar Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Jhanjhor Bazar
|  | Gaibandha | Shadullapur | Medium Market |  |  | Boxigonj Bazar
|  | Gaibandha | Shadullapur | Medium Market |  |  | Naldanga kachari Bazar
|  | Gaibandha | Sundargonj | Medium Market |  |  | Belka Bazar
|  | Gaibandha | Sundargonj | Medium Market |  |  | Charoker Hat
|  | Gaibandha | Sundargonj | Medium Market |  |  | Domer Hat
|  | Gaibandha | Sundargonj | Medium Market |  |  | Moyej Mear Hat
|  | Gaibandha | Sundargonj | Medium Market |  |  | Jamaler Hat
|  | Gaibandha | Shadullapur | Medium Market |  |  | Boxigonj Bazar
|  | Gaibandha | Shadullapur | Medium Market |  |  | Kantanagar bazar
|  | Gaibandha | Saghata | Small Market |  |  | Futani Bazar
|  | Gaibandha | Fulchori | Small Market |  |  | Moshamari Bazar
|  | Gaibandha | Fulchori | Small Market |  |  | Katlamari Bazar
|  | Gaibandha | Sundargonj | Small Market |  |  | Shokher Hat