## Gaibandha
Contract Status of Flood & Disaster Damaged Rural Road Infrastructure Rehabilitation Project (FDDRIRP), FY: 2018-2019
District : |  | Gaibandha | [14 empty] | Date of Reporting: | 2021-01-04
Sl. No. | Name of Upazila | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Contract's Name | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progr. (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
A. Rehabilitation Road [Strengthening/Widening]
1 | Shaghata | W01 | 1 | 132882003 | Bonar Para GC (Bonar Para college)-Shankorgonj kheyaghat rd (Nakaihat GC) | M/S Dalia Trading, House No. 40, Road No.1/1, JNC Road, East Gupt apara, Rangpur-5400 | 0 | 3575 | 3575 | 16768998 | 15930548.1 | 15815896 | 2018-07-22 | 2019-05-30 | 287.5% | 100% | - | Final Bill Paid |  | 312 | 897
2 | Shaghata | W02 | 1 | 132883001 | Saghata GC-Kachua UP Office via Ullah Sonatala Bazar | Md. Atiqur Rahman Kishamat Malibari, Dariapur, Gaibandha Sadar, Gaibandha | 0 | 2465 | 2465 | 11405463 | 10835189.85 | 10821163 | 2018-07-17 | 2019-01-14 | 498.3% | 100% | - | Final Bill Paid |  | 181 | 902
3 | Gobindaganj | W03 | 1 | 132303020 | Salmara UP - Sonatola Upazila via Heatpur | M/S Dalia Trading, House No. 40, Road No.1/1, JNC Road, East Gupt apara, Rangpur-5400 | 3920 | 5080 | 1160 | 4873986 | 4630286.7 | 4623560 | 2018-07-22 | 2019-03-30 | 357.4% | 100% | - | Final Bill Paid |  | 251 | 897
4 | Sundarganj | W04 | 1 | 132912008 | Bamandangha R&H - Luxmipur GC Via Naldanga G.C & Dhupadangha UP Road.(Sundarganj Upazila part ch.0.00-4.800 & 7.650-10.938)km | Md. Matlubour Rahman, Gaibandha | 0 | 4800 | 4800 | [5 empty] | - |  | - |  |  | 0 | -
[7 empty] | 7650 | 10938 | 3288 | 43262795 | 41235562.578 | 41201662 | 2018-06-08 | 2019-06-30 | 243.2% | 100% | - | Final Bill Paid |  | 387 | 941
5 | Sadullapur | W05 | 1 | 132822002 | Sadullapur -Naldanga GC Road | M/S. Md. Rabiul Alam (Bulbul) | 2650 | 6078 | 3428 | [5 empty] | - |  | - |  |  | 0 | -
[7 empty] | 7287 | 10955 | 3668 | 46067785 | 40538436.158 | 35525014 | 2018-08-18 | 2019-07-30 | 251.4% | 100% | - |  |  | 346 | 870
6 | Palashbari | W06&W08 | 1 | 132673002 | Kalibari GC at cinema hall-chattra UP office Road [Length=9.50km] | M/S Shihab Construction, Gobindaganj, Gaibandha | 0 | 2000 | 2000 | 2889422 | 2744950 | 2744880.5 | 2019-01-09 | 2019-05-29 | 518.6% | 100% | - | Final Bill Paid |  | 140 | 726
|  |  | 2 | 132672007 | Satarpara RHW-Fakirhat GC Road | M/S Shihab Construction, Gobindaganj, Gaibandha | 0 | 4750 | 4750 | 7760165 | 7372156.75 | 7372054.2 | 2019-01-09 | 2019-05-29 | 518.6% | 100% | - | Final Bill Paid |  | 140 | 726
|  |  | 3 | 132672009 | Komorpur GC-Marirhat GC Road via sahindaha | M/S Shihab Construction, Gobindaganj, Gaibandha | 0 | 1580 | 1580 | 4785734 | 4546447.3 | 4546447.3 | 2019-01-09 | 2019-05-29 | 518.6% | 100% | - | Final Bill Paid |  | 140 | 726
7 | Sadullapur | W10 | 1 | 132825009 | Sadullapur Naldanga Road - Kismat Khejur via maruadaha | Rabbi Ent. Pirganj, Rangpur | 0 | 1875 | 1875 | 6432417 | 6110796.15 | 5941352 | 2019-04-02 | 2019-08-02 | 527% | 100% | - | Final Bill Paid |  | 122 | 643
8 | Sundarganj | W14 | 1 | 132912003 | Nagarkatgara GC-Luxmipur GC Via Balachira FRA Road. | ALH-MR-JV, Gaibandha | 3500 | 17700 | 14200 | 114872725 | 114852140.826 | 55477708 | 2019-07-28 | 2021-03-05 | 89.76% | 70% | - |  |  | 586 | 526
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
9 | Gobindaganj | W18 | 1 | 132303020 | Salmara UP - Sonatola Upazila via Heatpur | Hazi & Sons, Sadar, Gaibandha | 0 | 1093 | 1093 | 5175424 | 4916652.8 |  | 2020-06-09 | 2020-09-07 | 232.2% | 50% | Time Expired |  |  | 90 | 209
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
9 | Sub-Total (A): | 0 | 11 |  | Not Contacted Amount | 0 |  |  | 47.882 | 264294914 | 253713167.212 | 184069737 | Fin. Pgr. (%) | 72.55% |  | 85.45%
B. Rehabilitation Structure [Bridges/Culverts]
1 | Gobindaganj | BW09 | 1 | 132304129 | Mohimagonj UP - Bishpukur Naya Bazar via Balua BRIDGE | Mokaddes Ali Badu, Gobindaganj, Gaibandha | 130 | 160 | 30 | 22815685 | 22808061.79 | 16450000 | 2019-03-25 | 2020-03-02 | 189.8% | 90% | Time Expired |  |  | 343 | 651
2 | Gobindaganj | BW11 | 1 | 132302014 | Mohimagonj GC-Bonarpra GC (Shaghata) Road. BRIDGE | Mokaddes Ali Badu, Gobindaganj, Gaibandha JV | 2160 | 2180 | 20 | 16560415 | 16521439.66 | 16490268 | 2019-04-29 | 2020-04-09 | 178% | 100% | - |  |  | 346 | 616
3 | Gobindaganj | BW12 | 1 | 132303025 | Katabari U.P-Bagulagari hat BRIDGE | Md. Atair Rahman, Faridpur | 2290 | 2320 | 30 | 26164467 | 26080155.61 | 9850000 | 2019-05-04 | 2020-10-21 | 114% | 60% | Time Expired |  |  | 536 | 611
4 | Shaghata | BW13 | 1 | 132884060 | Helencha FRB - Bati Road .BRIDGE | SR Traders, Gaibandha | 423 | 443 | 20 | 20148392 | 20130000 |  | 2019-07-01 | 2020-06-30 | 151.5% | 15% | Time Expired |  |  | 365 | 553
5 | Sadullapur | CW16/17 | 1 | 132822013 | Madargonj GC-Laxmipur G.C Road via Kantanagar. | icon construction&builders | 2730 | 2733.5 | 3.5 | 1729441 | 1642968.95 | 1639995 | 2019-12-18 | 2020-05-20 | 248.7% | 100% | - |  |  | 154 | 383
6 | Shaghata | CW19-21 | 1 | 132882010 | Bonarpara GC - Gobindogonj -Gaibandha RHD at Sagdha Bridge via Ramnagar Bazar (Saghata part ) | M. R Construction, Saghata | 1900 | 1902 | 2 | [5 empty] | - | 20% | - |  |  | 0 | -
[7 empty] | 2852 | 2858 | 6 | [5 empty] | - | 20% | - |  |  | 0 | -
[7 empty] | 989 | 1002.5 | 13.5 | 7422261 | 7051147.95 |  | 2020-06-10 | 2020-12-07 | 115.6% | 20% | Time Expired |  |  | 180 | 208
7 | Gobindaganj | BW11(A) | 1 | 132302014 | Mohimagonj GC-Bonarpra GC (Shaghata) Road | Md. Mokaddesh Ali Badu, Gobindaganj, Gaibandha | 2160 | 2180 | 20 | 1099003 | 1044052.85 |  | 2020-10-03 | 2021-01-03 | 101.1% | 75% | Time Expired |  |  | 92 | 93
8 | Shaghata | BW22 | 1 | 132882010 | Bonarpara GC - Gobindogonj -Gaibandha RHD at Sagdha Bridge via Ramnagar Bazar (Saghata part ) |  | 626 | 662 | 36 | 28116226 |  |  |  |  | - |  | - | APP Sent |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
8 | Sub-Total (B): | 1 | 8 |  | Not Contacted Amount | 28116226 |  |  | 181 | 124055890 | 95277826.81 | 44430263 | Fin. Pgr. (%) | 46.63% |  | 0.62504
17 | Grand Total: | 1 | 19 |  | Not Contacted Amount | 28116226 |  |  |  | 388350804 | 348990994.022 | 228500000 | Fin. Pgr. (%) | 65.47% |  | 79.19% |  |  |  | Dec
Fund Received: | [5 empty] | Structure | 181 | m | Road | 47.882 | km |  |  |  |  | Cash in Hand: |  | 1500000
Date: | 18-19 |  | 19-20 |  | 20-21 | [12 empty] | Total:
Tk. | 80000000 |  | 140000000 |  | 10000000 | [12 empty] | 230000000
Comments if any:
| W15 This Package Ch.7650-10938m Completed from Package W04 .Thats why do not entry in the report | [10 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  |  | Amount Required upto June (Tk.)
Gaibandha Sadar
Gobindaganj
Fulchhari
Palashbari
Sadullapur
Shaghata
Sundarganj