## Ponds & Canals
Progress Report of
Improvement of Pond, Canal Across the Country Project
District: Gaibandha | [11 empty] | Month: | Dec |  | F/Y: | 2020-21
SL No. | Upazila | Package No. | Name of the Work | Length (Km)/ Area (Acre) | Approved Estimated Cost (Tk) | Name of contractor and Adress | Date of Contract | Contract Amount (Tk) | Implementation Details |  |  |  | Progress |  |  | Remarks
[9 empty] | Starting Date | Completion Date as per Contract | Revised Completion Date | Actual Completion Date | Physical (%) | ActuaI Payment (Tk) | Financial (%)
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Sadaullapur | IPCP/GAIB/SADUL/C/19-20/1.01 | 1. a) Excavation of Noleya River 2nd part at Ch.0.00-4222.00m, b) Construction of Reference Line (Considering 9 Nos. of 30.00m Length) , c) Construction of TBM (Considering 250mm x 250mm) under Bhatgram Union, Sadaullapur Upazila, Dist Gaibandha. | 4.222 | 21385322 | Mohammad Eunus & Brothers, Chittagong | 2020-02-06 | 16935544.89 | 2020-02-12 | 2021-01-26 |  |  | 30% | 2300000
2 | Gobindaganj | IPCP/GAIB/GOBIN/C/19-20/2.01 | 2. a) Excavation of Sarai Bridge-Rajahar Shimana Khal at Ch.0.00-2827.129m, b) Construction of Reference Line and TBM (Considering 3 Nos.) under Gumanigonj Union, Gobindaganj Upazila, Dist Gaibandha. | 2.827 | 4948519 | M/S Ekramul Hoq, Gobindaganj, Gaibandha | 2020-02-06 | 4701093.05 | 2020-01-03 | 2020-05-30 |  |  | 100% | 3700000
| Saghata | IPCP/GAIB/SAGHA/P/20-21/3.01 | 3: 1. a. Re-excavation of Dhonarua Hafiza Madrasha & Atimkhana Pond, b. Construction of 01 No. Ghatla of 11.60m x 4.00m x 3.90m at Dhonarua Hafiza Madrasha & Atimkhana Pond under Saghata Upazila Dist Gaibandha.2. a Re-excavation of Folia Hafiza Madrasha Pond. b. Construction of 01 No. Ghatla of 12.80m x 4.00m x 4.50m at Folia Hafiza Madrasha Pond under Saghata Upazila Dist Gaibandha.3.a. Re-excavation of Kazi Azhar Ali High School Pond b Construction of 01 No. Ghatla of 15.20m x 4.00m x 5.40m at Kazi Azhar Ali High School Pond under Saghata Upazila Dist Gaibandha.; 5: 2902227; 6: M/S NAFI NILOY TRADERS; 8: 2757115.65; 16: Tender Receive Date 14-Dec-2020
| Total = |  | 4: 7.049; 5: 29236068; 8: 24393753.59; 14: 6000000
[6 empty] | Fund Received | [7 empty] | 6000000
[6 empty] | Balance | [7 empty] | 0
|  |  | SAE, IPCP/ SAE |  |  |  |  | AE/ Sr.AE | [5 empty] | XEN

## Sheet3
List of Schemes ( Khas Khal/Canal and Ponds/Dighi) Status
Sl. No. | District | Khal FS Status |  |  | Khal Survey Status |  | Pond FS Status |  |  | Pond Survey Status |  | Ghatla |  | Remarks
|  | Scheme No. (DPP) | FS Found | Pass/Fail | Survey | Actual Length (m) | Scheme No. (DPP) | FS Found | Pass/Fail | Survey | Actual Area (Sq.m) | Scheme No. (DPP) | FS Found
1 | Panchagar | 7 | Not Found
2 | Thakurgaon | 9 | Not Found
3 | Dinajpur | 5 | Not Found
4 | Nilphamari | 3
5 | Lalmonirhat | 9
6 | Kurigram | 6
7 | Rangpur | 8
8 | Gaibandha | 11
9 | Bogra | 3
10 | Sirajgonj | 15
11 | Pabna | 6
12 | Joypurhat
13 | Rajshahi
14 | Natore
15 | Naogan
16 | Chapainababgonj
17 | Kushtia | 16
18 | Meherpur | 5
19 | Chuadanga | 9
20 | Jhenaidah | 9
21 | Magura | 15
22 | Jessore | 11 |  |  |  |  | 55 | 3
23 | Narail | 8
24 | Satkhira | 18
25 | Khulna | 39
26 | Bagerhat | 17 | 1 | [9 empty] | 1
27 | Borgona | 26
28 | Patuakhali | 38
29 | Bhola | 40
30 | Barishal | 19
31 | Jalokhati | 45
32 | Perojpur
33 | Gopalgonj
34 | Madaripur
35 | Shariatpur
36 | Rajbari
37 | Dhaka
38 | Manikgonj
39 | Narsingdi
40 | Munshigonj
41 | Gazipur
42 | Tangail
43 | Kishorgonj
44 | Mymensingh
45 | Netrokona
46 | Jamalpur
47 | Sherpur
48 | Chittagong
49 | Cox's Bazar
50 | Rangamati
51 | Khagrachari
52 | Bandarban
53 | Comilla
54 | Chandpur | 32 | 4 |  |  |  | 90 | 18
55 | B-Baria
56 | Noakhali
57 | Feni
58 | Lixmipur
59 | Sylhet
60 | Sunamganj
61 | Habiganj
62 | Moulvibazar
63
64