## APP_Goods
ANNUAL PROCUREEMT PLAN FOR GOODS (2021-22)
(Capital Budget)
Ministry/Division |  |  | : | Power Division
Agency |  |  | : | Bangladesh Rural Electrification Board
Procuring Entity Name & Code |  |  | : | Dinajpur Polly Bidyut Samity- 1
O&M : Schedule 1 as per Budget
Tender Package No. | Lot | Description of procurement package Goods | Unit | Qnty. | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. ('000') | Time Code for Process | Advertise Tender Date | Tender Opening Date | Tender Evaluation | Approval of Award | Notification of Award | Signing of Contract | Completion of Contract | Total Time (in days)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
G-21-22.18.01 | G-21-2218.01-001 | Distribution Transformer (5,10,15 & 37.5 KVA) | Nos | 3600 | OTM Lead PBS/ BREB | REB Board | Self- Finance | 5176 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 3600 |  |  |  | 5176
G-21-22.18.02 | G-21-22.18.02-001 | Meter( Single Phase) | Nos | 5000 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 10360 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| G-21-22.18.02-002 | Meter ( Three Phase) | Nos | 100 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 18000 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 5100 |  |  |  | 28360
G-21-22.18.03 | G-21-22.18.03-001 | Insulator | Nos | 2400 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 3045 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 2400 |  |  |  | 3045
G-21-22.18.04 | G-21-22.18.04-001 | Conductor | meters | 50000 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 4872 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 50000 |  |  |  | 4872
G-21-22.18.05 | G-21-22.18.05-001 | Armod Rod | Nos | 9000 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 1218 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 9000 |  |  |  | 1218
G-21-22.18.06 | G-21-22.18.06-001 | Fuse Link | Nos | 10000 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 3045 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 10000 |  |  |  | 3045
G-21-22.18.07 | G-21-22.18.07-001 | Connector | Nos | 30000 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 1817 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 30000 |  |  |  | 1817
G-21-22.18.08 | G-21-22.18.08-001 | Regulator | Nos | 9 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 6212 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 6212
G-21-22.18.09 | G-21-22.18.09-001 | Gaywear | Nos | 9 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 313 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 313
G-21-22.18.10 | G-21-22.18.10-001 | Wooden Pole | Nos | 100 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 3045 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 3045
G-21-22.18.11 | G-21-22.18.11-001 | SPC Pole | Nos | 400 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 30450 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 400 |  |  |  | 30450
G-21-22.18.12 | G-21-22.18.12-001 | Cross Arm | Nos | 500 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 5481 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total |  |  | 500 |  |  |  | 5481
G-21-22.18.13 | G-21-22.18.13-001 | Ankorlog | Nos | Lot | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 268 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| G-21-22.18.13-002 | CT/PT | Nos | 50 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 900 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 1168
G-21-22.18.14 | G-21-22.18.14-001 | ACR/OCR | Nos | 25 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 9135 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 9135
G-21-22.18.15 | G-21-22.18.15-001 | Hardware | Nos | lot | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 7308 | Plan Dates | Date will be Settled by BREB or Lead PBS
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 7308
G-21-22.18.16 | G-21-22.18.16-001 | other | Nos | lot | OTM | GM | Self- Finance | 6699 | Plan Dates | 2021-07-12 | 2021-07-22 | 2021-07-25 | 2021-08-09 | 2021-08-12 | 2021-08-15 | 2021-11-13
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| Sub-Total | [6 empty] | 6699
Deposit work : Schedule 2 as per Budget
G-21-22.18.17 | G-21-22.18.17-001 | Distribution Transformer (5,10,15 & 37.5 KVA) | Nos | 400 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 3271 | Plan Dates | 2021-07-12: BREB
Plan Days
Actual Dates
| Sub-Total |  |  | 400 |  |  |  | 3271
G-21-22.18.18 | G-21-22.18.18-001 | Meter | Nos | 1000 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 1000 | Plan Dates | 2021-07-12: BREB
Plan Days
Actual Dates
| Sub-Total |  |  | 1000 |  |  |  | 1000
G-21-22.18.19 | G-21-22.18.19-001 | Insulator | Nos | 500 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 1000 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 500 |  |  |  | 1000
G-21-22.18.20 | G-21-22.18.20-001 | Conductor | meters | 18250 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 2519 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 18250 |  |  |  | 2519
G-21-22.18.21 | G-21-22.18.21-001 | Fuse Link | Nos | Lot | RFQ | GM | Self- Finance | 6168 | Plan Dates | 2021-07-12: Lead pbs
[9 empty] | Plan Days | 2021-07-25: AS per Requirment
Actual Dates
| G-21-22.18.21-002 | Connector | Nos | Lot | RFQ | GM | Self- Finance | 350 | Plan Dates | 2021-07-12: Lead pbs
[9 empty] | Plan Days | 2021-07-25: AS per Requirment
Actual Dates
| Sub-Total |  |  | Lot |  |  |  | 6518
G-21-22-18.22 | G-21-22.18.22-001 | Fuse Link | Nos | 100 | DPM | GM | Self- Finance | 100 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 100 |  |  |  | 100
G-21-22.18.23 | G-21-22.18.23-001 | Gaywear | Nos | Lot | RFQ | GM | Self- Finance | 500 | Plan Dates | 2021-07-12: Lead pbs; 2021-07-22: AS per Requirment
Plan Days
Actual Dates
| Sub-Total |  |  | Lot |  |  |  | 500
G-21-22.18.24 | G-21-22.18.24-001 | Mask, Handsanitiser,etc | Nos | 67 | DPM | BREB Board | Self- Finance | 100 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 67 |  |  |  | 100
G-21-22.18.25 | G-21-22.18.25-001 | SPC Pole | Nos | 200 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 27985 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 200 |  |  |  | 27985
G-21-22.18.26 | G-21-22.18.26-001 | Cross Arm | Nos | 500 | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 300 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 500 |  |  |  | 300
G-21-22.18.27 | G-21-22.18.27-001 | Angkor Log | Nos |  | OTM Lead PBS/ BREB | BREB Board | Self- Finance | 300 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 300
G-21-22.18.28 | G-21-22.18.28-001 | Hardware | Nos |  | OTM | GM | Self- Finance | 9235 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
G-21-22.18.29 | G-21-22.18.28-001 | Hardware | Nos |  | RFQ | GM | Self- Finance | 500 | Plan Dates | 2021-07-12: Lead pbs
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 9735
G-21-22.18.29 | G-21-22.18.29-001 | Other Material | Nos |  | OTM/Lead PBS | GM | Self- Finance | 9795 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 9795
Schedule-(8+12) : Furniture
G-21-22.18.30 | G-21-22.18.30-001 | wooden furniture | Nos |  | OTM | GM | Self- Finance | 300 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 300
G-21-22.18.31 | G-21-22.18.31-001 | wooden furniture | Nos |  | RFQ | GM | Self- Finance | 275 | Plan Dates
[9 empty] | Plan Days | [7 empty] | 0
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 275
G-21-22.18.32 | G-21-22.18.32-001 | Steel Furniture | Nos |  | OTM | GM | Self- Finance | 370 | Plan Dates
[9 empty] | Plan Days | [7 empty] | 0
Actual Dates
G-21-22.18.33 | G-21-22.18.33-001 | Steel Furniture | Nos |  | RFQ | GM | Self- Finance | 280 | Plan Dates
[9 empty] | Plan Days | [7 empty] | 0
Actual Dates
G-21-22.18.34 | G-21-22.18.34-001 | Steel Furniture | Nos |  | DPM | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days | 2021-07-22: AS per Requirment (two step) | 0
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 750
| Sub-Total |  |  | #REF! |  |  |  | #REF!
G-21-22.18.35 | G-21-22.18.35-001 | air cooler | Nos | 3 | RFQ | GM | Self- Finance | 300 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 3 |  |  |  | 1050
G-21-22.18.36 | G-21-22.18.36-001 | Wooden Furniture (rest house & others) | Nos |  | RFQ | GM | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
| G-21-22.18.36-002 | Wooden Furniture (rest house & others) | Nos |  | DPM | GM | Self- Finance | 50 | Plan Dates
Plan Days
Plan Dates
Plan Days
Actual Dates
Actual Dates
| Sub-Total | [6 empty] | 150
G-21-22.18.37 | G-21-22.18.37-001 | Steel Furniture (rest house & others) | Nos |  | RFQ | GM | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
| G-21-22.18.37-002 | Steel Furniture (rest house & others) | Nos |  | DPM | GM | Self- Finance | 87 | Plan Dates
Plan Days
Plan Dates
Plan Days
Actual Dates
Actual Dates
| Sub-Total | [6 empty] | 187
G-21-22.18.38 | G-21-22.18.38-001 | crokeris, carpat, jutemate(rest house) | Nos |  | DPM | GM | Self- Finance | 50 | Plan Dates
[9 empty] | Plan Days | 2021-07-12: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 50
G-21-22.18.39 | G-21-22.18.39-001 | water griger, service dish | Nos | 4 | DPM | GM | Self- Finance | 15 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.39-002 | water griger, service dish | Nos | 4 | DPM | GM | Self- Finance | 15 | Plan Dates
Plan Days
Actual Dates
|  |  |  | 4 |  |  |  | 30
G-21-22.18.40 | G-21-22.18.40-001 | selling fan | Nos | 10 | RFQ | GM | Self- Finance | 50 | Plan Dates
[9 empty] | Plan Days | 2021-07-22: AS per Requirment
Actual Dates
G-21-22.18.41 | G-21-22.18.41-001 | selling fan | Nos | 10 | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-07-22: AS per Requirment
Actual Dates
| Sub-Total |  |  | 10 |  |  |  | 75
G-21-22.18.42 | G-21-22.18.42-001 | television & other | Nos |  | RFQ | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days | 2021-07-12: AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
G-21-22.18.43 | G-21-22.18.43-001 | Wooden Furniture & others | Nos | Lot | RFQ | GM | Self- Finance | 75 | Plan Dates
[9 empty] | Plan Days | 2021-07-22: AS per Requirment
Actual Dates
G-21-22.18.44 | G-21-22.18.44-002 | Wooden Furniture & others | Nos | Lot | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-07-22: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 100
Schedule-(8+12) : JUTE MATE, Carpet & Other
G-21-22.18.45 | G-21-22.18.45-001 | Jute Mate , Carpet & other | Nos | Lot | DPM | Gm | Self- Finance | 75 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.45-002 | Jute Mate , Carpet & other | Nos | Lot | DPM | Gm | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-07-22: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 100
G-21-2218.46 | G-21-22.18.46-001 | solar power plant | Nos | 1 | OTM | BREB | Self- Finance | 3500 | Plan Dates | 2021-07-12: Date will be Settled by BREB
[9 empty] | Plan Days | [7 empty] | 0
Actual Dates
| Sub-Total | [6 empty] | 3500
G-21-2218.47 | G-21-22.18.47-001 | Pre payement meter | Nos | 1000 | RFQ | Gm | Self- Finance | 500 | Plan Dates | 2021-08-30 | 2021-09-09 | 2021-09-12 | 2021-09-27 | 2021-09-30 | 2021-10-03 | 2022-01-01
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| Sub-Total | [6 empty] | 500
G-21-22.18.48 | G-21-22.18.48-001 | Weight Scale | Nos | 2 | RFQ | Gm | Self- Finance | 200 | Plan Dates | 2021-01-01 | 2021-01-11 | 2021-01-14 | 2021-01-29 | 2021-02-01 | 2021-02-04 | 2021-05-05
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
G-21-22.18.49 | G-21-22.18.49-001 | Weight Scaler | Nos | 1 | DPM | Gm | Self- Finance | 25 | Plan Dates | 2021-08-30 | 2021-09-09 | 2021-09-12 | 2021-09-27 | 2021-09-30 | 2021-10-03 | 2022-01-01
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| Sub-Total | [6 empty] | 225
G-21-22.18.50 | G-21-22.18.50-001 | Display Board, Flag Stand, Honour Board, White Board & Complan Box | Nos | 1 | RFQ | Gm | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.51-002 | Display Board, Flag Stand, Honour Board, White Board & Complan Box | Nos | 1 | DPM | Gm | Self- Finance | 75 | Plan Dates
G-21-22.18.51 | [8 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 175
G-21-2218.52 | G-21-22.18.52-001 | padstle, adjust fan | Nos | 10 | DPM | Gm | Self- Finance | 35 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 35
G-21-2218.53 | G-21-22.18.53-001 | other | Nos |  | DPM | Gm | Self- Finance | 50 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 50
OFFICE EQUIPMENT : Schedule 9 as per Budget
G-21-22.18.54 | G-21-22.18.54-001 | Computer & Accessoris | Nos | 20 | OTM | BREB Board | Self- Finance | 1000 | Plan Dates | 2021-08-15 | 2021-09-12 | 2021-09-19 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2022-01-16
[9 empty] | Plan Days | 0 | 28 | 7 | 15 | 7 | 7 | 90 | 154
Actual Dates
| G-21-22.18.54-002 | Server | Nos | 3 | OTM | BREB Boar | Self- Finance | 2500 | Plan Dates | 2021-09-15 | 2021-10-13 | 2021-10-20 | 2021-11-04 | 2021-11-11 | 2021-11-18 | 2022-02-16
[9 empty] | Plan Days | 0 | 28 | 7 | 15 | 7 | 7 | 90 | 154
Actual Dates
| G-21-22.18.54-003 | Dot Metrix printer | Nos | 13 | OTM | BREB Board | Self- Finance | 1000 | Plan Dates | 2021-10-08 | 2021-10-08 | 2021-10-15 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2022-02-11
[9 empty] | Plan Days | 0 | 28 | 7 | 15 | 7 | 7 | 90 | 154
Actual Dates
| G-21-22.18.54-004 | Laptop | Nos | 10 | OTM | BREB Board | Self- Finance | 1000 | Plan Dates | 2021-10-08 | 2021-10-08 | 2021-10-15 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2022-02-11
[9 empty] | Plan Days | 0 | 28 | 7 | 15 | 7 | 7 | 90 | 154
Actual Dates
| Sub-Total | [6 empty] | 4500
G-21-22.18.55 | G-21-22.18.55-001 | Lasser Printer | Nos | 5 | RFQ | Gm | Self- Finance | 120 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 120
G-21-22.18.56 | G-21-22.18.56-001 | Dot Metrix printer | Nos | 3 | RFQ | GM | Self- Finance | 200 | Plan Dates | 7/12/2021. | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| G-21-22.18.56-001 | scrol bord | Nos | 3 | RFQ | GM | Self- Finance | 200 | Plan Dates | 7/12/2021. | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| Sub-Total | [6 empty] | 200
G-21-22.18.57 | G-21-22.44.57-001 | Lasser Printer | Nos | 8 | DPM | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| G-21-22.44.57-002 | UPS | Nos | 10 | DPM | GM | Self- Finance | 120 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| G-21-22.18.57-003 | Computer Accessoris (Monitor, Pen Drive, CD, Anti Virus , cd drive, ram & etc.) | Nos | Lot | DPM | GM | Self- Finance | 10 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 330
G-21-22.18.58 | G-21-22.18.58-001 | Lemineting Machin | Nos | 4 | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| Sub-Total |  |  | 4 |  |  |  | 35
G-21-22.18.59 | G-21-22.18.59.001 | Scaner | Nos | 4 | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| Sub-Total |  |  | 4 |  |  |  | 25
G-21-22.18.60 | G-21-22.18.60-001 | CC TV CEMERA | Set | 4 | rfq | Gm | Self- Finance | 900 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment | 0
Actual Dates
| Sub-Total |  |  | 4 |  |  |  | 900
G-21-22.18.61 | G-21-22.18.61-001 | Celling Fan | Nos | 10 | RFQ | Gm | Self- Finance | 50 | Plan Dates
Plan Days
[9 empty] | Actual Dates | 2021-10-13: AS per Requirment
| Sub-Total |  |  | 10 |  |  |  | 50
G-21-22.18.62 | G-21-22.18.62-001 | Fair Extingusher | Nos | 25 | RFQ | Gm | Self- Finance | 75 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
G-21-22.18.59 | G-21-22.18.59-001 | Fair Extingusher | Nos | 25 | DPM | Gm | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
G-21-22.18.60 | G-21-22.18.60-001 | Gas Barner & Celinder | Nos | Lot | DPM | Gm | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 30
G-21-22.18.61 | G-21-22.18.61-001 | Wall Clock | Nos | 6 | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | [7 empty] | 0
[9 empty] | Actual Dates | 2021-10-13: AS per Requirment
| Sub-Total |  |  | 6 |  |  |  | 30
| Sub-Total |  |  | 0 |  |  |  | #REF!
G-21-22.18.62 | G-21-22.18.62-001 | Dustbin Troly | Nos | 2 | DPM | Gm | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 25
G-21-22.18.63 | G-21-22.18.63-001 | Water Filter | Nos | 6 | DPM | Gm | Self- Finance | 40 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 40
G-21-22.18.64 | G-21-22.18.64-001 | Other Office Equipment,vacumcleanar, spray machine, grass cuter, mike & etc Fogarmachine |  | Lot | DPM | Gm | Self- Finance | 150 | Plan Dates
Plan Days
[9 empty] | Actual Dates | 2021-10-13: AS per Requirment
| Sub-Total |  |  | 0 |  |  |  | 150
Line Tools & Line man Tools : Schedule 10 as per Budget
G-21-22.18.65 | G-21-22.18.65-001 | Avometer digital,AnaLog | Nos | 3 | RFQ | GM | Self- Finance | 40 | Plan Dates
[9 empty] | Plan Days | 2021-10-13: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 40
G-21-22.18.66 | G-21-22.18.66-001 | Mager digital,AnaLog | Nos | 2 | RFQ | GM | Self- Finance | 200 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 200
G-21-22.18.67 | G-21-22.18.67-001 | chainwheet | Nos |  | DPM | GM | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 25
| Sub-Total | [6 empty] | #REF!
G-21-22.18.68 | G-21-22.18.68-001 | Clip On Meter | Nos | 3 | DPM | GM | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.68-002 | Weight Machin | Nos | 5 | DPM | GM | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 75
G-21-22.18.69 | G-21-22.18.69-001 | Amartong Hot Stick | Nos | 5 | RFQ | GM | Self- Finance | 51 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 51
G-21-22.18.70 | G-21-22.18.70-001 | Oil Testing Mechin | Nos | 1 | RFQ | GM | Self- Finance | 400 | Plan Dates | 2021-03-03 | 2021-03-13 | 2021-03-16 | 2021-03-31 | 2021-04-03 | 2021-04-06 | 2021-07-05
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| Sub-Total | [6 empty] | 400
G-21-22.18.71 | G-21-22.18.71-001 | Power Factor Meter | Nos | 7 | RFQ | GM | Self- Finance | 200 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.71-002 | Alco meter | Nos | Lot | RFQ | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 300
G-21-22.18.72 | G-21-22.18.72-001 | Wellding Machin | Nos | 1 | RFQ | GM | Self- Finance | 45 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 45
G-21-22.18.73 | G-21-22.18.73-001 | Widing Machin | Nos | 2 | RFQ | GM | Self- Finance | 40 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 40
G-21-22.18.74 | G-21-22.18.74-001 | Cooling Fan | Nos | 9 | RFQ | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment ( Limit of financial delegation)
Actual Dates
G-21-22.18.75 | G-21-22.18.75-001 | Cooling Fan | Nos | 9 | DPM | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 600
G-21-22.18.76 | G-21-22.18.76-001 | Workshop Fachilities & groundingset | Nos | Lot | RFQ | GM | Self- Finance | 500 | Plan Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
Plan Days
Actual Dates
| G-21-22.18.76-002 | handlineblock (single) | Nos | Lot | RFQ | GM | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.76-003 | handlineblock (block) | Nos | Lot | RFQ | GM | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.76-004 | Earth Tester | Nos | Lot | RFQ | GM | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
G-21-22.18.77 | G-21-22.18.77-001 | Digital Multimeter | Nos | 6 | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment ( Limit of financial delegation)
Actual Dates
G-21-22.18.78 | G-21-22.18.78-001 | voltage steplizer | Nos | Lot | RFQ | GM | Self- Finance | 75 | Plan Dates
Plan Days
Actual Dates
G-21-22.18.79 | G-21-22.18.79-001 | voltage steplizer | Nos | 20 | DPM | GM | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.79-002 | chaintop | Nos | 25 | DPM | GM | Self- Finance | 17 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.79-003 | gasweldingset | Nos | 25 | DPM | GM | Self- Finance | 21 | Plan Dates
Plan Days
Actual Dates
G-21-22.18.80 | G-21-22.18.80-001 | handgrinder | Nos | Lot | RFQ | GM | Self- Finance | 65 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment
Actual Dates
G-21-22.18.81 | G-21-22.18.81-001 | players | Nos | 50 | DPM | GM | Self- Finance | 23 | Plan Dates
Plan Days
Actual Dates
| G-21-22.18.81-002 | metar berch | Nos | Lot | DPM | GM | Self- Finance | 60 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment
Actual Dates
G-21-22.18.82 | G-21-22.18.82-001 | solar betary/pole numbering (GIS) | Nos | Lot | RFQ | GM | Self- Finance | 150 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment ( Limit of financial delegation)
Actual Dates
G-21-22.18.83 | G-21-22.18.83-001 | solar betary/pole numbering (GIS) | Nos | Lot | DPM | GM | Self- Finance | 50 | Plan Dates
[9 empty] | Plan Days | 2021-03-13: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 1311 | Plan Dates
G-21-22.18.84 | G-21-22.18.84-001 | Mezaring Tape | Nos |  | DPM | GM | Self- Finance | 12 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 12 | Plan Dates
G-21-22.18.85 | G-21-22.18.85-001 | Folding Hot Stick | Nos | 45 | OTM | GM | Self- Finance | 600 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
G-21-22.18.86 | G-21-22.18.86-001 | Folding Hot Stick | Nos | 45 | DPM | GM | Self- Finance | 200 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| Sub-Total | [6 empty] | 800 | Plan Dates
G-21-22.18.87 | G-21-22.18.87-001 | Sub-Station Pad & other | Nos | Lot | OTM | GM | Self- Finance | 4700 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 4700 | Plan Dates
G-21-22.18.89 | G-21-22.18.89-001 | Lineman Tools | Nos | Lot | RFQ | GM | Self- Finance | 500 | Plan Days
Actual Dates
AS per Requirment ( Limit of financial delegation)
G-21-22.18.90 | G-21-22.18.90-001 | Lineman Tools | Nos | Lot | DPM | GM | Self- Finance | 50 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| Sub-Total | [6 empty] | 550 | Plan Dates
Communication Equipment : Schedule (11) as per Budget | [8 empty] | Plan Dates
G-21-22.18.91 | G-21-22.18.91-001 | Mobile Phone set & Others | Nos | 20 | DPM | GM | Self- Finance | 100 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| G-21-22.18.91-002 | PABX | Nos | 3 | DPM | GM | Self- Finance | 150 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| Sub-Total |  |  | 60 |  |  |  | 250 | Plan Dates
G-21-22.18.92 | G-21-22.18.92-001 | E-mail & internet | Nos |  | DPM | GM | Self- Finance | 500 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| Sub-Total | [6 empty] | 500 | Plan Dates
G-21-22.18.93 | G-21-22.18.93-001 | intercom set/seting | Nos | 24 | RFQ | GM | Self- Finance | 65 | Plan Days
Actual Dates
G-21-22.18.94 | G-21-22.18.94-001 | telephone set | Nos | 6 | DPM | GM | Self- Finance | 25 | Plan Days
Actual Dates
| G-21-22.18.94-002 | bertary & others | Nos |  | DPM | GM | Self- Finance | 50 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| Sub-Total | [6 empty] | 140
Transport Equipment (Vehicle) : Schedule (13) as per Budget | [8 empty] | Plan Dates
G-21-22.18.95 | G-21-22.18.95-001 | Triple of Pick Up & others, etc | Nos | 3 | DPM | GM | Self- Finance | 90 | Plan Days
[9 empty] | Actual Dates | 2021-03-13: AS per Requirment ( Limit of financial delegation)
| G-21-22.18.95-002 | Pick Up | Nos | 1 | OTM | GM | Self- Finance | 6000 | Plan Days
Actual Dates
| Sub-Total |  |  | 3 |  |  |  | 6090 | Plan Dates
G-21-22.18.96 | G-21-22.18.96.001 | Motor Cycle | Nos | 20 | DPM Atlas | GM | Self- Finance | 3500 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 3500 | Plan Dates
G-20-21.18.97 | G-21-22.18.97-001 | Helmate | Nos | 20 | DPM | GM | Self- Finance | 40 | Plan Days
[9 empty] | Actual Dates | 2021-03-03: AS per Requirment ( Limit of financial delegation)
| Sub-Total |  |  | 40 |  |  |  | 40 | Plan Dates
G-21-22.18.98 | G-21-22.18.98-001 | Transformer Carring Troli | Nos | 5 | DPM | GM | Self- Finance | 20 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 20
Depriciation : Schedule 15 as per Budget | [8 empty] | Plan Dates
G-21-22.18.99 | G-21-22.18.99-001 | Wooden Furniture | Nos | Lot | RFQ | GM | Self- Finance | 450 | Plan Days | 2021-04-25 | 2021-05-05 | 2021-05-08 | 2021-05-23 | 2021-05-26 | 2021-05-29 | 2021-08-27
[9 empty] | Actual Dates | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
G-21-22.18.100 | G-21-22.18.100-001 | Wooden Furniture | Nos | Lot | DPM | GM | Self- Finance | 50 | Plan Days
| Sub-Total | [6 empty] | 500 | Plan Dates
G-21-22.18.101 | G-21-22.18.101-001 | Steel Furniture | Nos | Lot | RFQ | GM | Self- Finance | 275 | Plan Days | 2021-05-04 | 2021-05-14 | 2021-05-17 | 2021-06-01 | 2021-06-04 | 2021-06-07 | 2021-09-05
[9 empty] | Actual Dates | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
G-21-22.18.102 | G-20-21.18.102-001 | Steel Furniture | Nos | 15 | DPM | GM | Self- Finance | 50 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 300 | Plan Dates
G-21-22..18.103 | G-21-22..18.103-001 | Ferniture & Goods of Rest House | Nos |  | RFQ | GM | Self- Finance | 100 | Plan Days
Actual Dates
G-21-22..18.104 | G-21-22..18.104-001 | Ferniture & Goods of Rest House | Nos |  | DPM | GM | Self- Finance | 25 | Plan Days
[9 empty] | Actual Dates | 2021-05-14: AS per Requirment
G-21-22..18.105 | G-21-22..18.105-001 | Computer & Accessoris | Nos | 10 | OTM | BREB Board | Self- Finance | 700 | Plan Days
Actual Dates
| G-21-22.18.105-002 | server | Nos | 3 | OTM | BREB Board | Self- Finance | 900 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 1600 | Plan Dates
G-21-22..18.106 | G-21-22..18.106-001 | Motor Cycle | nos | 20 | DPM Atlas | BREB | Self- Finance | 3000 | Plan Days | 2021-05-10 | 2021-05-20 | 2021-05-23 | 2021-06-07 | 2021-06-10 | 2021-06-13 | 2021-09-11
[9 empty] | Actual Dates | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
| Sub-Total | [6 empty] | 3000 | Plan Dates
G-21-22..18.107 | G-21-22.18.107-001 | calculator | Nos | 25 | RFQ | GM | Self- Finance | 50 | Plan Days
[9 empty] | Actual Dates | 2021-05-10: AS per Requirment ( Limit of financial delegation)
| G-21-22..18.107-002 | Computer Software | Nos | Lot | RFQ | GM | Self- Finance | 400 | Plan Days | 2021-05-20: AS per Requirment ( Limit of financial delegation)
Actual Dates
G-21-22..18.108 | G-21-22..18.108-001 | Computer Software | Nos | lot | DPM | GM | Self- Finance | 100 | Plan Days | 2021-05-20: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 450 | Plan Dates
G-21-22..18.109 | G-21-22..18.109-001 | Paddlestand Fan | Nos | 4 | DPM | GM | Self- Finance | 25 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 25 | Plan Dates
G-21-22..18.110 | G-21-22..18.110-001 | Fire Extinguisher | Nos | 25 | RFQ | GM | Self- Finance | 40 | Plan Days
Actual Dates
| Sub-Total | [6 empty] | 40 | Plan Dates
G-21-22.18.111 | G-21-22..18.111-001 | Aircooler | Nos | 3 | RFQ | GM | Self- Finance | 300 | Plan Days | 2021-07-12 | 2021-07-22 | 2021-07-25 | 2021-08-09 | 2021-08-12 | 2021-08-15 | 2021-11-13
[9 empty] | Actual Dates | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
| Sub-Total | [6 empty] | 300 | Plan Dates
G-21-22..18.112 | G-21-22..18.112-001 | Comunication Goods & others | Nos | Lot | RFQ | GM | Self- Finance | 100 | Plan Days
[9 empty] | Actual Dates | 2021-07-25: AS per Requirment
G-21-22..18.113 | G-21-22..18.113-001 | Comunication Goods & others | Nos | Lot | DPM | GM | Self- Finance | 100 | Plan Days
[9 empty] | Actual Dates | 2021-07-25: AS per Requirment
G-21-22..18.114 | G-21-22..18.114-001 | Electrical & Electronics etc | Nos | Lot | DPM | GM | Self- Finance | 100 | Plan Days
[9 empty] | Actual Dates | 2021-07-25: AS per Requirment
| Sub-Total | [6 empty] | 300 | Plan Dates
Total (2021-2022) in Thousand Tk. | [7 empty] | 220108

## APP Goods R
ANNUAL PROCUREEMT PLAN FOR GOODS (2021-22)
(Revenue Budget)
Ministry/Division |  |  | : | Power Division
Agency |  |  | : | Bangladesh Rural Electrification Board
Procuring Entity Name & Code |  |  | : | Dinajpur Polly Bidyut Samity-1
Servicing and Maintenance : Schedule 01 as per Budget
Tender Package No. | Lot | Description of procurement package Goods | Unit | Qnty. | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (000) | Time Code for Process | Advertise Tender Date | Tender Opening Date | Tender Evaluation | Approval of Award | Notification of Award | Signing of Contract | Completion of Contract | Total Time (in days)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
G-21-22..18.01 | G-21-22..18.01-001 | Tyre Tube (Zeep Pickup) | Nos | 15 | RFQ | GM | Self- Finance | 300 | Plan Dates
Plan Days
[9 empty] | Actual Dates |  | AS per Requirment
| G-21-22..18.01-002 | Tyre Tube (Zeep Pickup) | Nos | 15 | RFQ | GM | Self- Finance | 300 | Plan Dates
Plan Days
Actual Dates
| G-21-22..18.01-003 | Tyre Tube (Zeep Pickup) | Nos | 10 | RFQ | GM | Self- Finance | 100 | Plan Dates
Plan Days
Actual Dates
G-21-22..18.02 | G-21-22..18.02-001 | Tyre Tube (Zeep Pickup) | Nos | 5 | DPM | GM | Self- Finance | 100 | Plan Dates |  | AS per Requirment ( Limit of financial delegation)
Plan Days
Actual Dates
| Sub-Total |  |  | 15 |  |  |  | 800
G-21-22..18.03 | G-21-22..18.03-001 | Tyre Tube (Motor Cycle) | Nos | 60 | DPM | GM | Self- Finance | 300 | Plan Dates | 2020-09-05
Plan Days
Actual Dates
| Sub-Total |  |  | 60 |  |  |  | 300
G-21-22..18.04 | G-21-22..18.04-001 | Maintenance, Spare Parts for Motor Cycle, Zeep & Pickup | Nos | Lot | DPM | GM | Self- Finance | 1000 | Plan Dates | As Per Requirement
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 1000
G-21-22..18.05 | G-21-22..18.05.001 | Over Holling | Nos | 4 | RFQ | GM | Self- Finance | 300 | Plan Dates | 2021-08-30 | 2021-09-09 | 2021-09-12 | 2021-09-27 | 2021-09-30 | 2021-10-03 | 2022-01-01
[9 empty] | Plan Days | 0 | 10 | 3 | 15 | 3 | 3 | 90 | 124
Actual Dates
| Sub-Total | [6 empty] | 300
G-21-22..18.06 | G-21-22..18.06-001 | Servicing (Zeep, Pickup & Motor Cycle) | Nos |  | DPM | GM | Self- Finance | 300 | Plan Dates | 2021-08-30: As Per Requirement
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 300
G-21-22..18.07 | G-21-22.18.07-001 | Other | Nos |  | DPM | GM | Self- Finance | 150 | Plan Dates | 2021-08-30: AS per Requirment ( Limit of financial delegation)
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 150
G-21-22..18.08 | G-21-22..18.08-001 | Transformer Oil | Nos |  | DPM | GM | Self- Finance | 3000 | Plan Dates | 2021-08-30: 2020-10-10
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 3000
G-21-22..18.09 | G-21-22.18.09-001 | Super Enamel Coper Wire (Transformer/OCR/ Regulator Maintenance) |  | Lot | DPM GAZiWare /OTM | GM | Self- Finance | 5000 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| G-21-22..18.09-002 | Super Enamel Coper Wire (Transformer/OCR/ Regulator Maintenance) |  | Lot | DPM GAZiWare /OTM | GM | Self- Finance | 5000 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| G-21-22..18.09-003 | Super Enamel Coper Wire (Transformer/OCR/ Regulator Maintenance) |  | Lot | DPM GAZiWare /OTM | GM | Self- Finance | 5000 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| G-21-22..18.09-004 | Super Enamel Coper Wire (Transformer/OCR/ Regulator Maintenance) |  | Lot | DPM GAZiWare /OTM | GM | Self- Finance | 5000 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 20000
G-21-22..18.10 | G-21-22..18.10-001 | Hardware Materials of Workshop (Transformer/OCR/Regulator Maintenance) |  | Lot | OTM | Gm | Self- Finance | 2300 | Plan Dates
Plan Days
Actual Dates
G-21-22.18.11 | G-21-22..18.11-001 | Hardware Materials of Workshop (Transformer/OCR/Regulator Maintenance) |  | Lot | RFQ | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 2600
Leaverage : Schedule 03 as per Budget
G-21-22..18.12 | G-21-22..18.12-001 | Uniform Summer Seasone | Nos | Lot | RFQ | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
G-21-22..18.13 | G-21-22..18.13-001 | Jacket, Pool over Winter Seasone | Nos | Lot | RFQ | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
G-21-22..18.14 | G-21-22..18.14-001 | Uniform/ Jacket, Pool over | Nos | Lot | DPM | GM | Self- Finance | 25
AS per Requirment ( Limit of financial delegation)
Actual Dates
G-21-22..18.15 | Sub-Total | [6 empty] | 625 |  | 2021-09-09: Plan Dates
| G-20-21.18.15.001 | Umbrella, Bag, Raincoat | Nos | Lot | RFQ | GM | Self- Finance | 300 | Plan Dates | 2021-09-09: Plan Days
Plan Days
Actual Dates
G-21-22..18.16 | G-21-22..18.16.001 | Umbrella, Bag, Raincoat | Nos | Lot | DPM | GM | Self- Finance | 25 | Plan Dates | 2021-09-09: Plan Days
[9 empty] | Plan Days | 2021-09-12: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 325
G-21-22..18.17 | G-21-22..18.17-001 | Uniform/ Jacket, Pool over | Nos | Lot | DPM | GM | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| G-21-22..18.17-002 | Uniform/ Jacket, Pool over | Nos | Lot | DPM | GM | Self- Finance | 25 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 50
G-21-22..18.18 | G-21-22..18.18.001 | Lineman Boot, Shoe, Pum shoe, GumBoot (EPSI/BMTF) | Nos | Lot | DPM | GM | Self- Finance | 600 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 600
G-21-22..18.19 | G-21-22..18.19.001 | Sports & Entertainment | Nos |  | DPM | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 300
Printing & Stationary: Schedule 06 as per Budget
G-21-22..18.20 | G-21-22..18.20.001 | Computer Bill Form & Protyon Patra | Nos |  | OTM | BREB | Self- Finance | 5500 | Plan Dates
Plan Days
Actual Dates
G-21-22..18.21 | G-21-22..18.21.001 | Computer Bill Form & Protyon Patra | Nos |  | RFQ | GM | Self- Finance | 300 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 5800
G-21-22..18.22 | G-21-22..18.22-001 | Printing | Nos | Lot | OTM | BREB | Self- Finance | 2000 | Plan Dates
Plan Days
Actual Dates
G-21-22.18.23 | G-21-22..18.23-001 | Printing | Nos | Lot | RFQ | Gm | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 2300
G-21-22..18.24 | G-21-22..18.24-001 | Stationary | Nos | Lot | OTM | BREB | Self- Finance | 1500 | Plan Dates
Plan Days
Actual Dates
G-21-22..18.25 | G-21-22..18.25-001 | Stationary | Nos | Lot | RFQ | BREB | Self- Finance | 300 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 1800
G-21-22.18.26 | G-21-22..18.26-001 | Printing | Nos | Lot | DPM | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 200
G-21-22..18.27 | G-21-22.18.27-001 | Printing (In Emergency), Annual Meeting & Other | Nos | Lot | DPM | GM | Self- Finance | 600 | Plan Dates | 2021-08-30: As Per Requirement
[9 empty] | Plan Days | [7 empty] | 0
Actual Dates
| Sub-Total | [6 empty] | 600
G-21-22..18.28 | G-21-22..18.28-001 | Binder | Nos |  | RFQ | GM | Self- Finance | 300 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 300
G-21-22..18.29 | G-21-22..18.29-001 | Stationary | Nos |  | DPM | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 200
G-21-22..18.30 | G-21-22.18.30-001 | Ribon & Toner , Sold Distributor | Nos | Lot | DPM | GM | Self- Finance | 600 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| G-21-22..18.30-002 | Ribon & Toner , Sold Distributor | Nos | Lot | DPM | GM | Self- Finance | 600 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| G-21-22..18.30-003 | Ribon & Toner , Sold Distributor | Nos | Lot | DPM | GM | Self- Finance | 600 | Plan Dates | 2021-09-09: AS per Requirment
Plan Days
Actual Dates
| G-21-22..18.30-004 | Ribon & Toner , Sold Distributor | Nos | Lot | DPM | GM | Self- Finance | 600 | Plan Dates
[9 empty] | Plan Days | 2021-09-09: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 2400
Petrol & Octen : Schedule 07 as per Budget
G-21-22..18.31 | G-21-22..18.31.001 | Fuel (Petrol / Octen, Disle & Mobil) |  | Lot | DPM | GM | Self- Finance | 7000 | Plan Dates | 2021-08-30: As Per Requirement
Plan Days
[9 empty] | Actual Dates | 2021-09-12: AS per Requirment
| Sub-Total | [6 empty] | 7000
BiBIDH : Schedule 08 as per Budget
G-21-22..18.32 | G-21-22..18.32.001 | BREB News Letter, News Paper & Megazine |  | Lot | DPM | GM | Self- Finance | 70 | Plan Dates | 2021-08-30: 2020-11-11
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 70
G-21-22..18.33 | G-21-22.18.33.001 | Perchase of Books, Calculator, Crokarige, Charger Light & Other | Nos | Lot | DPM | GM | Self- Finance | 210 | Plan Dates | 2021-08-30: 2021-01-01
[9 empty] | Plan Days | 2021-09-12: AS per Requirment | 0
Actual Dates
| Sub-Total | [6 empty] | 210
G-21-22..18.34 | G-21-22..18.34.001 | Tree Plantation | Nos | Lot | DPM | GM | Self- Finance | 50 | Plan Dates | 2021-08-30: 2021-01-01
[9 empty] | Plan Days | 2021-09-12: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 50
G-21-22..18.35 | G-21-22.18.35-001 | Bidyut Soptah, National Entegrity, Ethics & Other ocession | Nos | Lot | DPM | GM | Self- Finance | 900 | Plan Dates | 2021-08-30: As Per Requirement
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 900
Revenue Stamp : Schedule 04 as per Budget
G-21-22..18.36 | G-21-22.18.36-001 | Revenue Stamp, Insurances & tax |  |  | DPM | GM | Self- Finance | 5500 | Plan Dates | 2021-08-30: As Per Requirement
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 5500
Meeting & Cons. ID Card : Schedule12 as per Budget
G-21-22..18.37 | G-21-22.18.37-001 | Annual General Meeting, TA/DA PBS Bord director |  | Lot | DPM | GM | Self- Finance | 1650 | Plan Dates | 2021-08-30: 2020-02-10
[9 empty] | Plan Days | 2021-09-12: AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 1650
G-21-22..18.38 | G-21-22..18.38-001 | Employee & Consumer ID card |  | Lot | DPM | GM | Self- Finance | 150 | Plan Dates | 2021-08-30: 2020-11-10
[9 empty] | Plan Days | 2021-09-12: AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 150
Total (2021-2022) in Thousand Tk. | [7 empty] | 59270

## APP_Works
ANNUAL PROCUREEMT PLAN FOR WORKS (2021-22)
(Capital Budget)
Ministry/Division |  |  | : | Power Division
Agency |  |  | : | Bangladesh Rural Electrification Board
Procuring Entity Name & Code |  |  | : | Dinajpur Polly Bidyut Samity- 1
O&M : Schedule 3 & 15 as per Budget (Distribution Line Construction)
Tender Package No. | Lot | Description of procurement package works | Unit | Qnty. | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. ('000') | Time Code for Process | Advertise Tender Date | Tender Opening Date | Tender Evaluation | Approval of Award | Notification of Award | Signing of Contract | Completion of Contract | Total Time (in days)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
W-21-22.18.01 | W-21-22..18.01-001 | Line Construction of PBS Own Fund | Nos | Lot | LTM | PBS | Self- Finance | 30000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 30000
W-21-22..18.02 | W-21-22..18.02-001 | Line Construction of Deposit Works | Nos | Lot | LTM | PBS | Self- Finance | 10000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 10000
W-21-22..18.03 | W-21-22..18.03-001 | other Bill (Other Project) | Nos | Lot | DPM | PBS | Self- Finance | 2000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 2000
Schedule 4 & 15 as per Budget (Civil Work)
W-21-22.1.18.04 | W-21-22..18.04-001 | Office Building Construction | Nos | Lot | RFQ | BREB | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment |  |  |  |  | 0
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 200
W-21-22..18.05 | W-21-22.1.18.05-001 | Office Building Construction (Garrage) | Nos | Lot | RFQ | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 200
W-21-22..18.06 | W-21-22..18.06-001 | Construction Of Boundary Wall | Nos | 1 | RFQ | BREB | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment |  |  |  |  | 0
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
W-21-22..18.07 | W-21-22..18.07-001 | Construction of Substation Yeard | Nos | Lot | RFQ | GM | Self- Finance | 1200 | Plan Dates
[9 empty] | Plan Days |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 1200
W-21-22..18.08 | W-21-22..18.08-001 | Construction of Substation Yeard | Nos | Lot | OTM | GM | Self- Finance | 3800 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 3800
W-21-22..18.09 | W-21-22..18.09-001 | Construction of Dren | Nos | Lot | RFQ | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 200
W-21-22..18.10 | W20-21.18.10-001 | Internal Road | Nos | Lot | OTM | GM | Self- Finance | 8250 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
W-21-22..18.11 | W-21-22..18.11-001 | Internal Road | Nos | Lot | DPM | GM | Self- Finance | 50 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 8300
W-21-22..18.12 | W-21-22..18.12-001 | Construction of Water Line | Nos | Lot | DPM | GM | Self- Finance | 100 | Plan Dates |  |  | AS per Requirment ( Limit of financial delegation)
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
W-21-22..18.13 | W-21-22..18.13-001 | Dustbin | Nos |  | DPM | GM | Self- Finance | 50 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| W-21-22.18.13-002 | sports field/children park & garden light etc | Nos | Lot | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
W-21-22..18.14 | W-21-22..18.14-001 | sports field/children park & garden light etc | Nos | Lot | RFQ | GM | Self- Finance | 75 | Plan Dates
[9 empty] | Plan Days |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 150
W-21-22..18.15 | W-21-22..18.15-001 | Water Pump/ Tubewell & other | Nos |  | DPM | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 200
W-21-22..18.16 | W-21-22..18.16-001 | Sign Board & Stone Name Falak | Nos |  | DPM | GM | Self- Finance | 100 | Plan Dates | AS per Requirment ( Limit of financial delegation)
Plan Days
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 100
Schedule 06 as per Budget (Land/Land Development)
W-21-22..18.17 | W-21-22..18.17-001 | Land Purches | Nos |  | OTM (Negociation) | BREB | Self- Finance | 40000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 40000
W-21-22..18.18 | W-21-22..18.18-001 | Land Devlopment | Nos |  | DPM | GM | Self- Finance | 427 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment |  |  |  |  | 0
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 427
Schedule 07 as per Budget (Retainer Consultant ELECTRIC)
W-21-22..18.19 | W-21-22..18.19-001 | Retainer Consultant own PBS | Nos |  | DPM | GM | Self- Finance | 3000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 3000
| W-21-22..18.19-001 | Retainer Consultant Deposit Work | Nos |  | DPM | GM | Self- Finance | 3000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 3000
W-21-22.18.20 | W-21-22..18.20-001 | Purto Consultant Fee | Nos | Lot | DPM | GM | Self- Finance | 1500 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 1500
W-21-22..18.21 | W-21-22..18.21-001 | Computer Retainer Fee | Nos | Lot | DPM | GM | Self- Finance | 1500 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 1500
W-21-22..18.22 | W-21-22..18.22-001 | Manmanth | Nos | Lot | DPM | GM | Self- Finance | 2000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 2000
W-21-22..18.23 | W-21-22.18.23-001 | Sub station ConstractionS | Nos | Lot | OTM | GM | Self- Finance | 60000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 60000
W-21-22..18.24 | W-21-22..18.24-001 | Master Plan | Nos | Lot | DPM | GM | Self- Finance | 1500 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total |  |  | 0 |  |  |  | 1500
W-21-22..18.25 | W-21-22..18.25-001 | Matarial Carring FormCentral Wire house | Nos |  | DPM | GM | Self- Finance | 1500 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 1500
W-21-22.18.26 | W-21-22.18.26-001 | Matarial Carring Form other PBS | Nos |  | DPM | GM | Self- Finance | 1000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
W-21-22.18.27 | W-21-22..18.27-001 | Garden boundary & Fenching | Nos |  | RFQ | GM | Self- Finance | 750 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 1750
W-21-22.18.28 | W-21-22..18.28-001 | Matarial Carring Form PBS to other Office | Nos |  | DPM | GM | Self- Finance | 250 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
250
| Sub-Total | [6 empty] | 172977
Note on I79: ASUS:

## APP Works R
ANNUAL PROCUREEMT PLAN FOR WORKS (2021-2022)
(Revenue Budget)
Ministry/Division |  |  | : | Power Division
Agency |  |  | : | Bangladesh Rural Electrification Board
Procuring Entity Name & Code |  |  | : | Dinajpur Polly Bidyut Samity- 1
Maintenance : Schedule 01 as per Budget
Tender Package No. | Lot | Description of procurement package Works | Unit | Qnty. | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (Lac) | Time Code for Process | Advertise Tender Date | Tender Opening Date | Tender Evaluation | Approval of Award | Notification of Award | Signing of Contract | Completion of Contract | Total Time (in days)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
W-21-22..18.01 | W-21-22..18.01-001 | Building Maintenance | Nos |  | DPM | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 300
W-21-22..18.02 | W-21-22..18.02-001 | Tiles (VIP Rest House) | Nos |  | RFQ | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 200
W-21-22.1.18.03 | W-21-22..18.03-001 | White Wash/ Distemper / Sloshem/Weathercoat | Nos |  | RFQ | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| W-21-22..18.03-002 | White Wash/ Distemper / Sloshem/Weathercoat | Nos |  | RFQ | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 500
W-21-22..18.04 | W-21-22..18.04-001 | White Wash/ Distemper / Sloshem/Weathercoat | Nos |  | DPM | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 100
W-21-22..18.05 | W-21-22..18.05-001 | Repair of Office Equipment | Nos |  | RFQ | GM | Self- Finance | 600 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
W-21-22..18.06 | W-21-22..18.06-001 | Repair of Office Equipment | Nos |  | DPM | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 700
W-21-22..18.07 | W-21-22..18.07-001 | Office Yeard Clean & Repairs | Nos |  | RFQ | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
W-21-22..18.08 | W-21-22..18.08-001 | Office Yeard Clean & Repairs | Nos |  | DPM | GM | Self- Finance | 200 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 400
W-21-22..18.09 | W-21-22.18.09-001 | Road Maintenance | Nos |  | DPM | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 300
W-21-22..18.10 | W-21-22..18.10-001 | Store Yeard colour | Nos |  | RFQ | GM | Self- Finance | 150 | Plan Dates
Plan Days
[9 empty] | Actual Dates |  |  | AS per Requirment
| Sub-Total | [6 empty] | 150
W-21-22.18.11 | W-21-22.18.11-001 | Water Pump Maintenance | Nos |  | RFQ | GM | Self- Finance | 75 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
W-21-22.18.12 | W-21-22..18.12-001 | Water Pump Maintenance | Nos |  | DPM | GM | Self- Finance | 25 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 100
W-21-22..18.13 | W-21-22..18.13-001 | Right Of Way | Nos | lot | DPM | GM | Self- Finance | 8000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 8000
W-21-22..18.14 | W-21-22..18.14-001 | Emergency Maintenance | Nos | lot | DPM | GM | Self- Finance | 2000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 2000
W-21-22..18.15 | W-21-22..18.15-001 | Labour For Line Maintenance | Nos |  | DPM | GM | Self- Finance | 2000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 2000
W-21-22..18.16 | W-21-22..18.16-001 | Repeair & Maintenanc Meterials For Line | Nos |  | DPM | GM | Self- Finance | 6000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 6000
W-21-22..18.17 | W-21-22..18.17-001 | Maintenanc Meterials For Store | Nos |  | DPM | GM | Self- Finance | 150 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 150
W-21-22..18.18 | W-21-22..18.18-001 | Meter Repeair & Maintenanc | Nos |  | DPM | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 300
W-21-22.18.19 | W-21-22..18.19-001 | Tools Repeair & Maintenanc | Nos |  | DPM | GM | Self- Finance | 150 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 150
W-21-22.1.18.20 | W-21-22..18.20-001 | Substatiion Repeair & Maintenanc | Nos |  | DPM | GM | Self- Finance | 9000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 9000
W-21-22..18.21 | W-21-22..18.21-001 | Oil Filter/ Testing | Nos |  | DPM | GM | Self- Finance | 50 | Plan Dates | As Per Requirement
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 50 |  |  |  | AS per Requirment
W-21-22..18.22 | W-21-22..18.22-001 | Pole Numbering | Nos |  | DPM | GM | Self- Finance | 600 | Plan Dates
Plan Days
Actual Dates
| Sub-Total | [6 empty] | 600
W-21-22..18.23 | W-21-22..18.23-001 | Solar Power Battery / Control Room Battery | Nos |  | DPM | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 100
W-21-22..18.24 | W-21-22..18.24-001 | Testing Process develop & Parts | Nos |  | DPM | GM | Self- Finance | 10 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 10
W-21-22..18.24 | W-21-22..18.24-001 | Goods Carring | Nos |  | DPM | GM | Self- Finance | 400 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 400
W-21-22..18.25 | W-21-22..18.25-001 | Land Development , Pond filling & Pay for Pole yard | Nos |  | DPM | GM | Self- Finance | 4000 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 4000
W-21-22..18.26 | W-21-22..18.26-001 | Transformer Oil Centifussing & machine Maintenanc | Nos |  | DPM | GM | Self- Finance | 300 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| W-21-22..18.26-002 | Transformer /ocr & regulator Maintenanc | Nos |  | DPM | GM | Self- Finance | 1500 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| W-21-22..18.26-003 | Transformer Up/down | Nos |  | DPM | GM | Self- Finance | 120 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment
Actual Dates
| Sub-Total | [6 empty] | 1920
W-21-22..18.27 | W-21-22..18.27-001 | HQ Soil Filling & Cleaning Yard | Nos |  | DPM | GM | Self- Finance | 100 | Plan Dates
[9 empty] | Plan Days |  |  | AS per Requirment ( Limit of financial delegation)
Actual Dates
| Sub-Total | [6 empty] | 100
Total (2021-2022) in Thousand Tk. | [7 empty] | 37530

## APP_Service
ANNUAL PROCUREEMT PLAN FOR SERVICES (2021-22)
(Revenue Budget)
Ministry/Division |  |  | : | Power Division
Agency |  |  | : | Bangladesh Rural Electrification Board
Procuring Entity Name & Code |  |  | : | Dinajpur. Polly Bidyut Samity- 1
Bima & Tax: Schedule 04 as per Budget
Tender Package No. | Lot | Description of procurement package Services | Unit | Qnty. | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (Lac) | Time Code for Process | Advertise Tender Date | Tender Opening Date | Tender Evaluation | Approval of Award | Notification of Award | Signing of Contract | Completion of Contract | Total Time (in days)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
S-21-22.18.01 | S-21-22.18.01-001 | 3: Bima (Zeep, Pickup & Motor Cycle); 5: 50; 6: DPM; 7: GM; 8: Self- Finance; 9: 600; 10: Plan Dates; 11: As Per Requirement
Plan Days
[9 empty] | Actual Dates |  | AS per Requirment
| Sub-Total | 5: 50; 9: 600
S-21-22.18.02 | S-21-22.18.02-001 | 3: Root Permit & Resistration Fee; 5: 10; 6: DPM; 7: GM; 8: Self- Finance; 9: 1000; 10: Plan Dates
[9 empty] | Plan Days |  | AS per Requirment
Actual Dates
| Sub-Total | 5: 10; 9: 1000
S-21-22.18.03 | S-21-22..18.03-001 | 3: Substation Bima; 5: 10; 6: DPM; 7: GM; 8: Self- Finance; 9: 2000; 10: Plan Dates
[9 empty] | Plan Days |  | AS per Requirment
Actual Dates
| Sub-Total | 5: 10; 9: 2000
S-21-22.18.04 | S-21-22..18.04-001 | 3: Tax & Bima (Fidality, Workman compansasion, Municiple & Union Parishod, TaX For Land, Wireless Roelty); 6: DPM; 7: GM; 8: Self- Finance; 9: 700; 10: Plan Dates
[9 empty] | Plan Days |  | AS per Requirment
Actual Dates
| Sub-Total | 9: 700
S-21-22.18.05 | S-21-22..18.05-001 | 3: Others Matarial Carring of BREB; 4: Nos; 5: Lot; 6: DPM; 7: PBS; 8: Self- Finance; 9: 113; 10: Plan Dates
[9 empty] | Plan Days |  | AS per Requirment
Actual Dates
| Sub-Total | 5: 0; 9: 113
Schedule 09 as per Budget | [17 empty] | 0
S-21-22..18.06 | S-21-22..18.06-001 | 3: Office Rent.; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 2000; 10: Plan Dates | 0
|  | 10: Plan Days; 12: AS per Requirment | 0
|  | 10: Actual Dates | 0
| S-21-22..18.06-002 | 3: mebial bill; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 1200; 10: Plan Dates | 0
|  | 10: Plan Days; 12: AS per Requirment | 0
|  | 10: Actual Dates | 0
| S-21-22..18.06-003 | 3: entertainment bill; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 500; 10: Plan Dates | 0
|  | 10: Plan Days; 12: AS per Requirment | 0
|  | 10: Actual Dates | 0
| S-21-22..18.06-004 | 3: traveling; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 2500; 10: Plan Dates | 0
|  | 10: Plan Days; 12: AS per Requirment | 0
|  | 10: Actual Dates | 0
| Sub-Total | 5: 0; 9: 6200 | 800
Schedule 10 as per Budget | [17 empty] | 0
S-21-22..18.07 | S-21-22..18.07-001 | 3: Telephone bil/ Mobile Bill; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 1200; 10: Plan Dates
Plan Days
Actual Dates
| Sub-Total | 5: 0; 9: 1200
| S-21-22..18.07-002 | 3: Postage; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 5000; 10: Plan Dates | 0
|  | 10: Plan Days; 12: AS per Requirment | 0
|  | 10: Actual Dates | 0
| Sub-Total | 5: 0; 9: 5000 | 325
Advertisment & Publicity : Schedule 11 as per Budget | [17 empty] | 0
S-21-22..18.08 | S-21-22..18.08-001 | 3: Appointment; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 300; 10: Plan Dates
[9 empty] | Plan Days |  | AS per Requirment
Actual Dates
| Sub-Total | 5: 0; 9: 300
S-21-22..18.09 | S-21-22..18.09-001 | 3: Work order; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 200; 10: Plan Dates
[9 empty] | Plan Days |  | AS per Requirment
Actual Dates
| Sub-Total | 5: 0; 9: 200
S-21-22..18.10 | S-21-22..18.10-001 | 3: Publicity; 4: Nos; 6: DPM; 7: GM; 8: Self- Finance; 9: 550; 10: Plan Dates | 0
|  | 10: Plan Days; 12: AS per Requirment | 0
|  | 10: Actual Dates | 0
| Sub-Total | 5: 0; 9: 550 | 600
Total (2021-2022) in Thousand Tk. |  | 8: 17863 | 1725
1 | Goods | 3: Capital; 4: 220108000
|  | Revenue | 59270000
2 | Works | 3: Capital; 4: 171977000
|  | Revenue | 37530000
3 | Service | 3: Revenue; 4: 17863000
Grant Total = |  | 4: 506748000