## Annual Procurement Plan
Annual Procurement Plan (Non- Services) for 2025-26
Ministry/ Division: Ministry of Civil Aviation & Tourism
Agency: Bangladesh Tourism Board
Procuring Entity Name & Code:
Package No | Description of Procurement Packages SERVICES | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Million Tk. | Time code for process | Advertise EOI | Issue RFP | Technical Proposal Opening | Technical Proposal Evaluation | Financial Proposal Opening & Evaluation | Negotiation | Signing of Contract | Time for Completion of Contract
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 19
SR1 | Tourism Sattelite Account | 1 | 1 | Single Source | CEO, BTB | GoB | 20 | Planned Dates | 2025-10-03 | 2025-10-21 | 2025-11-19 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-23 | 2026-06-30
[8 empty] | Planned Days | 0 | 18 | 29 | 15 | 7 | 7 | 5 | 6 months
Actual Dates
Annual Procurement Plan ( Services) for 2025-26
Ministry/ Division: Ministry of Civil Aviation & Tourism | [8 empty] | 2025-12-18: Budget : Revenue
Agency: Bangladesh Tourism Board
Procuring Entity Name & Code:
Package No | Description of Procurement Packages Non-Consulting Services | Unit | Quantity | Procurement method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Million Tk. | Time code for process | Invite/Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total Time to Contract Signature
Annual Procurement Plan (Goods) for 2025-26
Ministry/ Division: Ministry of Civil Aviation & Tourism | [8 empty] | 2025-12-18: Budget : Revenue
Agency: Bangladesh Tourism Board
Procuring Entity Name & Code:
Package No | Description of Procurement Packages | Unit | Quantity | Procurement method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Million Tk. | Time code for process | Not used in GOODS | Invite / Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of the Contract
GOODS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
GR3 | Office Stationary | 1 | 1 | OTM | CEO, BTB | GoB | 4.1 | Planned Dates |  | 2025-01-02 | 2025-01-30 | 2025-02-19 | 2025-03-04 | 2025-03-11 | 2025-03-25
[8 empty] | Planned Days |  | 0 | 28 | 20 | 13 | 7 | 14
Actual Dates
GR4 | SIGNAGE INSTALLATION | 15 | 45000 | OTM | CEO, BTB | GoB | 30 | Planned Dates |  | 2025-11-05 | 2025-11-26 | 2025-12-17 | 2025-12-28 | 2026-01-04 | 2026-01-22
[8 empty] | Planned Days |  | 0 | 21 | 21 | 11 | 7 | 18
Actual Dates
GR5 | World Tourism Day | 1 | 1 | OTM | CEO, BTB | GoB | 0.5 | Planned Dates |  | 2025-09-01 | 2025-09-14 | 2025-09-16 | 2025-09-18 | 2025-09-18 | 2025-09-18
[8 empty] | Planned Days |  | 0 | 21 | 21 | 14 | 7 | 21
Actual Dates
GR8 | TVC | 1 | 1 | OTM | CEO, BTB | GoB | 0.5 | Planned Dates |  | 2025-12-01 | 2025-12-07 | 2025-12-14 | 2025-12-15 | 2025-12-15 | 2025-12-16
[8 empty] | Planned Days |  | 0 | 21 | 21 | 14 | 7 | 21
Actual Dates
Annual Procurement Plan (Works) for 2025-26
Ministry/ Division: Ministry of Civil Aviation & Tourism | [9 empty] | 2026-01-04: Budget : Revenue
Agency: Bangladesh Tourism Board
Procuring Entity Name & Code:
Package No | Description of Procurement Packages | Unit | Quantity | Procurement method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Million Tk. | Time code for process | Advertise Prequel (if applicable) | Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of the Contract
WORKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
WR2 | Installation of Wifi Station at Different Tourism Attractions | 1 | 40 | OTM | CEO,BTB | GoB | 10 | Planned Dates |  | 2025-08-01 | 2025-08-28 | 2025-09-18 | 2025-09-20 | 2025-09-27 | 2025-10-08
[8 empty] | Planned Days |  | 0 | 27 | 21 | 2 | 7 | 11
Actual Dates
WR3 | SIGNAGE INSTALLATION | 1 | 80 | OTM | CEO,BTB | GoB | 10 | Planned Dates |  | 2025-08-01 | 2025-08-28 | 2025-09-18 | 2025-09-20 | 2025-09-27 | 2025-10-08
[8 empty] | Planned Days |  | 0 | 27 | 21 | 2 | 7 | 11
Actual Dates
Annual Procurement Plan (Non- Services) for 2025-26
Ministry/ Division: Ministry of Civil Aviation & Tourism
Agency: Bangladesh Tourism Board
Procuring Entity Name & Code:
Package No | Description of Procurement Packages SERVICES | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Million Tk. | Time code for process | Advertise EOI | Issue RFP | Technical Proposal Opening | Technical Proposal Evaluation | Financial Proposal Opening & Evaluation | Negotiation | Approval | Time for Completion of Contract
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 19
GR8 | TVC | 1 | 1 | QCBS | CEO, BTB | GoB | 0.5 | Planned Dates |  | 2025-12-01 | 2025-12-07 | 2025-12-14 | 2025-12-15 | 2025-12-15 | 2025-12-16 | 2026-06-30
[8 empty] | Planned Days |  | 0 | 21 | 21 | 14 | 7 | 21
Actual Dates
GR8 | Bangladesh Festival | 1 | 1 | QCBS | CEO, BTB | GoB | 0.5 | Planned Dates |  | 2025-11-01 | 2025-11-07 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2026-06-30
[8 empty] | Planned Days |  | 0 | 21 | 21 | 14 | 7 | 21
Actual Dates
GR8 | Tasty of Bangladesh | 1 | 1 | QCBS | CEO, BTB | GoB | 0.5 | Planned Dates |  | 2025-11-15 | 2025-11-22 | 2025-12-01 | 2025-12-15 | 2025-12-15 | 2025-12-16 | 2026-06-30
[8 empty] | Planned Days |  | 0 | 21 | 21 | 14 | 7 | 21
Actual Dates
GR8 | Harmony Festival | 1 | 1 | QCBS | CEO, BTB | GoB | 0.5 | Planned Dates |  | 2025-12-01 | 2025-12-07 | 2025-12-14 | 2025-12-15 | 2025-12-15 | 2025-12-16 | 2026-06-30
[8 empty] | Planned Days |  | 0 | 21 | 21 | 14 | 7 | 21
Actual Dates