## Ongoing
WEST ZONE POWER DISTRIBUTION COMPANY LTD. (An Enterprise of Bangladesh Power Development Board) Bidyut Bhaban, Boyra Main Road, Khulna.Ph: 041-730484, Fax: 041-731786 Project Status
Ongoing Projects:
Sl No. | Name of the Project and Project period | Program/Project wise indicative cost with Source of Finance (Lakh Tk& Million US$) | Financed by | Scope of Works
|  |  |  | Tagets |  |  | Progress (Upto 30.10.2018) | Progress (Upto 30.10.2018) | Under Processing
|  |  |  | Item | Unit | Quantity
1 | Strengthening Power Distribution System project July’14 – June’19 | • Total : 83243.66 Lakh Taka=106.72 Million US$ • GOB : 78801.14 Lakh Taka=101.03 Million US$ • WZPDCL: 4442.52 Lakh Taka=5.69 Million US$ • P.A : 0.0 Lakh Taka =0.0 Million US$ | GOB | 33KV Overhead Line(new) | km | 70 | 29 |  | 41 | Progress
|  |  |  | 33KV XLPE Single Core Submarine Cable(new) | km | 68 | 0 |  | 68 | new | 953.06
|  |  |  | 33KV U/G Cable (new) | km | 20 | 0 |  | 20 | reno | 803.95
|  |  |  | 33 KV overhead line (renovation) | km | 100 | 21 |  | 79 | total line work | 1757.01
|  |  |  | 11KV overhead line (new) | km | 100 | 138.13 |  | -38.13
|  |  |  | 11KV U/G Cable (new) | km | 10 | 4.85 |  | 5.15
|  |  |  | 11 KV overhead line (renovation) | km | 100 | 80.49 |  | 19.51 | target
|  |  |  | 11/0.4 KV overhead line (new) | km | 441 | 351.83 |  | 89.17 | new | 1081
|  |  |  | 11/0.4 KV overhead line (renovation) | km | 277 | 259.49 |  | 17.51 | reno | 777
|  |  |  | 0.4 KV overhead line (new) | km | 372 | 434.1 |  | -62.1 | total line work | 1858
|  |  |  | 0.4 KV overhead line (renovation) | km | 300 | 442.97 |  | -142.97
|  |  |  | 11/0.4 KV distribution transformer (new) | Nos. | 2100 | 1515 |  | 585
|  |  |  | 33/11 KV Sub-staion (new) | Nos. | 3 | 1 |  | 2
|  |  |  | 33/11 KV Sub-staion (renovation) | Nos. | 11 |  |  | 11
|  |  |  | Financial Progress (%) | FY 2018-19 | 20.03% | Overall |  | 57.12%
|  |  |  | Physical Progress (%) | FY 2018-19 | 31% | Overall |  | 72%
2 | Expansion and Upgradation of Power Distribution System in West Zone Area July’16 – June’19 | • Total: 127819.42 Lakh Taka =163.20 Million US$ • GOB: 124978.09 Lakh Taka= 159.73 Million US$ • WZPDCL: 2841.33 Lakh Taka=3.63 Million US$ • P.A. : 0.0 Lakh Taka=0.0 Million US$ | GOB | 33KV overhead/underground line (new) | km | 449 | 15 |  | 434
|  |  |  | 33 KV overhead line (renovation) | km | 605 | 0 |  | 605
|  |  |  | 11KV overhead line (new) | km | 62 | 62 |  | 0 | new | 511
[7 empty] | (Procurement) |  |  | reno | 605
|  |  |  | 11/0.4 KV distribution transformer (new) | Nos. | 1722 | 719 |  | 1003
(Installation)
|  |  |  | 33/11 KV Sub-staion (new) | Nos. | 31 | 6 |  | 49
4Nos. Contract signed & 02 Nos. Evaluation Going on
|  |  |  | 33/11 KV Sub-staion (renovation) | Nos. | 32 | 8 |  |  | new | 2408.92
[7 empty] | 08 Nos. Evaluation Going on |  |  | reno | 2390.24
|  |  |  | Financial Progress | FY 2018-19 | 26.88% | Overall |  | 19.8%
|  |  |  | Physical Progress | FY 2018-19 | 42.29% | Overall |  | 39%
3 | Extension & Augmentation of Power Distribution System Project in West Zone Area. July’17 – June’21 | Total :124905.05 Lakh Taka=156.13 Million US$  GOB :119789.51 Lakh Taka=149.749 Million US$ WZPDCL: 5115.54 Lakh Taka=6.39 Million US$  P.A : 0 Lakh Taka= 0 Million US$ | GOB | 11KV overhead line (new) | km | 587.9 | 13 Tender is invited of FY-2018-19 Contract sign of all package for fy 2017-18. material delivery of all contract for fy 2017-18 is complete.
|  |  |  | 11 KV overhead line (renovation) | km | 620.87
|  |  |  | 11/0.4 KV overhead line (new) | km | 866.22
|  |  |  | 11/0.4 KV overhead line (renovation) | km | 736.98
|  |  |  | 0.4 KV overhead line (new) | km | 954.8
|  |  |  | 0.4 KV overhead line (renovation) | km | 1032.39
|  |  |  | 11/0.4 KV distribution transformer (new) | Nos. | 2530
|  |  |  | Non-residencial civil works (Office and others) | sq.m | 35638.18
|  |  |  | Residencial civil works | sq.m | 17640.63
|  |  |  | Financial Progress | FY 2018-19 | 39.36% | Overall |  | 4.1%
|  |  |  | Physical Progress | FY 2018-19 | 46.29% | Overall |  | 28.1%
4 | Smart Prepayment Metering Project For West Zone Power Distribution Company Ltd. (WZPDCL) Area. July/17-June/20 |  Total : 42637.00 Lakh Taka=53.31 Million US$  GOB : 41253.91 Lakh Taka=51.58 Million US$  WZPDCL: 1383.09 Lakh Taka=1.73 Million US$  P.A : 0.00 Lakh Taka= 0.00 Million US$ | GOB | To install 5,00,000 nos of Pre-paid meter |  |  | Pre-shipment inspection of 124000 nos. single phase smart pre-payment meter is completed on 05/12/2018 and production of 6000 nos. three phase smart pre-payment meter is going on under package-1.
|  |  |  | (i) Single Phase | Nos. | 486000
|  |  |  | (ii) Three Phase | Nos. | 14000
|  |  |  | Financial Progress | FY 2018-19 | 1.25% | Overall |  | 1.25%
|  |  |  | Physical Progress | FY 2018-19 | 23.08% | Overall |  | 23.08%

## Upcoming
WEST ZONE POWER DISTRIBUTION COMPANY LTD. (An Enterprise of Bangladesh Power Development Board) Bidyut Bhaban, Boyra Main Road, Khulna.Ph: 041-730484, Fax: 041-731786 Project Status
Upcoming Projects: | [5 empty] | 99600
Sl. No | Name of the Project and Period | Goals | Program/Project wise indicative cost (Cr. Tk & Million US$) | Financed by | Progress
1 | Modernization of Power Distribution Smart Grid Phase-I, Sub-station Rehabilitation and Implementation of Supervisory Control and Data Aquisition (SCADA) System Project in West Zone Area. July’18 – June’22 | To automate all of the Substation of WZPDCL under SCADA system upto 11KV feeders. | Initially predicted cost of the project is...  Total Cost: 996.00 Crore BDT (97 Million Uro )  PA : 697.00 Crore BDT (68 Million Uro )  GoB : 199.00 Crore BDT (19 Million Uro)  WZPDCL: 99.00 Crore BDT (10 Million Uro) Actual project cost will be determined by feasibility study. | KFW |  120MUro has been confirmed for project aid and 2.2MUro confirmed for technical assistance project for WZPDCL and BREB which was decided at the inter-govenment negotiation meeting between Bangladesh govt. and German govt. on 26.10.2016  A Contract has been signed with Lahmeyer International GmbH (Consultant) for executing feasibility study of the project on 26/09/2018.  Kick-off Meeting has been held on 07/11/2018  Training on " Grid Modeling and Network Analysis" has been started as part of FS from 25.11.2018 | 1 Uro=102.54 BDT(Date of 14.03.2018) | 0.47588
2 | Assessment on System Planning, Project Design and Capacity Building in West Zone Area July’18-Nov’19 |  To Assess whole WZPDCL System  To make feasibility study report for underground power distribution system in Khulna, Jessore and Barisal.  To make feasibility study report/implement GIS mapping in khulna city area.  Capacity building of Human Resource (Training). | Initially predicted cost of the project is…  Total: 866.19 Lakh Taka (1.09 Million of US$)  GOB: 184.41 (0.23 Million of US$)  WZPDCL: 176.05 (0.22 Million of US$)  P.A : 505.73 (0.64 Million of US$) Actual project cost will be determined by ADB regarding approval of concept paper. | ADB |  PTAPP has been approved by principle on 04.04.2017 by honorable Planning Minister.  ADB has responded positively to finance the proposed project on their Aide Memoire dated on 29.01.2017.  ADB is interested to one of the scope that is to make feasibility study (FS) report for underground power distribution system in Khulna, Jessore and Barisal. For this FS, 0.5 million USD has been approved by ADB. Now, ADB is making need-based ToR as well as tender document collaborating with west zone which is supposed to be tendered at november'2018. Institutional Analysis of WZPDCL has been done by WZPDCL on 20 September 2018. .
3 | Smart Prepayment Metering Project For West Zone Power Distribution Company Ltd. (WZPDCL) Area (phase-II) July/17-December/18 |  To install 9,00,000 nos of Pre-paid meter, where Single Phase meter: 8,80,000 nos. Three Phase meter: 20,000 nos | Initially predicted cost of the project is...  Total: 972.89 Crore BDT (114.82 Million of US$)  GOB: 262.44 Crore BDT (30.97 Million of US$)  WZPDCL: 53.22 Crore BDT (6.28 Million of US$)  P.A : 657.21 Crore BDT (77.57 Million of US$) | AIIB |  AIIB has shown their interest on the meeting at WZPDCL Liaision office on 05.07.2018.  PDPP was submitted to Power Division on 11.07.2018 and Power Division has sent to Planning Commission on 23.07.2018. On 19.08.2018 Planning Commission has returned the PDPP and adviced to increase the proportion of organisational funding to a logical extent and resubmit the recast PDPP.
4 | Underground Power Distribution System Project in West Zone Area (Phase-1) July’18- June’21 |  To accommodate clean metropolitan and improved power distribution network of WZPDCL by imposing underground GIS S/S and distribution lines in Khulna, Jessore & Barisal city. | Initially predicted cost of the project is...  Estimated capital costs: 7041.51 Crore BDT (853 Million of US$)  Estimated yearly operation costs: 33.02 Crore BDT (4 Million US$)  Total cost: 7701.92 Crore BDT (933 Million US$ ) | PPP |  ADB has enlisted this project into their COBP (Country Operation Business Plan) to finance 200 Million USD at 2020.  Moreover, a project proposal under PPP (G2G with Japan) has been sent to Power Division on 26.12.2017. | 1 Dollar=82.55 BDT Taka(Date of 14.03.2018)
5 | GIS Mapping of WZPDCL area. July’18- June’21 |  To make GIS Mapping into whole WZPDCL area |  Total: 28.75 Crore BDT (3.42 Million of US$) | - |  To establish GIS mapping in Khulna city as a pilot project fund searching is going on. Training on GIS at WZPDCL training centre has been completed from 11.08.2018 to 15.08.2018.  Draft Scope of work, Cost Estimation, Terms of reference(ToR) and advertisement for invitation of Expression of Interest (EoI) has been prepared.
6 | Prepayment Meter Manufacturing Plant, WZPDCL July’18 – June’19 |  To establish a Pre-payment Meter Factory in khulna city. |  Total: 28.60 Crore BDT (3.4 Million of US$) | - | WZPDCL has signed a Joint Venture Agreement (JVA) with Hexing Electrical Co. Ltd, China to form a joint venture company named "Bangladesh Smart Electricals Company Ltd." on 21 October,2018. Trial production will be started from January'2019. | 2860
7 | Installation of Transformer Manufacturing Plant and Upgradation of Zonal Repairing Shop in West Zone Area. Jul’18 – Jun’20 |  To install a new Transformer Manufacturing Plant in Khulna  Renovation of existing two ZRS at Jessore and Barisal | Initially predicted cost of the project is...  Total: 100.00 Crore BDT (12.11 Million of US$)  GOB: 30.00 Crore BDT (3.634 Million of US$)  P.A : 70.00 Crore BDT (8.479 Million of US$) Actual project cost will be determined by feasibility study. | PPP | A project proposal under PPP has been sent to Power Division on 04.10.2017
8 | Upgradation of Distribution System of WZPDCL |  Erection of new distribution lines in WZPDCL area.  Renovation of existing non-standard distribution lines of WZPDCL. | To be determined | _ | Feasibility study of the project is under progress.

## Future
WEST ZONE POWER DISTRIBUTION COMPANY LTD. (An Enterprise of Bangladesh Power Development Board) Bidyut Bhaban, Boyra Main Road, Khulna.Ph: 041-730484, Fax: 041-731786 Project Status
Future Projects:
Sl. No | Name of the Project with Period | Goals | Program/Project wise indicative cost (Lakh Tk & Million US$) | Financed by | Remarks/Progress
1 | Distribution System Improvement Project up to ‘2030 (Phase-1). July’21 – June’24 | To accommodate future load growth upto 2025 of power distribution network of WZPDCL. | To Be Determined | To Be Determined |  For expansion of distribution line and installation of substaions, in-house feasibility study is going on according to the plasusible demand of electricty forcasted on PSMP and SDG
2 | Distribution System Improvement Project up to ‘2030 (Phase-2) July’26 – June’29 | To accommodate future load growth upto 2030 of power distribution network of WZPDCL. | To Be Determined | To Be Determined |  In order to expand distribution line and install substaions, in-house feasibility study is going on according to the plasusible demand of electricty forcasted on PSMP and SDG | 11631